## Overview
No | Feature ID | Name | Description | Start Date | End Date | Status | Total Tasks | Done Tasks | Progress %
1 | 001-eutr-steps | EUTR Steps Management | CRUD screen for managing steps in the EUTR process, per the design at design/eutr_steps.md; the backend API already exists at api/eutr-steps. | 2026-07-01 |  | In Progress | 30 | 28 | 93.33%
2 | 002-eutr-masters | EUTR Masters Management | New EUTR master feature with CRUD and Import per the eutr_masters design, storing data in eutr_master_documents keyed by eutr_steps.Id and displaying the step name on the grid; add uses a step select box plus a Prefix field, and Excel import/export use 2 columns (step name, prefix). | 2026-07-02 |  | In Progress | 65 | 61 | 93.85%
3 | 003-eutr-templates | EUTR Templates Management | New feature based on docs/design/eutr/eutr_templates_overview.md: manage EUTR templates with a list grid, create a new template with a recursive step tree, delete, and import. | 2026-07-03 |  | In Progress | 396 | 344 | 86.87%
4 | 004-eutr-documents | EUTR Documents Management | New eutr-documents feature, built per the design overview at Eutr/docs/design/eutr/eutr_documents_overview.md, for managing EUTR compliance documents (upload, classify by Type/Step, and track conditions). | 2026-07-09 |  | In Progress | 312 | 285 | 91.35%
5 | 005-eutr-sales-orders | EUTR Sales Orders Management | A new EUTR Sales Orders feature whose frontend loads data from ComplianceSys.Api controllers via POST /reference with reftype=11, showing Sales ID, Customer, Customer name and Delivery date columns, with Template and Progress columns initially fixed as demo data. | 2026-07-14 |  | In Progress | 344 | 299 | 86.92%
6 | 006-eutr-reference-types | EUTR Reference Types Management | A new CRUD feature for EUTR reference types, storing data in the eutr_reference_types table already added to the database, per the eutr_db design file. | 2026-07-23 |  | In Progress | 68 | 65 | 95.59%
11 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | A new backend controller, modeled on the existing compliance notification controller, exposing a test-so-template-sync endpoint that pulls ERP Sales Order Template reference data into a local purchase-attachment mapping table, skipping sales orders that already have one. | 2026-08-13 |  | In Progress | 33 | 30 | 90.91%
12 | 012-eutr-purchase-orders | EUTR Purchase Orders | A new screen displaying purchase order reference data with columns Purch id, Vendor code, Vendor name, Template, Progress, and a View action; Progress compares the template's steps against recorded documents, and View opens a per-PO document-management screen adapted from the Sales Order Map File screen. | 2026-08-14 |  | In Progress | 31 | 29 | 93.55%
13 | 013-compl-synchronize-data | Compliance Synchronize Data (Sales Line + Variant Attributes) | A new compl-synchronize-data feature, modeled on EutrSynchronizeDataController, that pulls Sales Line data from the ERP, enriches it with Product reference fields, then derives distinct Product/Config combinations and syncs their Variant Attribute data locally. | 2026-08-19 |  | In Progress | 40 | 38 | 95%

## User Stories
No | Feature ID | Feature Name | Story | Title | Priority | Description | Start Date | End Date | Status | Total Tasks | Done Tasks | Progress %
1 | 001-eutr-steps | EUTR Steps Management | US1 | View and search step list | P1 | View a paginated, searchable table of EUTR steps showing step name, creator, and creation date. | 2026-07-01 | 2026-08-13 | Done | 5 | 5 | 100%
2 | 001-eutr-steps | EUTR Steps Management | US2 | Add a new step | P1 | Create a new step via a form, blocking empty names or names duplicating an existing step (case/whitespace-insensitive). | 2026-07-01 | 2026-08-13 | Done | 3 | 3 | 100%
3 | 001-eutr-steps | EUTR Steps Management | US3 | Edit a step | P2 | Edit an existing step's name, blocking duplicates with other steps while allowing the record to keep its own name. | 2026-07-01 | 2026-08-13 | Done | 2 | 2 | 100%
4 | 001-eutr-steps | EUTR Steps Management | US4 | Delete step(s) | P2 | Delete a single step with confirmation, or delete multiple selected steps at once. | 2026-07-01 | 2026-08-13 | Done | 2 | 2 | 100%
5 | 002-eutr-masters | EUTR Masters Management | US1 | View and search master document list | P1 | View a paginated, searchable table of EUTR master documents showing step name (resolved from the step catalog), prefix, creator and creation date. | 2026-07-02 | 2026-08-13 | Done | 6 | 6 | 100%
6 | 002-eutr-masters | EUTR Masters Management | US2 | Add a new master document | P1 | Create a master document by selecting a step from a dropdown and entering a Prefix, blocked when the Prefix already exists system-wide. | 2026-07-02 | 2026-08-13 | Done | 5 | 5 | 100%
7 | 002-eutr-masters | EUTR Masters Management | US3 | Edit a master document | P2 | Edit a master document's step and/or prefix, blocked when the new prefix duplicates another existing record. | 2026-07-02 | 2026-08-13 | Done | 5 | 5 | 100%
8 | 002-eutr-masters | EUTR Masters Management | US4 | Delete master document(s) | P2 | Delete a single record with confirmation, or delete multiple selected records at once. | 2026-07-02 | 2026-08-13 | Done | 4 | 4 | 100%
9 | 002-eutr-masters | EUTR Masters Management | US5 | Import from Excel | P2 | Bulk-import master documents from a 2-column Excel file (step name, prefix), partially importing valid rows while skipping and reporting errored/duplicate rows. | 2026-07-02 | 2026-08-13 | Done | 9 | 9 | 100%
10 | 002-eutr-masters | EUTR Masters Management | US6 | Export to Excel | P2 | Export the master document list to a 2-column Excel file (Step name, Prefix) whose format round-trips back into Import. | 2026-07-02 | 2026-08-13 | Done | 7 | 7 | 100%
11 | 003-eutr-templates | EUTR Templates Management | US1 | View EUTR Templates list | P1 | View and search the paginated EUTR templates list showing Code/Name, Status, Version, Default, Steps count, and Edit/Clone/Apply/Delete actions. | 2026-07-03 | 2026-08-18 | Done | 34 | 34 | 100%
12 | 003-eutr-templates | EUTR Templates Management | US2 | Quick-create a new template | P1 | Create a new template quickly via a 3-field dialog (Name, Alert for, Set as default) with no Vendor field or step tree. | 2026-07-03 | 2026-08-18 | Done | 54 | 54 | 100%
13 | 003-eutr-templates | EUTR Templates Management | US3 | Edit template | P2 | Edit a template's header fields and step tree via TemplateBuilderPage, with versioning tied to the Draft/Approved status lifecycle. | 2026-07-03 | 2026-08-18 | Done | 66 | 66 | 100%
14 | 003-eutr-templates | EUTR Templates Management | US4 | Delete template (soft delete) | P2 | Soft-delete templates individually or in bulk with confirmation, preserving the underlying data for traceability. | 2026-07-03 | 2026-08-18 | Done | 6 | 6 | 100%
15 | 003-eutr-templates | EUTR Templates Management | US5 | Import templates (deferred) | P3 | Bulk-import templates from a file with success/failure result reporting; deferred from the Table-layout UI in Update 10. | 2026-07-03 | 2026-08-18 | Done | 10 | 10 | 100%
16 | 003-eutr-templates | EUTR Templates Management | US6 | Apply template to Vendor (Apply to Customer) | P2 | Apply a template to one or more Vendors over an effective date range via a dedicated Apply to Customer screen, including Import/Export. | 2026-07-03 | 2026-08-18 | Done | 33 | 33 | 100%
17 | 003-eutr-templates | EUTR Templates Management | US7 | Clone template | P2 | Clone an existing template's full step tree and vendor mappings into a brand-new, independent template. | 2026-07-03 | 2026-08-18 | Done | 12 | 12 | 100%
18 | 003-eutr-templates | EUTR Templates Management | US8 | Approve template | P2 | Approve a Draft template, marking it read-only until a change is requested. | 2026-07-03 | 2026-08-18 | Done | 11 | 11 | 100%
19 | 003-eutr-templates | EUTR Templates Management | US9 | Request change (revert Approved template to Draft) | P2 | Request a change on an Approved template, creating a new Draft version while preserving the Approved record as immutable history. | 2026-07-03 | 2026-08-18 | Done | 3 | 3 | 100%
20 | 004-eutr-documents | EUTR Documents Management | US1 | View list of EUTR documents | P1 | Display a paginated table of EUTR documents with File name, Step name, Invoice, Conditions, Type, Valid dates, Created by/date and Action (Edit/Delete/View) columns. | 2026-07-09 |  | In Progress | 30 | 27 | 90%
21 | 004-eutr-documents | EUTR Documents Management | US2 | Add a new document via the Add popup (Type/Step/Value/Valid dates/Upload) | P1 | Add new documents through a unified 'Add EUTR documents' popup that captures Type, Step, Value chips, Valid from/to dates, and uploads files to SharePoint, creating eutr_documents and eutr_references records. | 2026-07-09 |  | In Progress | 84 | 75 | 89.29%
22 | 004-eutr-documents | EUTR Documents Management | US3 | Edit a document via the same Add popup, with Type locked | P2 | Edit an existing document by reopening the same popup in edit mode with Type locked, Step and Valid dates editable, and chip values editable for non-PO types. | 2026-07-09 |  | In Progress | 69 | 64 | 92.75%
23 | 004-eutr-documents | EUTR Documents Management | US4 | Delete a document | P2 | Delete one or multiple documents, cascading deletion of all related eutr_references records within the same transaction. | 2026-07-09 |  | In Progress | 9 | 8 | 88.89%
24 | 004-eutr-documents | EUTR Documents Management | US5 | View the actual file via the View icon | P2 | Open a preview popup of the actual uploaded file via a View icon, or show it disabled with a tooltip when no file exists. | 2026-07-09 |  | In Progress | 13 | 12 | 92.31%
25 | 004-eutr-documents | EUTR Documents Management | US6 | Search/filter the list via a search box | P2 | Filter the main document list using a search box with Type, Step name, and Conditions criteria combined with AND logic. | 2026-07-09 |  | In Progress | 46 | 44 | 95.65%
26 | 004-eutr-documents | EUTR Documents Management | US7 | (unlabeled) |  |  | 2026-07-09 |  | In Progress | 20 | 17 | 85%
27 | 005-eutr-sales-orders | EUTR Sales Orders Management | US1 | View the EUTR Sales Orders list | P1 | Shows a table of sales orders from ERP reference data (Sales ID, Customer, Customer name, Delivery date, Template, Progress) with a per-row Download button. | 2026-07-14 |  | In Progress | 39 | 33 | 84.62%
28 | 005-eutr-sales-orders | EUTR Sales Orders Management | US2 | Search sales orders by Sales ID or Customer | P2 | Lets users filter the list by keyword and restores search/page state when returning from Map File or View via Back. | 2026-07-14 | 2026-08-13 | Done | 3 | 3 | 100%
29 | 005-eutr-sales-orders | EUTR Sales Orders Management | US3 | Paginate through a long list | P3 | Lets users page through the sales order list when it exceeds one page of results. | 2026-07-14 | 2026-08-13 | Done | 2 | 2 | 100%
30 | 005-eutr-sales-orders | EUTR Sales Orders Management | US4 | Select Purchase Orders and view the document set for a Sales Order (Map File) | P2 | Lets users pick real POs from D365, save the PO mapping, and manage/upload/edit/view mapped compliance documents against the template step tree. | 2026-07-14 | 2026-08-13 | Done | 60 | 60 | 100%
31 | 005-eutr-sales-orders | EUTR Sales Orders Management | US5 | View a read-only EUTR document overview for a Sales Order (View Sales Order) | P2 | Read-only overview of a Sales Order's selected POs, per-template checklist progress, available files panel, validation summary, and zip download. | 2026-07-14 | 2026-08-13 | Done | 60 | 60 | 100%
32 | 006-eutr-reference-types | EUTR Reference Types Management | US1 | View and search the reference type list | P1 | Shows a paginated table of reference types (Name, Created by, Created date) with keyword search. | 2026-07-23 | 2026-07-24 | Done | 5 | 5 | 100%
33 | 006-eutr-reference-types | EUTR Reference Types Management | US2 | Add a new reference type | P1 | Lets a user create a new reference type by entering a name, with created-by/date recorded automatically. | 2026-07-23 | 2026-07-24 | Done | 2 | 2 | 100%
34 | 006-eutr-reference-types | EUTR Reference Types Management | US3 | Edit a reference type | P2 | Lets a user edit an existing reference type's name. | 2026-07-23 | 2026-07-24 | Done | 1 | 1 | 100%
35 | 006-eutr-reference-types | EUTR Reference Types Management | US4 | Delete a reference type | P2 | Lets a user delete one or many reference types with confirmation, blocking deletion when still referenced elsewhere. | 2026-07-23 | 2026-07-24 | Done | 6 | 6 | 100%
36 | 006-eutr-reference-types | EUTR Reference Types Management | US5 | Assign steps to a reference type | P2 | Lets a user assign/edit/remove EUTR steps for a reference type on a dedicated screen, storing rows in eutr_reference_type_details. | 2026-07-23 | 2026-07-24 | Done | 3 | 3 | 100%
51 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | US1 | Populate purchase attachment records from the ERP's Sales Order Template data | P1 | Syncs ERP Sales Order Template reference data into local mapping records, creating one per unmapped sales order and skipping ones already mapped. | 2026-08-13 | 2026-08-18 | Done | 6 | 6 | 100%
52 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | US2 | Detect and alert on purchase orders with incomplete EUTR documentation | P1 | Scans every ERP purchase order for a missing template, missing document folder, or missing template steps, stores flagged results, and emails each responsible group an Excel report. | 2026-08-13 | 2026-08-18 | Done | 13 | 13 | 100%
53 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | US3 | Push eligible local Templates and their active Vendor mappings out to the ERP | P1 | Pushes approved, active local Templates and their currently active Vendor mappings to the ERP, removing and recreating ERP records each run, with a blank Vendor Code when no mapping exists. | 2026-08-13 | 2026-08-18 | Done | 9 | 9 | 100%
54 | 012-eutr-purchase-orders | EUTR Purchase Orders | US1 | View the list of EUTR Purchase Orders | P1 | Displays a table of ERP purchase orders with Purch id, Vendor code, Vendor name, Template, Progress (based on required template steps with documents), and a View action. | 2026-08-14 | 2026-08-14 | Done | 7 | 7 | 100%
55 | 012-eutr-purchase-orders | EUTR Purchase Orders | US2 | View and manage compliance documents for a Purchase Order | P1 | Opens a detail screen per purchase order, modeled on the Sales Order Map File screen minus PO selection, showing header info, template step tree, available files, and Upload/Edit actions. | 2026-08-14 | 2026-08-14 | Done | 8 | 8 | 100%
56 | 012-eutr-purchase-orders | EUTR Purchase Orders | US3 | Search Purchase Orders by Purch Id or Vendor | P2 | Adds a search box to filter the purchase order list by Purch Id, Vendor code, or Vendor name. | 2026-08-14 | 2026-08-14 | Done | 3 | 3 | 100%
59 | 014-map-product-test | Map for Product Test — Complete Record Visibility | US1 | See every eligible compliance master in the list | P1 | Ensure every compliance master record eligible for the tab appears reliably via both scroll and search. | 2026-08-19 | 2026-08-19 | Done | 9 | 9 | 100%
60 | 014-map-product-test | Map for Product Test — Complete Record Visibility | US2 | Understand why a record is not mapped | P2 | Confirm records genuinely out of scope for the tab are correctly excluded, distinguishing correct behavior from a defect. | 2026-08-19 | 2026-08-19 | Done | 3 | 3 | 100%

## Tasks
No | Feature ID | Feature Name | Phase | Story | Task ID | Description | Status
1 | 001-eutr-steps | EUTR Steps Management | Phase 1: Setup & Verify |  | T001 | Verify backend contract api/eutr-steps matches the API contract doc; confirm 7 endpoints + EutrSteps.* policies. Do not modify backend. | Done
2 | 001-eutr-steps | EUTR Steps Management | Phase 1: Setup & Verify |  | T002 | Review the document-type feature to learn the convention across all layers. | Done
3 | 001-eutr-steps | EUTR Steps Management | Phase 1: Setup & Verify |  | T003 | Confirm menu has (or add) the eutr-steps menu code and permissions for the test user. | Done
4 | 001-eutr-steps | EUTR Steps Management | Phase 2: Foundational |  | T004 | Create domain entity EutrStep.js. | Done
5 | 001-eutr-steps | EUTR Steps Management | Phase 2: Foundational |  | T005 | Create IEutrStepRepository.js interface with CRUD methods. | Done
6 | 001-eutr-steps | EUTR Steps Management | Phase 2: Foundational |  | T006 | Create eutrStepApi.js infrastructure API client mapping to backend endpoints. | Done
7 | 001-eutr-steps | EUTR Steps Management | Phase 2: Foundational |  | T007 | Create RestEutrStepRepository.js implementing the repository interface. | Done
8 | 001-eutr-steps | EUTR Steps Management | Phase 2: Foundational |  | T008 | Register RestEutrStepRepository in the DI container. | Done
9 | 001-eutr-steps | EUTR Steps Management | Phase 2: Foundational |  | T009 | Create 6 use cases (Create/Update/Delete/DeleteMulti/GetAll/GetPaging) for eutr-step. | Done
10 | 001-eutr-steps | EUTR Steps Management | Phase 3: User Story 1 | US1 | T010 | Create useEutrStepData.js hook for paginated/filterable data fetching. | Done
11 | 001-eutr-steps | EUTR Steps Management | Phase 3: User Story 1 | US1 | T011 | Create useEutrStepColumns.jsx hook defining grid columns (name, createdBy, createdDate, actions). | Done
12 | 001-eutr-steps | EUTR Steps Management | Phase 3: User Story 1 | US1 | T012 | Create eutr-steps/index.jsx page with DataGrid, search, pagination, breadcrumb. | Done
13 | 001-eutr-steps | EUTR Steps Management | Phase 3: User Story 1 | US1 | T013 | Add route for eutr-steps page in RouteResolver.jsx. | Done
14 | 001-eutr-steps | EUTR Steps Management | Phase 3: User Story 1 | US1 | T014 | Add menu item for EUTR steps in ComplianceSystem.jsx. | Done
15 | 001-eutr-steps | EUTR Steps Management | Phase 4: User Story 2 | US2 | T015 | Create EutrStepModal.jsx with a single Step name field and validation. | Done
16 | 001-eutr-steps | EUTR Steps Management | Phase 4: User Story 2 | US2 | T016 | Wire the Add button and Create flow into index.jsx with success feedback. | Done
17 | 001-eutr-steps | EUTR Steps Management | Phase 5: User Story 3 | US3 | T017 | Wire the Edit flow (modal prefill + Update use case) into index.jsx. | Done
18 | 001-eutr-steps | EUTR Steps Management | Phase 6: User Story 4 | US4 | T018 | Create EutrStepActionCell.jsx with permission-gated Edit/Delete buttons. | Done
19 | 001-eutr-steps | EUTR Steps Management | Phase 6: User Story 4 | US4 | T019 | Wire single Delete (with confirmation) and bulk DeleteMulti into index.jsx. | Done
20 | 001-eutr-steps | EUTR Steps Management | Phase 7: Polish & Cross-cutting |  | T020 | Review all user-facing UI text is in English (labels, buttons, messages, empty states). | Done
21 | 001-eutr-steps | EUTR Steps Management | Phase 7: Polish & Cross-cutting |  | T021 | Verify Create/Update/Delete buttons are hidden/disabled correctly per permissionList. | Done
22 | 001-eutr-steps | EUTR Steps Management | Phase 7: Polish & Cross-cutting |  | T022 | Run npm lint in compliance-client and fix warnings in new files. | Done
23 | 001-eutr-steps | EUTR Steps Management | Phase 7: Polish & Cross-cutting |  | T023 | Manually test 6 scenarios per quickstart.md (requires running backend + logged-in user). | To do
24 | 001-eutr-steps | EUTR Steps Management | Phase 8: Prevent duplicate step name (FR-005a) |  | T024 | Add ExistsNameAsync(name, excludeId) method to IEutrStepRepository.cs interface. | Done
25 | 001-eutr-steps | EUTR Steps Management | Phase 8: Prevent duplicate step name (FR-005a) |  | T025 | Create EutrStepRepository.cs implementing ExistsNameAsync with case/trim-insensitive SQL check. | Done
26 | 001-eutr-steps | EUTR Steps Management | Phase 8: Prevent duplicate step name (FR-005a) |  | T026 | Register IEutrStepRepository/EutrStepRepository in backend DI. | Done
27 | 001-eutr-steps | EUTR Steps Management | Phase 8: Prevent duplicate step name (FR-005a) |  | T027 | Update EutrStepService.cs to check ExistsNameAsync in AddAsync/UpdateAsync and throw on duplicate. | Done
28 | 001-eutr-steps | EUTR Steps Management | Phase 8: Prevent duplicate step name (FR-005a) | US2 | T028 | Fix Create catch block in index.jsx to surface duplicate-name error via snackbar. | Done
29 | 001-eutr-steps | EUTR Steps Management | Phase 8: Prevent duplicate step name (FR-005a) | US3 | T029 | Fix Update catch block in index.jsx the same way as Create (shared catch block). | Done
30 | 001-eutr-steps | EUTR Steps Management | Phase 8: Prevent duplicate step name (FR-005a) |  | T030 | Manually test duplicate-name scenarios 7 & 8 per quickstart.md. | To do
31 | 002-eutr-masters | EUTR Masters Management | Phase 1: Setup |  | T001 | Confirm the eutr_master_documents table exists per the DB design; create it if missing. | To do
32 | 002-eutr-masters | EUTR Masters Management | Phase 1: Setup |  | T002 | Create frontend feature folder structure for eutr-masters (pages, hooks, components, usecases). | Done
33 | 002-eutr-masters | EUTR Masters Management | Phase 2: Foundational |  | T003 | Create EutrMastersDocument.cs entity (Id, StepId, Prefix + audit fields). | Done
34 | 002-eutr-masters | EUTR Masters Management | Phase 2: Foundational |  | T004 | Create EutrMastersRequestDto.cs (StepId, Prefix). | Done
35 | 002-eutr-masters | EUTR Masters Management | Phase 2: Foundational |  | T005 | Create EutrMastersResponseDto.cs (entity + StepName). | Done
36 | 002-eutr-masters | EUTR Masters Management | Phase 2: Foundational |  | T006 | Create EutrMastersRequestDtoValidator.cs (StepId>0, Prefix not empty). | Done
37 | 002-eutr-masters | EUTR Masters Management | Phase 2: Foundational |  | T007 | Add AutoMapper mappings for EutrMastersRequestDto/EutrMastersDocument/EutrMastersResponseDto. | Done
38 | 002-eutr-masters | EUTR Masters Management | Phase 2: Foundational |  | T008 | Create IEutrMastersService.cs interface extending base service plus GetPagedAsync. | Done
39 | 002-eutr-masters | EUTR Masters Management | Phase 2: Foundational |  | T009 | Create EutrMastersService.cs extending BaseService with CRUD wiring. | Done
40 | 002-eutr-masters | EUTR Masters Management | Phase 2: Foundational |  | T010 | Create EutrMastersController.cs skeleton (route, auth, DI). | Done
41 | 002-eutr-masters | EUTR Masters Management | Phase 2: Foundational |  | T011 | Register IEutrMastersService and its validator in backend DI. | Done
42 | 002-eutr-masters | EUTR Masters Management | Phase 2: Foundational |  | T012 | Create EutrMasters.js domain entity on the frontend. | Done
43 | 002-eutr-masters | EUTR Masters Management | Phase 2: Foundational |  | T013 | Create IEutrMastersRepository.js interface (CRUD + import). | Done
44 | 002-eutr-masters | EUTR Masters Management | Phase 2: Foundational |  | T014 | Create eutrMastersApi.js infrastructure API client. | Done
45 | 002-eutr-masters | EUTR Masters Management | Phase 2: Foundational |  | T015 | Create RestEutrMastersRepository.js implementing the repository interface. | Done
46 | 002-eutr-masters | EUTR Masters Management | Phase 2: Foundational |  | T016 | Register RestEutrMastersRepository in frontend DI. | Done
47 | 002-eutr-masters | EUTR Masters Management | Phase 2: Foundational |  | T017 | Add lazy import + componentMap entry for eutr-masters in RouteResolver.jsx. | Done
48 | 002-eutr-masters | EUTR Masters Management | Phase 2: Foundational |  | T018 | Add EUTR masters menu item under the EUTR parent menu. | Done
49 | 002-eutr-masters | EUTR Masters Management | Phase 2: Foundational |  | T019 | Create page shell eutr-masters/index.jsx with breadcrumb and empty DataGrid/toolbar. | Done
50 | 002-eutr-masters | EUTR Masters Management | Phase 3: User Story 1 | US1 | T020 | Override GetPagedAsync with a SQL JOIN to eutr_steps to resolve and filter by StepName. | Done
51 | 002-eutr-masters | EUTR Masters Management | Phase 3: User Story 1 | US1 | T021 | Add POST /get-all (paged/filtered) and GET /get-by-id/{id} controller actions. | Done
52 | 002-eutr-masters | EUTR Masters Management | Phase 3: User Story 1 | US1 | T022 | Create GetPagingEutrMastersUseCase.js. | Done
53 | 002-eutr-masters | EUTR Masters Management | Phase 3: User Story 1 | US1 | T023 | Create useEutrMastersData.js hook for paging/filtering/sorting. | Done
54 | 002-eutr-masters | EUTR Masters Management | Phase 3: User Story 1 | US1 | T024 | Create useEutrMastersColumns.jsx hook (stepName, prefix, createdBy, createdDate columns). | Done
55 | 002-eutr-masters | EUTR Masters Management | Phase 3: User Story 1 | US1 | T025 | Wire server-mode DataGrid with search/pagination into eutr-masters/index.jsx. | Done
56 | 002-eutr-masters | EUTR Masters Management | Phase 4: User Story 2 | US2 | T026 | Override AddAsync to reject duplicate (StepId, Prefix) pairs before insert (later superseded to Prefix-only). | Done
57 | 002-eutr-masters | EUTR Masters Management | Phase 4: User Story 2 | US2 | T027 | Add POST / create controller action with Create policy. | Done
58 | 002-eutr-masters | EUTR Masters Management | Phase 4: User Story 2 | US2 | T028 | Create CreateEutrMastersUseCase.js. | Done
59 | 002-eutr-masters | EUTR Masters Management | Phase 4: User Story 2 | US2 | T029 | Create EutrMastersModal.jsx with a Step select/autocomplete and Prefix text field. | Done
60 | 002-eutr-masters | EUTR Masters Management | Phase 4: User Story 2 | US2 | T030 | Wire Add button + modal + Create use case + duplicate-warning display in index.jsx. | Done
61 | 002-eutr-masters | EUTR Masters Management | Phase 5: User Story 3 | US3 | T031 | Override UpdateAsync to reject duplicate (StepId, Prefix) excluding the current record (later superseded). | Done
62 | 002-eutr-masters | EUTR Masters Management | Phase 5: User Story 3 | US3 | T032 | Add PUT /{id} update controller action with Update policy. | Done
63 | 002-eutr-masters | EUTR Masters Management | Phase 5: User Story 3 | US3 | T033 | Create UpdateEutrMastersUseCase.js. | Done
64 | 002-eutr-masters | EUTR Masters Management | Phase 5: User Story 3 | US3 | T034 | Create EutrMastersActionCell.jsx with permission-gated Edit/Delete buttons. | Done
65 | 002-eutr-masters | EUTR Masters Management | Phase 5: User Story 3 | US3 | T035 | Extend modal for edit mode (prefill via getById) and wire the Edit flow. | Done
66 | 002-eutr-masters | EUTR Masters Management | Phase 6: User Story 4 | US4 | T036 | Add DELETE /{id} and POST /delete-multi controller actions. | Done
67 | 002-eutr-masters | EUTR Masters Management | Phase 6: User Story 4 | US4 | T037 | Create DeleteEutrMastersUseCase.js. | Done
68 | 002-eutr-masters | EUTR Masters Management | Phase 6: User Story 4 | US4 | T038 | Create DeleteMultiEutrMastersUseCase.js. | Done
69 | 002-eutr-masters | EUTR Masters Management | Phase 6: User Story 4 | US4 | T039 | Wire delete confirmation dialog and bulk-delete-by-selection into index.jsx. | Done
70 | 002-eutr-masters | EUTR Masters Management | Phase 7: User Story 5 | US5 | T040 | Create ImportEutrMastersResultDto.cs with success/fail/duplicate counts and row-level errors. | Done
71 | 002-eutr-masters | EUTR Masters Management | Phase 7: User Story 5 | US5 | T041 | Create IEutrMastersImportService.cs interface. | Done
72 | 002-eutr-masters | EUTR Masters Management | Phase 7: User Story 5 | US5 | T042 | Create EutrMastersImportService.cs using ClosedXML to parse and partially import rows (dedupe key later superseded to Prefix-only). | Done
73 | 002-eutr-masters | EUTR Masters Management | Phase 7: User Story 5 | US5 | T043 | Register IEutrMastersImportService in backend DI. | Done
74 | 002-eutr-masters | EUTR Masters Management | Phase 7: User Story 5 | US5 | T044 | Add POST /import controller action accepting an uploaded file. | Done
75 | 002-eutr-masters | EUTR Masters Management | Phase 7: User Story 5 | US5 | T045 | Create ImportEutrMastersUseCase.js. | Done
76 | 002-eutr-masters | EUTR Masters Management | Phase 7: User Story 5 | US5 | T046 | Add import(file) multipart call to the API client/repository/interface. | Done
77 | 002-eutr-masters | EUTR Masters Management | Phase 7: User Story 5 | US5 | T047 | Create ImportResultDialog.jsx showing success/fail/duplicate rows with reasons. | Done
78 | 002-eutr-masters | EUTR Masters Management | Phase 7: User Story 5 | US5 | T048 | Wire Import button, file input, result dialog and grid refresh into index.jsx. | Done
79 | 002-eutr-masters | EUTR Masters Management | Phase 9: Polish & Cross-Cutting Concerns |  | T049 | Review all UI text is in English (labels, buttons, messages, empty states, import report). | Done
80 | 002-eutr-masters | EUTR Masters Management | Phase 9: Polish & Cross-Cutting Concerns |  | T050 | Handle empty state, network/server errors without corrupting data, and loading states. | Done
81 | 002-eutr-masters | EUTR Masters Management | Phase 9: Polish & Cross-Cutting Concerns |  | T051 | Gate Add/Edit/Delete/Import per permissionList from the menu. | Done
82 | 002-eutr-masters | EUTR Masters Management | Phase 9: Polish & Cross-Cutting Concerns |  | T052 | Run manual testing per quickstart.md (9 scenarios including Export) and fix issues found. | To do
83 | 002-eutr-masters | EUTR Masters Management | Phase 8: User Story 6 | US6 | T054 | Create IEutrMastersExportService.cs interface. | Done
84 | 002-eutr-masters | EUTR Masters Management | Phase 8: User Story 6 | US6 | T055 | Create EutrMastersExportService.cs generating an Excel workbook (header row always present) via ClosedXML. | Done
85 | 002-eutr-masters | EUTR Masters Management | Phase 8: User Story 6 | US6 | T056 | Register IEutrMastersExportService in backend DI. | Done
86 | 002-eutr-masters | EUTR Masters Management | Phase 8: User Story 6 | US6 | T057 | Add GET /export controller action returning the generated Excel file. | Done
87 | 002-eutr-masters | EUTR Masters Management | Phase 8: User Story 6 | US6 | T058 | Create ExportEutrMastersUseCase.js triggering a file download from the response blob. | Done
88 | 002-eutr-masters | EUTR Masters Management | Phase 8: User Story 6 | US6 | T059 | Add export() blob call to the API client/repository/interface. | Done
89 | 002-eutr-masters | EUTR Masters Management | Phase 8: User Story 6 | US6 | T060 | Add Export button to the toolbar, gated by Download permission. | Done
90 | 002-eutr-masters | EUTR Masters Management | Phase 10: Change duplicate rule to Prefix-only |  | T061 | Rename ExistsStepPrefixAsync to ExistsPrefixAsync in the repository interface, dropping the stepId parameter. | Done
91 | 002-eutr-masters | EUTR Masters Management | Phase 10: Change duplicate rule to Prefix-only |  | T062 | Update EutrMastersRepository.cs SQL to check Prefix uniqueness only (drop StepId condition). | Done
92 | 002-eutr-masters | EUTR Masters Management | Phase 10: Change duplicate rule to Prefix-only |  | T063 | Update EutrMastersService.cs Add/Update to call ExistsPrefixAsync and update the error message. | Done
93 | 002-eutr-masters | EUTR Masters Management | Phase 10: Change duplicate rule to Prefix-only |  | T064 | Update EutrMastersImportService.cs dedupe key and duplicate message to Prefix-only. | Done
94 | 002-eutr-masters | EUTR Masters Management | Phase 10: Change duplicate rule to Prefix-only |  | T065 | Manually retest quickstart scenarios 4 & 7 for the new Prefix-only duplicate rule. | To do
95 | 002-eutr-masters | EUTR Masters Management | Ops (non-code) |  | T053 | Create menu code eutr-masters and permissions in DB, assign to roles/users, clear cached userMenu. | To do
96 | 003-eutr-templates | EUTR Templates Management | Phase 1: Setup |  | T001 | Verify eutr_templates and eutr_template_details tables exist in MySQL | Done
97 | 003-eutr-templates | EUTR Templates Management | Phase 1: Setup |  | T002 | Create VendorsV3 domain model in ComplianceSys.Domain.Dynamics | Done
98 | 003-eutr-templates | EUTR Templates Management | Phase 1: Setup |  | T003 | Add VendorsV3 refType mapping to ComplDynamicsService entity dictionary | Done
99 | 003-eutr-templates | EUTR Templates Management | Phase 2: Foundational - Backend Core |  | T004 | Create EutrTemplates entity | Done
100 | 003-eutr-templates | EUTR Templates Management | Phase 2: Foundational - Backend Core |  | T005 | Create EutrTemplateDetails entity | Done
101 | 003-eutr-templates | EUTR Templates Management | Phase 2: Foundational - Backend Core |  | T006 | Create EutrTemplatesRequestDto | Done
102 | 003-eutr-templates | EUTR Templates Management | Phase 2: Foundational - Backend Core |  | T007 | Create EutrTemplateDetailsRequestDto | Done
103 | 003-eutr-templates | EUTR Templates Management | Phase 2: Foundational - Backend Core |  | T008 | Create EutrTemplatesResponseDto and EutrTemplateDetailsResponseDto | Done
104 | 003-eutr-templates | EUTR Templates Management | Phase 2: Foundational - Backend Core |  | T009 | Create EutrTemplatesRequestDtoValidator (Name/AlertFor NotEmpty) | Done
105 | 003-eutr-templates | EUTR Templates Management | Phase 2: Foundational - Backend Core |  | T010 | Add template mapping profiles to EutrMappingProfile | Done
106 | 003-eutr-templates | EUTR Templates Management | Phase 2: Foundational - Backend Core |  | T011 | Create IEutrTemplatesRepository interface | Done
107 | 003-eutr-templates | EUTR Templates Management | Phase 2: Foundational - Backend Core |  | T012 | Create EutrTemplatesRepository shell | Done
108 | 003-eutr-templates | EUTR Templates Management | Phase 2: Foundational - Backend Core |  | T013 | Create IEutrTemplatesService interface | Done
109 | 003-eutr-templates | EUTR Templates Management | Phase 2: Foundational - Backend Core |  | T014 | Create EutrTemplatesService shell | Done
110 | 003-eutr-templates | EUTR Templates Management | Phase 2: Foundational - Backend Core |  | T015 | Create EutrTemplatesController shell | Done
111 | 003-eutr-templates | EUTR Templates Management | Phase 2: Foundational - Backend Core |  | T016 | Register DI for EutrTemplatesService/Repository | Done
112 | 003-eutr-templates | EUTR Templates Management | Phase 2: Foundational - Frontend Core |  | T017 | Create EutrTemplates.js and EutrTemplateDetails.js domain entities | Done
113 | 003-eutr-templates | EUTR Templates Management | Phase 2: Foundational - Frontend Core |  | T018 | Create IEutrTemplatesRepository.js interface | Done
114 | 003-eutr-templates | EUTR Templates Management | Phase 2: Foundational - Frontend Core |  | T019 | Create eutrTemplatesApi.js axios calls | Done
115 | 003-eutr-templates | EUTR Templates Management | Phase 2: Foundational - Frontend Core |  | T020 | Create RestEutrTemplatesRepository.js | Done
116 | 003-eutr-templates | EUTR Templates Management | Phase 2: Foundational - Frontend Core |  | T021 | Register eutrTemplates repository in DI | Done
117 | 003-eutr-templates | EUTR Templates Management | Phase 2: Foundational - Frontend Core |  | T022 | Add codeToComponent entry in RouteResolver.jsx | Done
118 | 003-eutr-templates | EUTR Templates Management | Phase 2: Foundational - Frontend Core |  | T023 | Add /eutr/templates/add and /edit/:id routes in MainRoutes.jsx | Done
119 | 003-eutr-templates | EUTR Templates Management | Phase 2: Foundational - Frontend Core |  | T024 | Add 'EUTR templates' menu item under EUTR system | Done
120 | 003-eutr-templates | EUTR Templates Management | Phase 3: US1 View Template List | US1 | T025 | Implement GetPagedWithVendorNameAsync paged query with filter/sort | Done
121 | 003-eutr-templates | EUTR Templates Management | Phase 3: US1 View Template List | US1 | T026 | Add POST get-all endpoint to EutrTemplatesController | Done
122 | 003-eutr-templates | EUTR Templates Management | Phase 3: US1 View Template List | US1 | T027 | Create GetPagingEutrTemplatesUseCase.js | Done
123 | 003-eutr-templates | EUTR Templates Management | Phase 3: US1 View Template List | US1 | T028 | Create useEutrTemplatesColumns.jsx hook defining 9 grid columns | Done
124 | 003-eutr-templates | EUTR Templates Management | Phase 3: US1 View Template List | US1 | T029 | Create useEutrTemplatesData.js hook for pagination/filter/sort state | Done
125 | 003-eutr-templates | EUTR Templates Management | Phase 3: US1 View Template List | US1 | T030 | Create EutrTemplatesActionCell.jsx (Edit navigates, Delete placeholder) | Done
126 | 003-eutr-templates | EUTR Templates Management | Phase 3: US1 View Template List | US1 | T031 | Create list page index.jsx with DataGridStyled and toolbar | Done
127 | 003-eutr-templates | EUTR Templates Management | Phase 4: US2 Create Template with Step Tree | US2 | T032 | Implement auto Code generation (prefix + padded increment) | Done
128 | 003-eutr-templates | EUTR Templates Management | Phase 4: US2 Create Template with Step Tree | US2 | T033 | Implement IsDefault-per-vendor constraint in service | Done
129 | 003-eutr-templates | EUTR Templates Management | Phase 4: US2 Create Template with Step Tree | US2 | T034 | Override AddAsync (Code gen, VersionId=1, bulk insert details) | Done
130 | 003-eutr-templates | EUTR Templates Management | Phase 4: US2 Create Template with Step Tree | US2 | T035 | Implement GetByIdWithDetailsAsync with joins for StepName | Done
131 | 003-eutr-templates | EUTR Templates Management | Phase 4: US2 Create Template with Step Tree | US2 | T036 | Add POST create and GET /{id} endpoints | Done
132 | 003-eutr-templates | EUTR Templates Management | Phase 4: US2 Create Template with Step Tree | US2 | T037 | Create CreateEutrTemplatesUseCase.js and GetEutrTemplatesUseCase.js | Done
133 | 003-eutr-templates | EUTR Templates Management | Phase 4: US2 Create Template with Step Tree | US2 | T038 | Create StepFormRow.jsx (step/requirement/take-from comboboxes) | Done
134 | 003-eutr-templates | EUTR Templates Management | Phase 4: US2 Create Template with Step Tree | US2 | T039 | Create useStepTree.js hook for tree state management | Done
135 | 003-eutr-templates | EUTR Templates Management | Phase 4: US2 Create Template with Step Tree | US2 | T040 | Create StepTree.jsx recursive tree view with drag-and-drop and delete | Done
136 | 003-eutr-templates | EUTR Templates Management | Phase 4: US2 Create Template with Step Tree | US2 | T041 | Create EutrTemplatesAddEdit.jsx full-page Add form | Done
137 | 003-eutr-templates | EUTR Templates Management | Phase 5: US3 Edit Template with Versioning | US3 | T042 | Implement versioning in UpdateAsync (new row, VersionId+1, hide old row) | Done
138 | 003-eutr-templates | EUTR Templates Management | Phase 5: US3 Edit Template with Versioning | US3 | T043 | Add PUT /{id} update endpoint | Done
139 | 003-eutr-templates | EUTR Templates Management | Phase 5: US3 Edit Template with Versioning | US3 | T044 | Create UpdateEutrTemplatesUseCase.js | Done
140 | 003-eutr-templates | EUTR Templates Management | Phase 5: US3 Edit Template with Versioning | US3 | T045 | Integrate edit mode into EutrTemplatesAddEdit.jsx | Done
141 | 003-eutr-templates | EUTR Templates Management | Phase 6: US4 Delete Template | US4 | T046 | Override DeleteAsync/DeleteMultiAsync for soft delete (IsDeleted=1) | Done
142 | 003-eutr-templates | EUTR Templates Management | Phase 6: US4 Delete Template | US4 | T047 | Add DELETE /{id} and bulk DELETE endpoints | Done
143 | 003-eutr-templates | EUTR Templates Management | Phase 6: US4 Delete Template | US4 | T048 | Create DeleteEutrTemplatesUseCase.js and DeleteMultiEutrTemplatesUseCase.js | Done
144 | 003-eutr-templates | EUTR Templates Management | Phase 6: US4 Delete Template | US4 | T049 | Wire delete/bulk-delete with ConfirmDialog in list page | Done
145 | 003-eutr-templates | EUTR Templates Management | Phase 7: US5 Import Templates | US5 | T050 | Create ImportEutrTemplatesResultDto.cs (counts and errors list) | Done
146 | 003-eutr-templates | EUTR Templates Management | Phase 7: US5 Import Templates | US5 | T051 | Create Import service reading Excel via ClosedXML with partial import | Done
147 | 003-eutr-templates | EUTR Templates Management | Phase 7: US5 Import Templates | US5 | T052 | Create Export service generating Excel via ClosedXML | Done
148 | 003-eutr-templates | EUTR Templates Management | Phase 7: US5 Import Templates | US5 | T053 | Add POST /import and GET /export endpoints, register DI | Done
149 | 003-eutr-templates | EUTR Templates Management | Phase 7: US5 Import Templates | US5 | T054 | Create ImportEutrTemplatesUseCase.js and ExportEutrTemplatesUseCase.js | Done
150 | 003-eutr-templates | EUTR Templates Management | Phase 7: US5 Import Templates | US5 | T055 | Create ImportResultDialog.jsx showing summary and error rows | Done
151 | 003-eutr-templates | EUTR Templates Management | Phase 7: US5 Import Templates | US5 | T056 | Add import/export buttons to list page toolbar | Done
152 | 003-eutr-templates | EUTR Templates Management | Phase 8: Polish and Cross-Cutting Concerns |  | T057 | Seed backend userMenu entry and grant EutrTemplates.* permissions | Done
153 | 003-eutr-templates | EUTR Templates Management | Phase 8: Polish and Cross-Cutting Concerns |  | T058 | Verify all UI labels/messages are in English per FR-017 | Done
154 | 003-eutr-templates | EUTR Templates Management | Phase 8: Polish and Cross-Cutting Concerns |  | T059 | Run quickstart validation scenarios 1-9 end-to-end | Done
155 | 003-eutr-templates | EUTR Templates Management | Phase 8: Polish and Cross-Cutting Concerns |  | T060 | Code cleanup: comments, unused imports, naming consistency | Done
156 | 003-eutr-templates | EUTR Templates Management | Phase 9: Bug Fixes (Frontend Only) | US2 | T061 | Fix Vendor combobox to use ReferenceObjectAutocomplete (refType=13) | Done
157 | 003-eutr-templates | EUTR Templates Management | Phase 9: Bug Fixes (Frontend Only) | US2 | T062 | Fix ParentId mapping bug in useStepTree.js flattenForSave | Done
158 | 003-eutr-templates | EUTR Templates Management | Phase 10: Edit Step Inline (FR-008b) | US2 | T063 | Add edit step state/function (editingStepId, editStep) to useStepTree.js | Done
159 | 003-eutr-templates | EUTR Templates Management | Phase 10: Edit Step Inline (FR-008b) | US2 | T064 | Add inline Edit mode rendering to StepTree.jsx with Save/Cancel | Done
160 | 003-eutr-templates | EUTR Templates Management | Phase 11: 2-Column Layout (FR-004a) | US2 | T065 | Restructure EutrTemplatesAddEdit.jsx into 2-column Grid layout | Done
161 | 003-eutr-templates | EUTR Templates Management | Phase 12: Validation and Polish |  | T066 | Verify Vendor combobox calls D365 VendorsV3 API in Add/Edit modes | Done
162 | 003-eutr-templates | EUTR Templates Management | Phase 12: Validation and Polish |  | T067 | Verify ParentId correctness for 3-level nested steps | Done
163 | 003-eutr-templates | EUTR Templates Management | Phase 12: Validation and Polish |  | T068 | Verify Edit step inline persists RequirementType/TakeFrom/StepId changes | Done
164 | 003-eutr-templates | EUTR Templates Management | Phase 12: Validation and Polish |  | T069 | Verify 2-column layout desktop/mobile responsiveness | Done
165 | 003-eutr-templates | EUTR Templates Management | Phase 12: Validation and Polish |  | T070 | Run quickstart scenarios 2,3,7,8 end-to-end | Done
166 | 003-eutr-templates | EUTR Templates Management | Phase 12: Validation and Polish |  | T071 | Verify all UI text in updated components is English | Done
167 | 003-eutr-templates | EUTR Templates Management | Phase 13: Backend Dedicated Vendors Endpoint | US1 | T072 | Add GET vendors endpoint to DynController following data-area pattern | Done
168 | 003-eutr-templates | EUTR Templates Management | Phase 14: Frontend Vendor API Layer and Hook | US1 | T073 | Add getVendors method to dynamicsApi.js | Done
169 | 003-eutr-templates | EUTR Templates Management | Phase 14: Frontend Vendor API Layer and Hook | US1 | T074 | Add getVendors to RestDynamicsRepository.js and IDynamicsRepository.js | Done
170 | 003-eutr-templates | EUTR Templates Management | Phase 14: Frontend Vendor API Layer and Hook | US1 | T075 | Create useVendors.js hook managing vendor list/search state | Done
171 | 003-eutr-templates | EUTR Templates Management | Phase 15: Replace Vendor Combobox | US2 | T076 | Replace vendor combobox with MUI Autocomplete backed by useVendors | Done
172 | 003-eutr-templates | EUTR Templates Management | Phase 15: Replace Vendor Combobox | US1 | T077 | Verify grid vendor name resolution still works (verification only) | Done
173 | 003-eutr-templates | EUTR Templates Management | Phase 16: Validation Dedicated Vendors API |  | T078 | Verify backend vendors endpoint returns OData vendor list | Done
174 | 003-eutr-templates | EUTR Templates Management | Phase 16: Validation Dedicated Vendors API |  | T079 | Verify Vendor combobox in Add mode calls GET /dynamics/vendors | To do
175 | 003-eutr-templates | EUTR Templates Management | Phase 16: Validation Dedicated Vendors API |  | T080 | Verify Vendor combobox in Edit mode pre-selects current vendor | To do
176 | 003-eutr-templates | EUTR Templates Management | Phase 16: Validation Dedicated Vendors API |  | T081 | Verify vendor search filter param works | To do
177 | 003-eutr-templates | EUTR Templates Management | Phase 16: Validation Dedicated Vendors API |  | T082 | Verify grid vendorName column still works | To do
178 | 003-eutr-templates | EUTR Templates Management | Phase 16: Validation Dedicated Vendors API |  | T083 | Run quickstart scenarios 1,2,3 end-to-end | To do
179 | 003-eutr-templates | EUTR Templates Management | Phase 17: Backend Add $select to Vendors Endpoint | US1 | T084 | Append OData $select to limit vendors endpoint to 3 columns | Done
180 | 003-eutr-templates | EUTR Templates Management | Phase 18: Validation Vendors $select |  | T085 | Build backend and verify 0 compilation errors after $select change | Done
181 | 003-eutr-templates | EUTR Templates Management | Phase 18: Validation Vendors $select |  | T086 | Verify vendor API response only contains 3 selected fields | To do
182 | 003-eutr-templates | EUTR Templates Management | Phase 18: Validation Vendors $select |  | T087 | Verify vendor combobox still works after response shape change | To do
183 | 003-eutr-templates | EUTR Templates Management | Phase 18: Validation Vendors $select |  | T088 | Run quickstart vendor validation scenarios (no regression) | To do
184 | 003-eutr-templates | EUTR Templates Management | Phase 19: Backend Conditional Versioning (24h) | US3 | T089 | Add ReplaceDetailsAsync to repository interface | Done
185 | 003-eutr-templates | EUTR Templates Management | Phase 19: Backend Conditional Versioning (24h) | US3 | T090 | Implement ReplaceDetailsAsync (delete+reinsert details for same template) | Done
186 | 003-eutr-templates | EUTR Templates Management | Phase 19: Backend Conditional Versioning (24h) | US3 | T091 | Modify UpdateAsync to branch on record age (<24h update in place, else version) | Done
187 | 003-eutr-templates | EUTR Templates Management | Phase 20: Save Button Position and Column Ratio | US2 | T092 | Remove Save button from the title bar | Done
188 | 003-eutr-templates | EUTR Templates Management | Phase 20: Save Button Position and Column Ratio | US2 | T093 | Add Save button below the Default checkbox in left column | Done
189 | 003-eutr-templates | EUTR Templates Management | Phase 20: Save Button Position and Column Ratio | US2 | T094 | Change Grid column ratios (widen header column, narrow step tree) | Done
190 | 003-eutr-templates | EUTR Templates Management | Phase 21: Back Button Unsaved-Step Warning | US2 | T095 | Add isDirty state tracking to useStepTree.js | Done
191 | 003-eutr-templates | EUTR Templates Management | Phase 21: Back Button Unsaved-Step Warning | US2 | T096 | Wire ConfirmDialog to Back button when isDirty | Done
192 | 003-eutr-templates | EUTR Templates Management | Phase 21: Back Button Unsaved-Step Warning | US2 | T097 | Reset isDirty after successful Save | Done
193 | 003-eutr-templates | EUTR Templates Management | Phase 22: Validation Conditional Versioning and UI Changes |  | T098 | Build backend and verify 0 compilation errors | Done
194 | 003-eutr-templates | EUTR Templates Management | Phase 22: Validation Conditional Versioning and UI Changes |  | T099 | Verify <24h edit updates in place (same Id/VersionId/CreatedDate) | To do
195 | 003-eutr-templates | EUTR Templates Management | Phase 22: Validation Conditional Versioning and UI Changes |  | T100 | Verify >=24h edit creates a new version, old row hidden | To do
196 | 003-eutr-templates | EUTR Templates Management | Phase 22: Validation Conditional Versioning and UI Changes |  | T101 | Verify Save button position below Default checkbox | To do
197 | 003-eutr-templates | EUTR Templates Management | Phase 22: Validation Conditional Versioning and UI Changes |  | T102 | Verify column ratio (left wider than right) | To do
198 | 003-eutr-templates | EUTR Templates Management | Phase 22: Validation Conditional Versioning and UI Changes |  | T103 | Verify Back warning appears on Add page with unsaved step | To do
199 | 003-eutr-templates | EUTR Templates Management | Phase 22: Validation Conditional Versioning and UI Changes |  | T104 | Verify Back warning appears on Edit page inline changes | To do
200 | 003-eutr-templates | EUTR Templates Management | Phase 22: Validation Conditional Versioning and UI Changes |  | T105 | Verify Back with no changes navigates without warning | To do
201 | 003-eutr-templates | EUTR Templates Management | Phase 22: Validation Conditional Versioning and UI Changes |  | T106 | Run quickstart Scenario 2, 3 (3a/3b), 12 end-to-end | To do
202 | 003-eutr-templates | EUTR Templates Management | Phase 23: Replace Vendor Combobox with Generic Reference API | US2 | T107 | Replace vendor combobox back to ReferenceObjectAutocomplete (refType=13) | Done
203 | 003-eutr-templates | EUTR Templates Management | Phase 23: Replace Vendor Combobox with Generic Reference API | US2 | T108 | Remove unused useVendors.js hook | Done
204 | 003-eutr-templates | EUTR Templates Management | Phase 23: Replace Vendor Combobox with Generic Reference API | US1 | T109 | Verify grid Vendor name column resolution unaffected | Done
205 | 003-eutr-templates | EUTR Templates Management | Phase 24: Backend Cleanup Check |  | T110 | Search for other consumers of getVendors/vendors endpoint before leaving as dead code | Done
206 | 003-eutr-templates | EUTR Templates Management | Phase 25: Validation Vendor API Reversal |  | T111 | Verify Vendor combobox in Add mode uses POST /dynamics/reference refType=13 | To do
207 | 003-eutr-templates | EUTR Templates Management | Phase 25: Validation Vendor API Reversal |  | T112 | Verify Vendor combobox in Edit mode pre-selects via reference API | To do
208 | 003-eutr-templates | EUTR Templates Management | Phase 25: Validation Vendor API Reversal |  | T113 | Verify grid vendorName column still displays correctly | To do
209 | 003-eutr-templates | EUTR Templates Management | Phase 25: Validation Vendor API Reversal |  | T114 | Run quickstart scenarios 1,2,3 end-to-end | To do
210 | 003-eutr-templates | EUTR Templates Management | Phase 26: Backend StepName Field, Validation, Resolve/Auto-create | US2 | T115 | Add StepName field to EutrTemplateDetailsRequestDto | Done
211 | 003-eutr-templates | EUTR Templates Management | Phase 26: Backend StepName Field, Validation, Resolve/Auto-create | US2 | T116 | Add per-detail validator rule requiring StepId or StepName | Done
212 | 003-eutr-templates | EUTR Templates Management | Phase 26: Backend StepName Field, Validation, Resolve/Auto-create | US2 | T117 | Add ResolveOrCreateStepsByNameAsync to repository interface | Done
213 | 003-eutr-templates | EUTR Templates Management | Phase 26: Backend StepName Field, Validation, Resolve/Auto-create | US2 | T118 | Implement ResolveOrCreateStepsByNameAsync (dedupe/match/create steps) | Done
214 | 003-eutr-templates | EUTR Templates Management | Phase 26: Backend StepName Field, Validation, Resolve/Auto-create | US2 | T119 | Extract BuildDetailEntitiesAsync helper resolving step names before insert | Done
215 | 003-eutr-templates | EUTR Templates Management | Phase 27: Frontend Free-solo Step Combobox | US2 | T120 | Make StepFormRow.jsx Step combobox freeSolo with stepName tracking | Done
216 | 003-eutr-templates | EUTR Templates Management | Phase 27: Frontend Free-solo Step Combobox | US2 | T121 | Make StepTree.jsx inline edit Step combobox freeSolo | Done
217 | 003-eutr-templates | EUTR Templates Management | Phase 27: Frontend Free-solo Step Combobox | US2 | T122 | Update flattenForSave to include stepName in every detail | Done
218 | 003-eutr-templates | EUTR Templates Management | Phase 28: Validation Free-solo Step Combobox |  | T123 | Verify auto-create of a brand-new step name on Save | To do
219 | 003-eutr-templates | EUTR Templates Management | Phase 28: Validation Free-solo Step Combobox |  | T124 | Verify dedupe of identical new step name within one Save | To do
220 | 003-eutr-templates | EUTR Templates Management | Phase 28: Validation Free-solo Step Combobox |  | T125 | Verify case-insensitive/trimmed reuse of existing step name | To do
221 | 003-eutr-templates | EUTR Templates Management | Phase 28: Validation Free-solo Step Combobox |  | T126 | Verify inline Edit step free-solo auto-create | To do
222 | 003-eutr-templates | EUTR Templates Management | Phase 28: Validation Free-solo Step Combobox |  | T127 | Verify blank/whitespace step name is blocked client-side | To do
223 | 003-eutr-templates | EUTR Templates Management | Phase 28: Validation Free-solo Step Combobox |  | T128 | Run quickstart Scenario 14 end-to-end | To do
224 | 003-eutr-templates | EUTR Templates Management | Phase 29: Backend AlertFor Type Change | US2 | T129 | Change EutrTemplates.AlertFor from string to long? | Done
225 | 003-eutr-templates | EUTR Templates Management | Phase 29: Backend AlertFor Type Change | US2 | T130 | Change EutrTemplatesRequestDto.AlertFor to long? | Done
226 | 003-eutr-templates | EUTR Templates Management | Phase 29: Backend AlertFor Type Change | US1 | T131 | Add AlertForName to EutrTemplatesResponseDto | Done
227 | 003-eutr-templates | EUTR Templates Management | Phase 29: Backend AlertFor Type Change | US2 | T132 | Update validator rule for AlertFor to numeric > 0 | Done
228 | 003-eutr-templates | EUTR Templates Management | Phase 29: Backend AlertFor Type Change | US1 | T133 | Add LEFT JOIN compl_group_email for AlertForName, update FilterMap | Done
229 | 003-eutr-templates | EUTR Templates Management | Phase 29: Backend AlertFor Type Change | US2 | T134 | Create migration converting AlertFor column to BIGINT UNSIGNED NULL | Done
230 | 003-eutr-templates | EUTR Templates Management | Phase 30: Backend Import/Export AlertFor Name Resolution | US5 | T135 | Add ResolveAlertGroupIdByNameAsync repository method | Done
231 | 003-eutr-templates | EUTR Templates Management | Phase 30: Backend Import/Export AlertFor Name Resolution | US5 | T136 | Import service resolves AlertFor group Name to Id, fails if not found | Done
232 | 003-eutr-templates | EUTR Templates Management | Phase 30: Backend Import/Export AlertFor Name Resolution | US5 | T137 | Export service writes AlertForName instead of raw AlertFor | Done
233 | 003-eutr-templates | EUTR Templates Management | Phase 31: Frontend Alert For Combobox | US2 | T138 | Replace free-text Alert for with select-only combobox from compl_group_email | Done
234 | 003-eutr-templates | EUTR Templates Management | Phase 31: Frontend Alert For Combobox | US1 | T139 | Add alertForName to EutrTemplates.js domain entity | Done
235 | 003-eutr-templates | EUTR Templates Management | Phase 31: Frontend Alert For Combobox | US1 | T140 | Change grid Alert for column field to alertForName | Done
236 | 003-eutr-templates | EUTR Templates Management | Phase 32: Validation Alert For Combobox |  | T141 | Verify combobox data source calls GET /group-email filtered correctly | To do
237 | 003-eutr-templates | EUTR Templates Management | Phase 32: Validation Alert For Combobox |  | T142 | Verify Save persists the group Id, not the Name | To do
238 | 003-eutr-templates | EUTR Templates Management | Phase 32: Validation Alert For Combobox |  | T143 | Verify grid displays group Name for Alert for column | To do
239 | 003-eutr-templates | EUTR Templates Management | Phase 32: Validation Alert For Combobox |  | T144 | Verify Edit pre-selects the current Alert for group | To do
240 | 003-eutr-templates | EUTR Templates Management | Phase 32: Validation Alert For Combobox |  | T145 | Verify Import/Export resolve/display Alert for group Name correctly | To do
241 | 003-eutr-templates | EUTR Templates Management | Phase 32: Validation Alert For Combobox |  | T146 | Run quickstart scenarios covering AlertFor end-to-end | To do
242 | 003-eutr-templates | EUTR Templates Management | Phase 33: Move Shared Constants to helpers.js | US2 | T147 | Add REQUIREMENT_TYPES/TAKE_FROM_OPTIONS/labels exports to helpers.js | Done
243 | 003-eutr-templates | EUTR Templates Management | Phase 33: Move Shared Constants to helpers.js | US2 | T148 | Remove local constant declarations in StepTree.jsx, import from helpers | Done
244 | 003-eutr-templates | EUTR Templates Management | Phase 33: Move Shared Constants to helpers.js | US2 | T149 | Remove local constant declarations in StepFormRow.jsx, import from helpers | Done
245 | 003-eutr-templates | EUTR Templates Management | Phase 34: Validation Shared Constants |  | T150 | Verify Add step form combobox options still render correctly | To do
246 | 003-eutr-templates | EUTR Templates Management | Phase 34: Validation Shared Constants |  | T151 | Verify inline Edit step combobox and label rendering unchanged | To do
247 | 003-eutr-templates | EUTR Templates Management | Phase 34: Validation Shared Constants |  | T152 | Run frontend build/lint and quickstart check for no import errors | To do
248 | 003-eutr-templates | EUTR Templates Management | Phase 35: Rename List Page to TemplateListPage | US1 | T153 | Rename index.jsx to TemplateListPage.jsx, confirm FR-020 columns | Done
249 | 003-eutr-templates | EUTR Templates Management | Phase 35: Rename List Page to TemplateListPage | US1 | T154 | Update RouteResolver.jsx lazy import path to renamed file | Done
250 | 003-eutr-templates | EUTR Templates Management | Phase 36: Create Template Dialog | US2 | T155 | Create CreateTemplateDialog.jsx (Name/Alert for/Set as default only) | Done
251 | 003-eutr-templates | EUTR Templates Management | Phase 36: Create Template Dialog | US2 | T156 | Wire CreateTemplateDialog into TemplateListPage.jsx toolbar | Done
252 | 003-eutr-templates | EUTR Templates Management | Phase 37: Simplify Edit Page and Remove Add Route | US3 | T157 | Remove isEdit branch from EutrTemplatesAddEdit.jsx (Edit-only now) | Done
253 | 003-eutr-templates | EUTR Templates Management | Phase 37: Simplify Edit Page and Remove Add Route | US3 | T158 | Remove /eutr/templates/add route from MainRoutes.jsx | Done
254 | 003-eutr-templates | EUTR Templates Management | Phase 38: Validation TemplateListPage and Create/Edit Split |  | T159 | Verify TemplateListPage renders unchanged after rename (FR-020 columns) | To do
255 | 003-eutr-templates | EUTR Templates Management | Phase 38: Validation TemplateListPage and Create/Edit Split |  | T160 | Verify Create Template dialog shows only 3 fields with validation | To do
256 | 003-eutr-templates | EUTR Templates Management | Phase 38: Validation TemplateListPage and Create/Edit Split |  | T161 | Verify successful Create dialog Save creates 0-step template, no navigation | To do
257 | 003-eutr-templates | EUTR Templates Management | Phase 38: Validation TemplateListPage and Create/Edit Split |  | T162 | Verify Edit on freshly quick-created template allows first step/Vendor add | To do
258 | 003-eutr-templates | EUTR Templates Management | Phase 38: Validation TemplateListPage and Create/Edit Split |  | T163 | Verify /eutr/templates/add is no longer reachable | To do
259 | 003-eutr-templates | EUTR Templates Management | Phase 38: Validation TemplateListPage and Create/Edit Split |  | T164 | Run quickstart Scenario 2, 2b, and re-verify 3,8,9,12,14 | To do
260 | 003-eutr-templates | EUTR Templates Management | Phase 39: Backend Keyword Search and Real Steps Count | US1 | T165 | Add Keyword (Code OR Name) filter special-case to paged query | Done
261 | 003-eutr-templates | EUTR Templates Management | Phase 39: Backend Keyword Search and Real Steps Count | US1 | T166 | Add StepsCount property to EutrTemplatesResponseDto | Done
262 | 003-eutr-templates | EUTR Templates Management | Phase 39: Backend Keyword Search and Real Steps Count | US1 | T167 | Add StepsCount subquery to the paged list SQL SELECT | Done
263 | 003-eutr-templates | EUTR Templates Management | Phase 40: TemplateListPage Real-Data Wiring, Pagination, Search | US1 | T168 | Wire TemplateListPage.jsx to useEutrTemplatesData, remove mock imports | Done
264 | 003-eutr-templates | EUTR Templates Management | Phase 40: TemplateListPage Real-Data Wiring, Pagination, Search | US1 | T169 | Replace row rendering to read Code/Name/Version/Default/Steps from real data | Done
265 | 003-eutr-templates | EUTR Templates Management | Phase 40: TemplateListPage Real-Data Wiring, Pagination, Search | US1 | T170 | Replace client-side search with debounced server-side keyword search | Done
266 | 003-eutr-templates | EUTR Templates Management | Phase 40: TemplateListPage Real-Data Wiring, Pagination, Search | US1 | T171 | Add TablePagination control bound to paginationModel/total | Done
267 | 003-eutr-templates | EUTR Templates Management | Phase 41: Create/Delete/Bulk-Delete/Disabled Actions | US2 | T172 | Replace mock create dialog with real CreateTemplateDialog reuse | Done
268 | 003-eutr-templates | EUTR Templates Management | Phase 41: Create/Delete/Bulk-Delete/Disabled Actions | US4 | T173 | Wire single-row Delete with ConfirmDialog and DeleteEutrTemplatesUseCase | Done
269 | 003-eutr-templates | EUTR Templates Management | Phase 41: Create/Delete/Bulk-Delete/Disabled Actions | US4 | T174 | Add per-row checkbox and bulk-delete toolbar action | Done
270 | 003-eutr-templates | EUTR Templates Management | Phase 41: Create/Delete/Bulk-Delete/Disabled Actions | US1 | T175 | Remove mock Clone dialog, disable Clone/Apply icons, add CustomSnackbar | Done
271 | 003-eutr-templates | EUTR Templates Management | Phase 42: TemplateBuilderPage Real-Data Wiring | US3 | T176 | Remove mock imports, load real template/steps/alert-groups on mount | Done
272 | 003-eutr-templates | EUTR Templates Management | Phase 42: TemplateBuilderPage Real-Data Wiring | US3 | T177 | Replace hand-rolled tree state with useStepTree hook | Done
273 | 003-eutr-templates | EUTR Templates Management | Phase 42: TemplateBuilderPage Real-Data Wiring | US3 | T178 | Change moveNode to call hook's reorderSiblings | Done
274 | 003-eutr-templates | EUTR Templates Management | Phase 42: TemplateBuilderPage Real-Data Wiring | US3 | T179 | Replace Add Root/Child dialogs with free-solo real-steps Autocomplete | Done
275 | 003-eutr-templates | EUTR Templates Management | Phase 42: TemplateBuilderPage Real-Data Wiring | US3 | T180 | Right panel switches between header form and step-detail form | Done
276 | 003-eutr-templates | EUTR Templates Management | Phase 42: TemplateBuilderPage Real-Data Wiring | US3 | T181 | Rename handleSaveDraft to handleSave calling real UpdateUseCase | Done
277 | 003-eutr-templates | EUTR Templates Management | Phase 42: TemplateBuilderPage Real-Data Wiring | US3 | T182 | Add isDirty + ConfirmDialog wiring to Back button | Done
278 | 003-eutr-templates | EUTR Templates Management | Phase 42: TemplateBuilderPage Real-Data Wiring | US3 | T183 | Replace not-found guard with loading spinner and updated breadcrumb | Done
279 | 003-eutr-templates | EUTR Templates Management | Phase 43: Cleanup Verification Orphaned Files |  | T184 | Grep for remaining imports of mock/treeUtils files (none expected) | Done
280 | 003-eutr-templates | EUTR Templates Management | Phase 43: Cleanup Verification Orphaned Files |  | T185 | Grep for remaining route/import references to EutrTemplatesAddEdit.jsx | Done
281 | 003-eutr-templates | EUTR Templates Management | Phase 44: Validation Table Layout + Builder + Search + Steps Count |  | T186 | Verify TemplateListPage Table layout, search box, no Import/Export | Done
282 | 003-eutr-templates | EUTR Templates Management | Phase 44: Validation Table Layout + Builder + Search + Steps Count |  | T187 | Verify server-side keyword search resets to page 1, matches full dataset | To do
283 | 003-eutr-templates | EUTR Templates Management | Phase 44: Validation Table Layout + Builder + Search + Steps Count |  | T188 | Verify Steps count column shows accurate real count | To do
284 | 003-eutr-templates | EUTR Templates Management | Phase 44: Validation Table Layout + Builder + Search + Steps Count |  | T189 | Verify single-row Delete confirmation and soft-delete | To do
285 | 003-eutr-templates | EUTR Templates Management | Phase 44: Validation Table Layout + Builder + Search + Steps Count |  | T190 | Verify bulk delete via checkboxes | To do
286 | 003-eutr-templates | EUTR Templates Management | Phase 44: Validation Table Layout + Builder + Search + Steps Count |  | T191 | Verify Clone/Apply-to-Customer icons are disabled and inert | Done
287 | 003-eutr-templates | EUTR Templates Management | Phase 44: Validation Table Layout + Builder + Search + Steps Count |  | T192 | Verify pagination control navigates between pages | Done
288 | 003-eutr-templates | EUTR Templates Management | Phase 44: Validation Table Layout + Builder + Search + Steps Count |  | T193 | Verify Edit opens TemplateBuilderPage with real data | Done
289 | 003-eutr-templates | EUTR Templates Management | Phase 44: Validation Table Layout + Builder + Search + Steps Count |  | T194 | Verify Add Root/Child dialogs use free-solo real steps, no Type/FSC fields | Done
290 | 003-eutr-templates | EUTR Templates Management | Phase 44: Validation Table Layout + Builder + Search + Steps Count |  | T195 | Verify Move Up/Down changes position and persists DisplayOrder | Done
291 | 003-eutr-templates | EUTR Templates Management | Phase 44: Validation Table Layout + Builder + Search + Steps Count |  | T196 | Verify side panel dual role (header form vs step detail) | Done
292 | 003-eutr-templates | EUTR Templates Management | Phase 44: Validation Table Layout + Builder + Search + Steps Count |  | T197 | Verify Save + versioning still applies on TemplateBuilderPage | To do
293 | 003-eutr-templates | EUTR Templates Management | Phase 44: Validation Table Layout + Builder + Search + Steps Count |  | T198 | Run quickstart Scenario 1' and 2b' end-to-end | To do
294 | 003-eutr-templates | EUTR Templates Management | Phase 45: useStepTree.js Bulk-Append Function | US3 | T199 | Add addSteps bulk-append function to useStepTree.js | Done
295 | 003-eutr-templates | EUTR Templates Management | Phase 46: BulkAddStepsDialog.jsx Component | US3 | T200 | Create BulkAddStepsDialog.jsx checkbox table with Add new step area | Done
296 | 003-eutr-templates | EUTR Templates Management | Phase 47: Wire BulkAddStepsDialog into TemplateBuilderPage | US3 | T201 | Wire BulkAddStepsDialog into TemplateBuilderPage's Root/Child dialogs | Done
297 | 003-eutr-templates | EUTR Templates Management | Phase 48: Validation Bulk-Select Add Root/Child |  | T202 | Verify initial dialog state (unticked, disabled fields, footer counter) | Done
298 | 003-eutr-templates | EUTR Templates Management | Phase 48: Validation Bulk-Select Add Root/Child |  | T203 | Verify bulk-add to root with multiple ticked + free-solo entries | Done
299 | 003-eutr-templates | EUTR Templates Management | Phase 48: Validation Bulk-Select Add Root/Child |  | T204 | Verify bulk-add to selected parent and same-parent dedupe | Done
300 | 003-eutr-templates | EUTR Templates Management | Phase 48: Validation Bulk-Select Add Root/Child |  | T205 | Verify Cancel discards all selections/entries | Done
301 | 003-eutr-templates | EUTR Templates Management | Phase 48: Validation Bulk-Select Add Root/Child |  | T206 | Verify free-solo auto-create still works via the bulk dialog | Done
302 | 003-eutr-templates | EUTR Templates Management | Phase 48: Validation Bulk-Select Add Root/Child |  | T207 | Verify single-step Edit is unaffected by bulk-select changes | Done
303 | 003-eutr-templates | EUTR Templates Management | Phase 48: Validation Bulk-Select Add Root/Child |  | T208 | Run quickstart Scenario 15 end-to-end | To do
304 | 003-eutr-templates | EUTR Templates Management | Phase 49: Backend Remove VendorCode | US2 | T209 | Remove VendorCode property from EutrTemplates entity | Done
305 | 003-eutr-templates | EUTR Templates Management | Phase 49: Backend Remove VendorCode | US2 | T210 | Remove VendorCode from EutrTemplatesRequestDto | Done
306 | 003-eutr-templates | EUTR Templates Management | Phase 49: Backend Remove VendorCode | US2 | T211 | Remove VendorName from EutrTemplatesResponseDto | Done
307 | 003-eutr-templates | EUTR Templates Management | Phase 49: Backend Remove VendorCode | US2 | T212 | Remove VendorCode from SortMap/FilterMap/SQL, rename GetPagedWithVendorNameAsync | Done
308 | 003-eutr-templates | EUTR Templates Management | Phase 49: Backend Remove VendorCode | US2 | T213 | Rename ClearIsDefaultForVendorAsync to ClearGlobalDefaultAsync (global scope) | Done
309 | 003-eutr-templates | EUTR Templates Management | Phase 49: Backend Remove VendorCode | US2 | T214 | Delete D365 vendor-name-resolution block from GetPagedAsync | Done
310 | 003-eutr-templates | EUTR Templates Management | Phase 49: Backend Remove VendorCode | US3 | T215 | Update AddAsync/UpdateAsync call sites to use ClearGlobalDefaultAsync | Done
311 | 003-eutr-templates | EUTR Templates Management | Phase 49: Backend Remove VendorCode | US2 | T216 | Remove VendorCode column read from Import service, shift columns | Done
312 | 003-eutr-templates | EUTR Templates Management | Phase 49: Backend Remove VendorCode | US2 | T217 | Remove Vendor code column from Export service headers/cells | Done
313 | 003-eutr-templates | EUTR Templates Management | Phase 49: Backend Remove VendorCode |  | T218 | Grep and remove VendorCode from unused RSVNEutrTemplates.cs D365 sync model | Done
314 | 003-eutr-templates | EUTR Templates Management | Phase 50: Frontend Remove VendorCode | US2 | T219 | Remove vendorCode/vendorName from EutrTemplates.js domain entity | Done
315 | 003-eutr-templates | EUTR Templates Management | Phase 50: Frontend Remove VendorCode | US3 | T220 | Remove Vendor state/combobox from TemplateBuilderPage.jsx | Done
316 | 003-eutr-templates | EUTR Templates Management | Phase 50: Frontend Remove VendorCode | US2 | T221 | Remove vendorCode from CreateTemplateDialog.jsx payload | Done
317 | 003-eutr-templates | EUTR Templates Management | Phase 50: Frontend Remove VendorCode |  | T222 | Remove vendorCode/vendorName from useEutrTemplatesColumns.jsx | Done
318 | 003-eutr-templates | EUTR Templates Management | Phase 51: New eutr_template_references CRUD Stack | US6 | T223 | Create migration for eutr_template_references table | Done
319 | 003-eutr-templates | EUTR Templates Management | Phase 51: New eutr_template_references CRUD Stack | US6 | T224 | Add CREATE TABLE to fresh-install eutr_db.sql | Done
320 | 003-eutr-templates | EUTR Templates Management | Phase 51: New eutr_template_references CRUD Stack | US6 | T225 | Create EutrTemplateReferences entity | Done
321 | 003-eutr-templates | EUTR Templates Management | Phase 51: New eutr_template_references CRUD Stack | US6 | T226 | Create EutrTemplateReferencesRequestDto | Done
322 | 003-eutr-templates | EUTR Templates Management | Phase 51: New eutr_template_references CRUD Stack | US6 | T227 | Create EutrTemplateReferencesResponseDto with VendorName | Done
323 | 003-eutr-templates | EUTR Templates Management | Phase 51: New eutr_template_references CRUD Stack | US6 | T228 | Create EutrTemplateReferencesRequestDtoValidator | Done
324 | 003-eutr-templates | EUTR Templates Management | Phase 51: New eutr_template_references CRUD Stack | US6 | T229 | Create IEutrTemplateReferencesRepository interface | Done
325 | 003-eutr-templates | EUTR Templates Management | Phase 51: New eutr_template_references CRUD Stack | US6 | T230 | Implement EutrTemplateReferencesRepository (GetByTemplateId, HasOverlap) | Done
326 | 003-eutr-templates | EUTR Templates Management | Phase 51: New eutr_template_references CRUD Stack | US6 | T231 | Create EutrTemplateReferencesService with overlap validation, hard delete | Done
327 | 003-eutr-templates | EUTR Templates Management | Phase 51: New eutr_template_references CRUD Stack | US6 | T232 | Create EutrTemplateReferencesController (GET/POST/PUT/DELETE) | Done
328 | 003-eutr-templates | EUTR Templates Management | Phase 51: New eutr_template_references CRUD Stack | US6 | T233 | Add AutoMapper mappings for EutrTemplateReferences | Done
329 | 003-eutr-templates | EUTR Templates Management | Phase 51: New eutr_template_references CRUD Stack | US6 | T234 | Register DI for EutrTemplateReferences service/repository/validator | Done
330 | 003-eutr-templates | EUTR Templates Management | Phase 52: Apply-to-Customer Frontend Layers | US6 | T235 | Create EutrTemplateReferences.js domain entity | Done
331 | 003-eutr-templates | EUTR Templates Management | Phase 52: Apply-to-Customer Frontend Layers | US6 | T236 | Create IEutrTemplateReferencesRepository.js interface | Done
332 | 003-eutr-templates | EUTR Templates Management | Phase 52: Apply-to-Customer Frontend Layers | US6 | T237 | Create eutrTemplateReferencesApi.js axios wrapper | Done
333 | 003-eutr-templates | EUTR Templates Management | Phase 52: Apply-to-Customer Frontend Layers | US6 | T238 | Create RestEutrTemplateReferencesRepository.js | Done
334 | 003-eutr-templates | EUTR Templates Management | Phase 52: Apply-to-Customer Frontend Layers | US6 | T239 | Register eutrTemplateReferences repository in DI | Done
335 | 003-eutr-templates | EUTR Templates Management | Phase 52: Apply-to-Customer Frontend Layers | US6 | T240 | Create GetByTemplateId and Create use cases | Done
336 | 003-eutr-templates | EUTR Templates Management | Phase 52: Apply-to-Customer Frontend Layers | US6 | T241 | Create Update and Delete use cases | Done
337 | 003-eutr-templates | EUTR Templates Management | Phase 53: ApplyCustomerPage Rewrite + Wiring | US6 | T242 | Rewrite ApplyCustomerPage.jsx from mock Customer data to real Vendor data | Done
338 | 003-eutr-templates | EUTR Templates Management | Phase 53: ApplyCustomerPage Rewrite + Wiring | US6 | T243 | Add /eutr/templates/apply/:id route for ApplyCustomerPage | Done
339 | 003-eutr-templates | EUTR Templates Management | Phase 53: ApplyCustomerPage Rewrite + Wiring | US6 | T244 | Enable Apply to Customer icon navigation on TemplateListPage | Done
340 | 003-eutr-templates | EUTR Templates Management | Phase 54: Steps-Count Investigation | US1 | T245 | Investigate reported Steps-count display bug (verify-first, no speculative fix) | Done
341 | 003-eutr-templates | EUTR Templates Management | Phase 55: Validation Update 13 |  | T246 | Run Scenario 16 VendorCode removal verification | Done
342 | 003-eutr-templates | EUTR Templates Management | Phase 55: Validation Update 13 |  | T247 | Run Scenario 5 IsDefault global constraint verification | Done
343 | 003-eutr-templates | EUTR Templates Management | Phase 55: Validation Update 13 |  | T248 | Run Scenario 17 Apply to Customer end-to-end | Done
344 | 003-eutr-templates | EUTR Templates Management | Phase 55: Validation Update 13 |  | T249 | Verify new authorization policies are granted (resolved by reusing existing) | Done
345 | 003-eutr-templates | EUTR Templates Management | Phase 55: Validation Update 13 |  | T250 | Verify all new UI text is in English | Done
346 | 003-eutr-templates | EUTR Templates Management | Phase 55: Validation Update 13 |  | T251 | Regression check Create/Edit/Import flows after VendorCode removal | Done
347 | 003-eutr-templates | EUTR Templates Management | Phase 55: Validation Update 13 |  | T252 | Record Scenario 18 outcome and close out FR-042/SC-035 | Done
348 | 003-eutr-templates | EUTR Templates Management | Phase 56: Backend Import/Export Services for References | US6 | T253 | Create ImportEutrTemplateReferencesResultDto.cs | Done
349 | 003-eutr-templates | EUTR Templates Management | Phase 56: Backend Import/Export Services for References | US6 | T254 | Create EutrTemplateReferencesImportService with row validation | Done
350 | 003-eutr-templates | EUTR Templates Management | Phase 56: Backend Import/Export Services for References | US6 | T255 | Create EutrTemplateReferencesExportService generating 4-column xlsx | Done
351 | 003-eutr-templates | EUTR Templates Management | Phase 56: Backend Import/Export Services for References | US6 | T256 | Add Import/Export controller actions to EutrTemplateReferencesController | Done
352 | 003-eutr-templates | EUTR Templates Management | Phase 56: Backend Import/Export Services for References | US6 | T257 | Register DI for Import/Export reference services | Done
353 | 003-eutr-templates | EUTR Templates Management | Phase 57: Frontend Import/Export API for References | US6 | T258 | Add importByTemplate/exportByTemplate to eutrTemplateReferencesApi.js | Done
354 | 003-eutr-templates | EUTR Templates Management | Phase 57: Frontend Import/Export API for References | US6 | T259 | Add passthrough methods to RestEutrTemplateReferencesRepository.js | Done
355 | 003-eutr-templates | EUTR Templates Management | Phase 57: Frontend Import/Export API for References | US6 | T260 | Create ImportEutrTemplateReferencesUseCase.js | Done
356 | 003-eutr-templates | EUTR Templates Management | Phase 57: Frontend Import/Export API for References | US6 | T261 | Create ExportEutrTemplateReferencesUseCase.js with blob download | Done
357 | 003-eutr-templates | EUTR Templates Management | Phase 58: ApplyCustomerPage Import/Export UI | US6 | T262 | Create ImportMappingResultDialog.jsx (Row/TemplateCode/VendorCode/Reason) | Done
358 | 003-eutr-templates | EUTR Templates Management | Phase 58: ApplyCustomerPage Import/Export UI | US6 | T263 | Add Import/Export buttons and wiring to ApplyCustomerPage.jsx | Done
359 | 003-eutr-templates | EUTR Templates Management | Phase 59: Validation Import/Export Vendor Mapping |  | T264 | Run Scenario 19 Import/Export end-to-end (valid/invalid/overlap rows) | Done
360 | 003-eutr-templates | EUTR Templates Management | Phase 59: Validation Import/Export Vendor Mapping |  | T265 | Verify Import/Export actions reuse existing authorization policies | Done
361 | 003-eutr-templates | EUTR Templates Management | Phase 59: Validation Import/Export Vendor Mapping |  | T266 | Verify all new Import/Export UI text is in English | Done
362 | 003-eutr-templates | EUTR Templates Management | Phase 59: Validation Import/Export Vendor Mapping |  | T267 | Record Scenario 19 verification outcome in quickstart.md | Done
363 | 003-eutr-templates | EUTR Templates Management | Phase 60: Copy References on Version-up | US3 | T268 | Add CopyReferencesAsync to repository interface | Done
364 | 003-eutr-templates | EUTR Templates Management | Phase 60: Copy References on Version-up | US3 | T269 | Implement CopyReferencesAsync (set-based INSERT SELECT) | Done
365 | 003-eutr-templates | EUTR Templates Management | Phase 60: Copy References on Version-up | US3 | T270 | Wire CopyReferencesAsync into UpdateAsync's version-up branch | Done
366 | 003-eutr-templates | EUTR Templates Management | Phase 61: Clone Template Service and Endpoint | US7 | T271 | Create CloneEutrTemplatesRequestDto (Name, AlertFor) | Done
367 | 003-eutr-templates | EUTR Templates Management | Phase 61: Clone Template Service and Endpoint | US7 | T272 | Create CloneEutrTemplatesRequestDtoValidator | Done
368 | 003-eutr-templates | EUTR Templates Management | Phase 61: Clone Template Service and Endpoint | US7 | T273 | Extract GenerateNextCodeAsync helper from AddAsync | Done
369 | 003-eutr-templates | EUTR Templates Management | Phase 61: Clone Template Service and Endpoint | US7 | T274 | Implement CloneAsync copying header/step tree/vendor mappings | Done
370 | 003-eutr-templates | EUTR Templates Management | Phase 61: Clone Template Service and Endpoint | US7 | T275 | Add POST {id}/clone endpoint | Done
371 | 003-eutr-templates | EUTR Templates Management | Phase 61: Clone Template Service and Endpoint | US7 | T276 | Register CloneEutrTemplatesRequestDtoValidator in DI | Done
372 | 003-eutr-templates | EUTR Templates Management | Phase 62: Frontend Clone API/Repository/Use Case | US7 | T277 | Add clone(id, payload) to eutrTemplatesApi.js | Done
373 | 003-eutr-templates | EUTR Templates Management | Phase 62: Frontend Clone API/Repository/Use Case | US7 | T278 | Add clone passthrough to RestEutrTemplatesRepository.js | Done
374 | 003-eutr-templates | EUTR Templates Management | Phase 62: Frontend Clone API/Repository/Use Case | US7 | T279 | Create CloneEutrTemplatesUseCase.js | Done
375 | 003-eutr-templates | EUTR Templates Management | Phase 63: CloneTemplateDialog + Wiring | US7 | T280 | Create CloneTemplateDialog.jsx (New name/Alert for + confirm warning) | Done
376 | 003-eutr-templates | EUTR Templates Management | Phase 63: CloneTemplateDialog + Wiring | US7 | T281 | Wire Clone icon on TemplateListPage to open CloneTemplateDialog | Done
377 | 003-eutr-templates | EUTR Templates Management | Phase 64: Validation Update 15 |  | T282 | Run Scenario 3b step 9 (reference copy on version-up) | Done
378 | 003-eutr-templates | EUTR Templates Management | Phase 64: Validation Update 15 |  | T283 | Run Scenario 20 Clone Template end-to-end | Done
379 | 003-eutr-templates | EUTR Templates Management | Phase 64: Validation Update 15 |  | T284 | Verify clone endpoint reuses existing Create authorization policy | Done
380 | 003-eutr-templates | EUTR Templates Management | Phase 64: Validation Update 15 |  | T285 | Verify all new Clone UI text is in English | Done
381 | 003-eutr-templates | EUTR Templates Management | Phase 64: Validation Update 15 |  | T286 | Record Scenario 3b/20 verification outcomes in quickstart.md | Done
382 | 003-eutr-templates | EUTR Templates Management | Phase 65: Status Column and Copy/SetStatus Helpers | US3 | T287 | Create migration adding Status column to eutr_templates | Done
383 | 003-eutr-templates | EUTR Templates Management | Phase 65: Status Column and Copy/SetStatus Helpers | US3 | T288 | Add Status column to fresh-install eutr_db.sql | Done
384 | 003-eutr-templates | EUTR Templates Management | Phase 65: Status Column and Copy/SetStatus Helpers | US3 | T289 | Add Status property to EutrTemplates entity | Done
385 | 003-eutr-templates | EUTR Templates Management | Phase 65: Status Column and Copy/SetStatus Helpers | US3 | T290 | Create TemplateStatusEnum (Draft=0, Approved=1) | Done
386 | 003-eutr-templates | EUTR Templates Management | Phase 65: Status Column and Copy/SetStatus Helpers | US3 | T291 | Add CopyDetailTreeAsync as private service method (deviation from repository) | Done
387 | 003-eutr-templates | EUTR Templates Management | Phase 65: Status Column and Copy/SetStatus Helpers | US3 | T292 | Implement CopyDetailTreeAsync extracted from CloneAsync logic | Done
388 | 003-eutr-templates | EUTR Templates Management | Phase 65: Status Column and Copy/SetStatus Helpers | US3 | T293 | Refactor CloneAsync to call CopyDetailTreeAsync | Done
389 | 003-eutr-templates | EUTR Templates Management | Phase 65: Status Column and Copy/SetStatus Helpers | US3 | T294 | Add SetStatusAsync to repository interface | Done
390 | 003-eutr-templates | EUTR Templates Management | Phase 65: Status Column and Copy/SetStatus Helpers | US3 | T295 | Implement SetStatusAsync single-column update | Done
391 | 003-eutr-templates | EUTR Templates Management | Phase 66: Remove 24h Branch, Approve/Request-Change | US2 | T296 | AddAsync sets Status=Draft unconditionally on new templates | Done
392 | 003-eutr-templates | EUTR Templates Management | Phase 66: Remove 24h Branch, Approve/Request-Change | US7 | T297 | CloneAsync sets Status=Draft unconditionally regardless of source | Done
393 | 003-eutr-templates | EUTR Templates Management | Phase 66: Remove 24h Branch, Approve/Request-Change | US3 | T298 | Remove 24h branch from UpdateAsync, reject edits when Approved | Done
394 | 003-eutr-templates | EUTR Templates Management | Phase 66: Remove 24h Branch, Approve/Request-Change | US8 | T299 | Add ApproveAsync service method (Draft to Approved, no version change) | Done
395 | 003-eutr-templates | EUTR Templates Management | Phase 66: Remove 24h Branch, Approve/Request-Change | US9 | T300 | Add RequestChangeAsync service method (Approved to new Draft version) | Done
396 | 003-eutr-templates | EUTR Templates Management | Phase 66: Remove 24h Branch, Approve/Request-Change | US8 | T301 | Add ApproveAsync/RequestChangeAsync signatures to service interface | Done
397 | 003-eutr-templates | EUTR Templates Management | Phase 66: Remove 24h Branch, Approve/Request-Change | US8 | T302 | Add POST {id}/approve endpoint | Done
398 | 003-eutr-templates | EUTR Templates Management | Phase 66: Remove 24h Branch, Approve/Request-Change | US9 | T303 | Add POST {id}/request-change endpoint | Done
399 | 003-eutr-templates | EUTR Templates Management | Phase 67: Frontend Status Enum, Entity, API/Repo/UseCases | US8 | T304 | Add TEMPLATE_STATUS/TEMPLATE_STATUS_LABELS to helpers.js | Done
400 | 003-eutr-templates | EUTR Templates Management | Phase 67: Frontend Status Enum, Entity, API/Repo/UseCases | US8 | T305 | Add status field to EutrTemplates.js domain entity | Done
401 | 003-eutr-templates | EUTR Templates Management | Phase 67: Frontend Status Enum, Entity, API/Repo/UseCases | US8 | T306 | Add approve/requestChange methods to eutrTemplatesApi.js | Done
402 | 003-eutr-templates | EUTR Templates Management | Phase 67: Frontend Status Enum, Entity, API/Repo/UseCases | US8 | T307 | Add approve/requestChange passthrough to repository/interface | Done
403 | 003-eutr-templates | EUTR Templates Management | Phase 67: Frontend Status Enum, Entity, API/Repo/UseCases | US8 | T308 | Create ApproveEutrTemplatesUseCase.js | Done
404 | 003-eutr-templates | EUTR Templates Management | Phase 67: Frontend Status Enum, Entity, API/Repo/UseCases | US9 | T309 | Create RequestChangeEutrTemplatesUseCase.js | Done
405 | 003-eutr-templates | EUTR Templates Management | Phase 68: Status Chip and Approve/Request-Change Toolbar | US8 | T310 | Add real Status Chip per row on TemplateListPage | Done
406 | 003-eutr-templates | EUTR Templates Management | Phase 68: Status Chip and Approve/Request-Change Toolbar | US8 | T311 | Rewire Approve/Request change toolbar buttons with selection gating | Done
407 | 003-eutr-templates | EUTR Templates Management | Phase 68: Status Chip and Approve/Request-Change Toolbar | US8 | T312 | Wire Approve/Request change ConfirmDialog to call use cases and refresh | Done
408 | 003-eutr-templates | EUTR Templates Management | Phase 69: TemplateBuilderPage Read-Only Gate | US3 | T313 | Lock TemplateBuilderPage fields/actions when template Status=Approved | Done
409 | 003-eutr-templates | EUTR Templates Management | Phase 70: Validation Update 16 |  | T314 | Run Scenario 3'a (Save always updates in place regardless of age) | Done
410 | 003-eutr-templates | EUTR Templates Management | Phase 70: Validation Update 16 |  | T315 | Run Scenario 3'b (Approve gating, read-only, HTTP 400 on Approved edit) | Done
411 | 003-eutr-templates | EUTR Templates Management | Phase 70: Validation Update 16 |  | T316 | Run Scenario 3'c (Request change creates new Draft version) | Done
412 | 003-eutr-templates | EUTR Templates Management | Phase 70: Validation Update 16 |  | T317 | Run Scenario 3'd (toolbar enable/disable matrix) | Done
413 | 003-eutr-templates | EUTR Templates Management | Phase 70: Validation Update 16 |  | T318 | Verify clean backend and frontend builds | Done
414 | 003-eutr-templates | EUTR Templates Management | Phase 70: Validation Update 16 |  | T319 | Verify all new Status/Approve/Request-change UI text is English | Done
415 | 003-eutr-templates | EUTR Templates Management | Phase 70: Validation Update 16 |  | T320 | Verify new endpoints reuse existing Update authorization policy | Done
416 | 003-eutr-templates | EUTR Templates Management | Phase 70: Validation Update 16 |  | T321 | Record Scenario 3'a-3'd verification outcomes | Done
417 | 003-eutr-templates | EUTR Templates Management | Phase 71: Drag-and-Drop Wiring | US3 | T322 | Add dnd-kit imports and sensors to TemplateBuilderPage.jsx | Done
418 | 003-eutr-templates | EUTR Templates Management | Phase 71: Drag-and-Drop Wiring | US3 | T323 | Add SortableStepLabel component wrapping step row with drag handle | Done
419 | 003-eutr-templates | EUTR Templates Management | Phase 71: Drag-and-Drop Wiring | US3 | T324 | Modify renderTree to wrap sibling groups in SortableContext | Done
420 | 003-eutr-templates | EUTR Templates Management | Phase 71: Drag-and-Drop Wiring | US3 | T325 | Add handleDragEnd resolving sibling reorder via reorderSiblings | Done
421 | 003-eutr-templates | EUTR Templates Management | Phase 71: Drag-and-Drop Wiring | US3 | T326 | Wrap tree view in DndContext with sensors/collision detection | Done
422 | 003-eutr-templates | EUTR Templates Management | Phase 72: Validation Update 17 |  | T327 | Verify drag reorder matches Move Up/Down result and persists on Save | Done
423 | 003-eutr-templates | EUTR Templates Management | Phase 72: Validation Update 17 |  | T328 | Verify Move Up/Down still work unchanged | Done
424 | 003-eutr-templates | EUTR Templates Management | Phase 72: Validation Update 17 |  | T329 | Verify no reparenting occurs via drag across different parents | Done
425 | 003-eutr-templates | EUTR Templates Management | Phase 72: Validation Update 17 |  | T330 | Verify drag-and-drop disabled when Status=Approved | Done
426 | 003-eutr-templates | EUTR Templates Management | Phase 72: Validation Update 17 |  | T331 | Verify clean build/lint, no new dependency added | Done
427 | 003-eutr-templates | EUTR Templates Management | Phase 72: Validation Update 17 |  | T332 | Verify no UI text regressions from drag handle addition | Done
428 | 003-eutr-templates | EUTR Templates Management | Phase 72: Validation Update 17 |  | T333 | Run quickstart Scenario 2b'' end-to-end | To do
429 | 003-eutr-templates | EUTR Templates Management | Phase 73: SetDefaultAsync Backend | US3 | T334 | Create SetDefaultEutrTemplatesRequestDto (IsDefault byte) | Done
430 | 003-eutr-templates | EUTR Templates Management | Phase 73: SetDefaultAsync Backend | US3 | T335 | Add SetIsDefaultAsync to repository interface | Done
431 | 003-eutr-templates | EUTR Templates Management | Phase 73: SetDefaultAsync Backend | US3 | T336 | Implement SetIsDefaultAsync single-column update | Done
432 | 003-eutr-templates | EUTR Templates Management | Phase 73: SetDefaultAsync Backend | US3 | T337 | Add SetDefaultAsync service method (Status-agnostic, atomic) | Done
433 | 003-eutr-templates | EUTR Templates Management | Phase 73: SetDefaultAsync Backend | US3 | T338 | Add POST {id}/set-default endpoint | Done
434 | 003-eutr-templates | EUTR Templates Management | Phase 74: Set-as-Default While Approved Frontend | US3 | T339 | Add setDefault(id, isDefault) to eutrTemplatesApi.js | Done
435 | 003-eutr-templates | EUTR Templates Management | Phase 74: Set-as-Default While Approved Frontend | US3 | T340 | Add setDefault passthrough to repository/interface | Done
436 | 003-eutr-templates | EUTR Templates Management | Phase 74: Set-as-Default While Approved Frontend | US3 | T341 | Create SetDefaultEutrTemplatesUseCase.js | Done
437 | 003-eutr-templates | EUTR Templates Management | Phase 74: Set-as-Default While Approved Frontend | US3 | T342 | Wire Set-as-default checkbox to stay enabled with confirm dialog when Approved | Done
438 | 003-eutr-templates | EUTR Templates Management | Phase 75: Validation Update 18 |  | T343 | Verify Draft behavior of Set-as-default checkbox unchanged | Done
439 | 003-eutr-templates | EUTR Templates Management | Phase 75: Validation Update 18 |  | T344 | Verify Approved header lock exception for Set-as-default only | Done
440 | 003-eutr-templates | EUTR Templates Management | Phase 75: Validation Update 18 |  | T345 | Verify confirm-dialog gating before persisting default change | Done
441 | 003-eutr-templates | EUTR Templates Management | Phase 75: Validation Update 18 |  | T346 | Verify Yes persists only IsDefault, clears other default globally | Done
442 | 003-eutr-templates | EUTR Templates Management | Phase 75: Validation Update 18 |  | T347 | Verify set-default endpoint is Status-agnostic | Done
443 | 003-eutr-templates | EUTR Templates Management | Phase 75: Validation Update 18 |  | T348 | Run quickstart Scenario 21 end-to-end | To do
444 | 003-eutr-templates | EUTR Templates Management | Phase 76: TakeFrom Sourced from eutr_reference_types | US3 | T349 | Load referenceTypes on mount, derive takeFromOptions/labels in TemplateBuilderPage | Done
445 | 003-eutr-templates | EUTR Templates Management | Phase 76: TakeFrom Sourced from eutr_reference_types | US3 | T350 | BulkAddStepsDialog accepts takeFromOptions prop instead of hardcoded constant | Done
446 | 003-eutr-templates | EUTR Templates Management | Phase 77: TemplateListPage via DataGridStyled | US1 | T351 | Rewrite useEutrTemplatesColumns.jsx with 6 DataGrid column definitions | Done
447 | 003-eutr-templates | EUTR Templates Management | Phase 77: TemplateListPage via DataGridStyled | US1 | T352 | Swap TemplateListPage.jsx Table markup for DataGridStyled/DataGrid | Done
448 | 003-eutr-templates | EUTR Templates Management | Phase 78: Validation Update 19 |  | T353 | Verify TakeFrom combobox reflects eutr_reference_types live | Done
449 | 003-eutr-templates | EUTR Templates Management | Phase 78: Validation Update 19 |  | T354 | Verify TakeFrom persistence and label lookup, blank when deleted | Done
450 | 003-eutr-templates | EUTR Templates Management | Phase 78: Validation Update 19 |  | T355 | Verify no regression on eutr-sales-orders pages using old constants | Done
451 | 003-eutr-templates | EUTR Templates Management | Phase 78: Validation Update 19 |  | T356 | Verify DataGridStyled rendering with identical column content | Done
452 | 003-eutr-templates | EUTR Templates Management | Phase 78: Validation Update 19 |  | T357 | Verify unchanged interactive behavior (search/pagination/bulk/actions) | Done
453 | 003-eutr-templates | EUTR Templates Management | Phase 78: Validation Update 19 |  | T358 | Run quickstart Scenario 22 and 23 end-to-end | To do
454 | 003-eutr-templates | EUTR Templates Management | Phase 79: Extend FilterMap Whitelist | US1 | T359 | Add Status/VersionId/IsDefault to FilterMap dictionary | Done
455 | 003-eutr-templates | EUTR Templates Management | Phase 80: Selective Column Filterable + Merge | US1 | T360 | Flip filterable:true on name/status/versionId/isDefault columns | Done
456 | 003-eutr-templates | EUTR Templates Management | Phase 80: Selective Column Filterable + Merge | US1 | T361 | Merge quick-search keyword and column-filter panel in filterModel | Done
457 | 003-eutr-templates | EUTR Templates Management | Phase 81: Validation Update 20 |  | T362 | Verify each filterable column actually filters server-side | Done
458 | 003-eutr-templates | EUTR Templates Management | Phase 81: Validation Update 20 |  | T363 | Verify non-filterable columns show no Filter option | Done
459 | 003-eutr-templates | EUTR Templates Management | Phase 81: Validation Update 20 |  | T364 | Verify quick-search and column filter coexist without overwriting | Done
460 | 003-eutr-templates | EUTR Templates Management | Phase 81: Validation Update 20 |  | T365 | Verify reverse order (column filter first, then search) also works | Done
461 | 003-eutr-templates | EUTR Templates Management | Phase 81: Validation Update 20 |  | T366 | Verify no regression on other EUTR list pages | Done
462 | 003-eutr-templates | EUTR Templates Management | Phase 81: Validation Update 20 |  | T367 | Run manual click-through of column filtering and search coexistence | To do
463 | 003-eutr-templates | EUTR Templates Management | Phase 82: Widen Step Exclusion to Whole Tree | US3 | T368 | Widen usedStepIds prop to include steps anywhere in the tree | Done
464 | 003-eutr-templates | EUTR Templates Management | Phase 82: Widen Step Exclusion to Whole Tree | US3 | T369 | Rename BulkAddStepsDialog prop to usedStepIds | Done
465 | 003-eutr-templates | EUTR Templates Management | Phase 83: Block Duplicate Name in Add New Step | US3 | T370 | Add duplicate-name guard blocking Add new step with inline error | Done
466 | 003-eutr-templates | EUTR Templates Management | Phase 84: Validation Update 21 |  | T371 | Verify whole-tree exclusion (FR-076) across dialogs/targets | Done
467 | 003-eutr-templates | EUTR Templates Management | Phase 84: Validation Update 21 |  | T372 | Verify duplicate-name block (FR-077) case/whitespace-insensitive | Done
468 | 003-eutr-templates | EUTR Templates Management | Phase 84: Validation Update 21 |  | T373 | Verify duplicate-name check covers same-session pending entries | Done
469 | 003-eutr-templates | EUTR Templates Management | Phase 84: Validation Update 21 |  | T374 | Verify Edit step (FR-008b) is unaffected by the new exclusion/block | Done
470 | 003-eutr-templates | EUTR Templates Management | Phase 84: Validation Update 21 |  | T375 | Verify no backend/contract regression from frontend-only change | Done
471 | 003-eutr-templates | EUTR Templates Management | Phase 84: Validation Update 21 |  | T376 | Run eslint/build and (partial) manual click-through of Scenario 25 | Done
472 | 003-eutr-templates | EUTR Templates Management | Phase 85: By-StepId Default Lookup Backend | US3 | T377 | Add GetByStepIdsAsync to repository interface | Done
473 | 003-eutr-templates | EUTR Templates Management | Phase 85: By-StepId Default Lookup Backend | US3 | T378 | Implement GetByStepIdsAsync querying eutr_reference_type_details | Done
474 | 003-eutr-templates | EUTR Templates Management | Phase 85: By-StepId Default Lookup Backend | US3 | T379 | Add GetDefaultTypeIdByStepIdsAsync to service interface | Done
475 | 003-eutr-templates | EUTR Templates Management | Phase 85: By-StepId Default Lookup Backend | US3 | T380 | Implement GetDefaultTypeIdByStepIdsAsync with lowest-Id tie-break | Done
476 | 003-eutr-templates | EUTR Templates Management | Phase 85: By-StepId Default Lookup Backend | US3 | T381 | Add POST default-by-steps controller endpoint | Done
477 | 003-eutr-templates | EUTR Templates Management | Phase 86: Default-Lookup Frontend API Layer | US3 | T382 | Add getDefaultByStepIds to eutrReferenceTypeDetailsApi.js | Done
478 | 003-eutr-templates | EUTR Templates Management | Phase 86: Default-Lookup Frontend API Layer | US3 | T383 | Add getDefaultByStepIds to domain interface | Done
479 | 003-eutr-templates | EUTR Templates Management | Phase 86: Default-Lookup Frontend API Layer | US3 | T384 | Implement getDefaultByStepIds in repository | Done
480 | 003-eutr-templates | EUTR Templates Management | Phase 86: Default-Lookup Frontend API Layer | US3 | T385 | Create GetDefaultByStepIdsEutrReferenceTypeDetailsUseCase.js | Done
481 | 003-eutr-templates | EUTR Templates Management | Phase 87: TemplateBuilderPage Default Computation Wiring | US3 | T386 | Compute defaultTakeFromByStepId/defaultTakeFromId, pass to BulkAddStepsDialog | Done
482 | 003-eutr-templates | EUTR Templates Management | Phase 88: BulkAddStepsDialog Default Logic | US3 | T387 | Apply Required + two-tier Take From default on tick/select-all/new-step | Done
483 | 003-eutr-templates | EUTR Templates Management | Phase 89: Validation Update 22 |  | T388 | Verify backend by-StepId lookup returns lowest-Id TypeId per StepId | Done
484 | 003-eutr-templates | EUTR Templates Management | Phase 89: Validation Update 22 |  | T389 | Verify Requirement Type defaults to Required for mapped and unmapped steps | Done
485 | 003-eutr-templates | EUTR Templates Management | Phase 89: Validation Update 22 |  | T390 | Verify Take From default resolution (PO vs mapped TypeId) | Done
486 | 003-eutr-templates | EUTR Templates Management | Phase 89: Validation Update 22 |  | T391 | Verify untick/retick reapplies default, not manual override | Done
487 | 003-eutr-templates | EUTR Templates Management | Phase 89: Validation Update 22 |  | T392 | Verify Add new step always defaults Required/PO with no mapping lookup | Done
488 | 003-eutr-templates | EUTR Templates Management | Phase 89: Validation Update 22 |  | T393 | Verify manually-changed Take From survives Add and Save | Done
489 | 003-eutr-templates | EUTR Templates Management | Phase 89: Validation Update 22 |  | T394 | Verify blank-fallback when no PO reference type exists | Done
490 | 003-eutr-templates | EUTR Templates Management | Phase 89: Validation Update 22 |  | T395 | Verify Edit step (FR-008b) unaffected by new default logic | Done
491 | 003-eutr-templates | EUTR Templates Management | Phase 89: Validation Update 22 |  | T396 | Run backend/frontend build+lint and (partial) manual click-through of Scenario 26 | Done
492 | 004-eutr-documents | EUTR Documents Management | Phase 1: Setup (Shared Infrastructure) |  | T001 | Create migration changing eutr_documents.Name column to VARCHAR(255) | Done
493 | 004-eutr-documents | EUTR Documents Management | Phase 1: Setup (Shared Infrastructure) |  | T002 | Update eutr_db.sql design docs so Name column type matches the migration | Done
494 | 004-eutr-documents | EUTR Documents Management | Phase 1: Setup (Shared Infrastructure) |  | T003 | Create frontend feature folder structure for eutr-documents pages/usecases | Done
495 | 004-eutr-documents | EUTR Documents Management | Phase 2: Foundational (Blocking Prerequisites) |  | T004 | Create EutrDocuments domain entity (Id, Name, FileId, ValidFrom, ValidTo) | Done
496 | 004-eutr-documents | EUTR Documents Management | Phase 2: Foundational (Blocking Prerequisites) |  | T005 | Create EutrDocumentsRequestDto (Name, ValidFrom, ValidTo) | Done
497 | 004-eutr-documents | EUTR Documents Management | Phase 2: Foundational (Blocking Prerequisites) |  | T006 | Create EutrDocumentsResponseDto (empty subclass of entity) | Done
498 | 004-eutr-documents | EUTR Documents Management | Phase 2: Foundational (Blocking Prerequisites) |  | T007 | Create EutrDocumentsRequestDtoValidator requiring Name | Done
499 | 004-eutr-documents | EUTR Documents Management | Phase 2: Foundational (Blocking Prerequisites) |  | T008 | Add AutoMapper mappings for EutrDocuments DTOs/entity | Done
500 | 004-eutr-documents | EUTR Documents Management | Phase 2: Foundational (Blocking Prerequisites) |  | T009 | Create IEutrDocumentsService interface (base CRUD + GetPagedAsync) | Done
501 | 004-eutr-documents | EUTR Documents Management | Phase 2: Foundational (Blocking Prerequisites) |  | T010 | Create EutrDocumentsService implementing base CRUD service | Done
502 | 004-eutr-documents | EUTR Documents Management | Phase 2: Foundational (Blocking Prerequisites) |  | T011 | Create EutrDocumentsController skeleton with DI | Done
503 | 004-eutr-documents | EUTR Documents Management | Phase 2: Foundational (Blocking Prerequisites) |  | T012 | Register EutrDocumentsService and validator in DI container | Done
504 | 004-eutr-documents | EUTR Documents Management | Phase 2: Foundational (Blocking Prerequisites) |  | T013 | Create frontend EutrDocuments domain entity | Done
505 | 004-eutr-documents | EUTR Documents Management | Phase 2: Foundational (Blocking Prerequisites) |  | T014 | Create IEutrDocumentsRepository interface | Done
506 | 004-eutr-documents | EUTR Documents Management | Phase 2: Foundational (Blocking Prerequisites) |  | T015 | Create eutrDocumentsApi.js base API client | Done
507 | 004-eutr-documents | EUTR Documents Management | Phase 2: Foundational (Blocking Prerequisites) |  | T016 | Create RestEutrDocumentsRepository implementation | Done
508 | 004-eutr-documents | EUTR Documents Management | Phase 2: Foundational (Blocking Prerequisites) |  | T017 | Register EutrDocuments repository in DI container | Done
509 | 004-eutr-documents | EUTR Documents Management | Phase 2: Foundational (Blocking Prerequisites) |  | T018 | Add lazy route/component mapping for the eutr-documents list page | Done
510 | 004-eutr-documents | EUTR Documents Management | Phase 2: Foundational (Blocking Prerequisites) |  | T019 | Add route for /eutr/documents/add page | Done
511 | 004-eutr-documents | EUTR Documents Management | Phase 2: Foundational (Blocking Prerequisites) |  | T020 | Add 'EUTR documents' menu item under the EUTR parent menu | Done
512 | 004-eutr-documents | EUTR Documents Management | Phase 2: Foundational (Blocking Prerequisites) |  | T021 | Create page shell with breadcrumb and empty DataGrid container | Done
513 | 004-eutr-documents | EUTR Documents Management | Phase 3: User Story 1 - View EUTR documents list (P1, MVP) | US1 | T022 | Add POST /get-all and GET /get-by-id actions to controller | Done
514 | 004-eutr-documents | EUTR Documents Management | Phase 3: User Story 1 - View EUTR documents list (P1, MVP) | US1 | T023 | Create GetPagingEutrDocumentsUseCase | Done
515 | 004-eutr-documents | EUTR Documents Management | Phase 3: User Story 1 - View EUTR documents list (P1, MVP) | US1 | T024 | Create useEutrDocumentsData hook for pagination/sort/filter | Done
516 | 004-eutr-documents | EUTR Documents Management | Phase 3: User Story 1 - View EUTR documents list (P1, MVP) | US1 | T025 | Create useEutrDocumentsColumns hook with placeholder Step name/Conditions/Type columns | Done
517 | 004-eutr-documents | EUTR Documents Management | Phase 3: User Story 1 - View EUTR documents list (P1, MVP) | US1 | T026 | Wire server-mode DataGrid into index.jsx with breadcrumb and empty state | Done
518 | 004-eutr-documents | EUTR Documents Management | Phase 4: User Story 2 - Add new document (P1) | US2 | T027 | Add POST / create action to controller | Done
519 | 004-eutr-documents | EUTR Documents Management | Phase 4: User Story 2 - Add new document (P1) | US2 | T028 | Create CreateEutrDocumentsUseCase | Done
520 | 004-eutr-documents | EUTR Documents Management | Phase 4: User Story 2 - Add new document (P1) | US2 | T029 | Create EutrDocumentsAdd.jsx page (File name, Valid from/to, Save/Back) | Done
521 | 004-eutr-documents | EUTR Documents Management | Phase 4: User Story 2 - Add new document (P1) | US2 | T030 | Wire toolbar Add button to navigate to the add page | Done
522 | 004-eutr-documents | EUTR Documents Management | Phase 5: User Story 3 - Edit document info (P2) | US3 | T031 | Add PUT /{id} update action to controller | Done
523 | 004-eutr-documents | EUTR Documents Management | Phase 5: User Story 3 - Edit document info (P2) | US3 | T032 | Create UpdateEutrDocumentsUseCase | Done
524 | 004-eutr-documents | EUTR Documents Management | Phase 5: User Story 3 - Edit document info (P2) | US3 | T033 | Create EutrDocumentsModal.jsx Edit popup (File name, Valid dates) | Done
525 | 004-eutr-documents | EUTR Documents Management | Phase 5: User Story 3 - Edit document info (P2) | US3 | T034 | Create EutrDocumentsActionCell.jsx with Edit/Delete icons | Done
526 | 004-eutr-documents | EUTR Documents Management | Phase 5: User Story 3 - Edit document info (P2) | US3 | T035 | Wire Edit flow: open modal, update, refresh grid | Done
527 | 004-eutr-documents | EUTR Documents Management | Phase 6: User Story 4 - Delete document (P2) | US4 | T036 | Add DELETE /{id} and POST /delete-multi actions to controller | Done
528 | 004-eutr-documents | EUTR Documents Management | Phase 6: User Story 4 - Delete document (P2) | US4 | T037 | Create DeleteEutrDocumentsUseCase | Done
529 | 004-eutr-documents | EUTR Documents Management | Phase 6: User Story 4 - Delete document (P2) | US4 | T038 | Create DeleteMultiEutrDocumentsUseCase | Done
530 | 004-eutr-documents | EUTR Documents Management | Phase 6: User Story 4 - Delete document (P2) | US4 | T039 | Wire delete confirmation dialog and multi-select delete | Done
531 | 004-eutr-documents | EUTR Documents Management | Phase 7: User Story 5 - View icon placeholder (P3) | US5 | T040 | Add placeholder View icon (silent no-op) to ActionCell | Done
532 | 004-eutr-documents | EUTR Documents Management | Phase 8: Polish & Cross-Cutting Concerns |  | T041 | Review all UI text is in English (labels, buttons, messages) | Done
533 | 004-eutr-documents | EUTR Documents Management | Phase 8: Polish & Cross-Cutting Concerns |  | T042 | Handle empty/error/loading states across grid and Save button | Done
534 | 004-eutr-documents | EUTR Documents Management | Phase 8: Polish & Cross-Cutting Concerns |  | T043 | Add permission gating for Add/Edit/Delete buttons based on menu permissions | Done
535 | 004-eutr-documents | EUTR Documents Management | Phase 8: Polish & Cross-Cutting Concerns |  | T044 | Run manual quickstart test scenarios 1-8 and fix issues found | To do
536 | 004-eutr-documents | EUTR Documents Management | Phase 8: Polish & Cross-Cutting Concerns |  | T045 | [Ops] Run migration 09 on real DB before testing Create/Update | To do
537 | 004-eutr-documents | EUTR Documents Management | Phase 8: Polish & Cross-Cutting Concerns |  | T046 | [Ops] Create menu code and permissions in DB for screen access | To do
538 | 004-eutr-documents | EUTR Documents Management | Phase 9: Update 3 - Add page UI redesign (Type/List PO/Upload manual, UI only) | US2 | T047 | Add Type Autocomplete (TAKE_FROM_OPTIONS: PO/Upload manual) to Add page | Done
539 | 004-eutr-documents | EUTR Documents Management | Phase 9: Update 3 - Add page UI redesign (Type/List PO/Upload manual, UI only) | US2 | T048 | Declare static demo data constants DEMO_PO_LIST and DEMO_FILE_LIST | Done
540 | 004-eutr-documents | EUTR Documents Management | Phase 9: Update 3 - Add page UI redesign (Type/List PO/Upload manual, UI only) | US2 | T049 | Render Screen1 (List PO table + drag-drop area) when Type=PO | Done
541 | 004-eutr-documents | EUTR Documents Management | Phase 9: Update 3 - Add page UI redesign (Type/List PO/Upload manual, UI only) | US2 | T050 | Render Screen2 (drag-drop + Assign condition button + file table) when Type=Upload manual | Done
542 | 004-eutr-documents | EUTR Documents Management | Phase 9: Update 3 - Add page UI redesign (Type/List PO/Upload manual, UI only) | US2 | T051 | Review all new UI text is in English | Done
543 | 004-eutr-documents | EUTR Documents Management | Phase 9: Update 3 - Add page UI redesign (Type/List PO/Upload manual, UI only) | US2 | T052 | Manual test scenarios 9-11 for Type switching and demo layouts | To do
544 | 004-eutr-documents | EUTR Documents Management | Phase 10: Update 4 - List PO real data via shared reference API (refType 15/16) | US2 | T053 | Register RSVNEutrPurchOrders (refType 15) and RSVNEutrSalesOrderPurchases (refType 16) mappings | Done
545 | 004-eutr-documents | EUTR Documents Management | Phase 10: Update 4 - List PO real data via shared reference API (refType 15/16) | US2 | T054 | Add case 15 mapping in MapDynamicsResponse for PO data | Done
546 | 004-eutr-documents | EUTR Documents Management | Phase 10: Update 4 - List PO real data via shared reference API (refType 15/16) | US2 | T055 | Add case 16 mapping in MapDynamicsResponse for Sales Order Purchase data | Done
547 | 004-eutr-documents | EUTR Documents Management | Phase 10: Update 4 - List PO real data via shared reference API (refType 15/16) | US2 | T056 | Add EUTR_PURCH_ORDER/EUTR_SALES_ORDER_PURCHASE values to ObjectType enum | Done
548 | 004-eutr-documents | EUTR Documents Management | Phase 10: Update 4 - List PO real data via shared reference API (refType 15/16) | US2 | T057 | Replace DEMO_PO_LIST with real data via useReferenceObjects(refType=15) | Done
549 | 004-eutr-documents | EUTR Documents Management | Phase 10: Update 4 - List PO real data via shared reference API (refType 15/16) | US2 | T058 | Show 'No data'/error states for List PO from useReferenceObjects state | Done
550 | 004-eutr-documents | EUTR Documents Management | Phase 10: Update 4 - List PO real data via shared reference API (refType 15/16) | US2 | T059 | Manual test scenarios 9/9a/9b for List PO real API data | To do
551 | 004-eutr-documents | EUTR Documents Management | Phase 11: Update 5 - PO search box filters via API | US2 | T060 | Remove local filteredPoList/poSearchTerms state, use server-filtered poList directly | Done
552 | 004-eutr-documents | EUTR Documents Management | Phase 11: Update 5 - PO search box filters via API | US2 | T061 | Add debounced (500ms) API call for PO search box using lodash.debounce | Done
553 | 004-eutr-documents | EUTR Documents Management | Phase 11: Update 5 - PO search box filters via API | US2 | T062 | Manual test scenarios 9c/9d for debounced PO search | To do
554 | 004-eutr-documents | EUTR Documents Management | Phase 12: Update 6 - Real SharePoint Upload button on Screen1 | US2 | T063 | Create EutrMultiUploadFileRequest DTO (Files, PoCode) | Done
555 | 004-eutr-documents | EUTR Documents Management | Phase 12: Update 6 - Real SharePoint Upload button on Screen1 | US2 | T064 | Create EutrUploadFileResultDto DTO | Done
556 | 004-eutr-documents | EUTR Documents Management | Phase 12: Update 6 - Real SharePoint Upload button on Screen1 | US2 | T065 | Create IEutrUploadService interface | Done
557 | 004-eutr-documents | EUTR Documents Management | Phase 12: Update 6 - Real SharePoint Upload button on Screen1 | US2 | T066 | Implement EutrUploadService: upload to SharePoint and create eutr_documents per file | Done
558 | 004-eutr-documents | EUTR Documents Management | Phase 12: Update 6 - Real SharePoint Upload button on Screen1 | US2 | T067 | Add eutr-upload-multi action to SharepointController | Done
559 | 004-eutr-documents | EUTR Documents Management | Phase 12: Update 6 - Real SharePoint Upload button on Screen1 | US2 | T068 | Register IEutrUploadService in DI | Done
560 | 004-eutr-documents | EUTR Documents Management | Phase 12: Update 6 - Real SharePoint Upload button on Screen1 | US2 | T069 | Add SharePointEutrPath config key to appsettings.json | Done
561 | 004-eutr-documents | EUTR Documents Management | Phase 12: Update 6 - Real SharePoint Upload button on Screen1 | US2 | T070 | Add SharePointEutrPath config key to appsettings.Development.json | Done
562 | 004-eutr-documents | EUTR Documents Management | Phase 12: Update 6 - Real SharePoint Upload button on Screen1 | US2 | T071 | Declare uploadEutrFilesMulti in ISharePointRepository | Done
563 | 004-eutr-documents | EUTR Documents Management | Phase 12: Update 6 - Real SharePoint Upload button on Screen1 | US2 | T072 | Implement uploadEutrFilesMulti in RestSharePointRepository (multipart FormData) | Done
564 | 004-eutr-documents | EUTR Documents Management | Phase 12: Update 6 - Real SharePoint Upload button on Screen1 | US2 | T073 | Add executeEutrMulti method to UploadToSharePointUseCase | Done
565 | 004-eutr-documents | EUTR Documents Management | Phase 12: Update 6 - Real SharePoint Upload button on Screen1 | US2 | T074 | Use selectedPoId/selectedPo state to gate Upload button, remove auto-select | Done
566 | 004-eutr-documents | EUTR Documents Management | Phase 12: Update 6 - Real SharePoint Upload button on Screen1 | US2 | T075 | Replace drag-drop area with Upload button, hidden file input, client-side validation | Done
567 | 004-eutr-documents | EUTR Documents Management | Phase 12: Update 6 - Real SharePoint Upload button on Screen1 | US2 | T076 | Wire file-select handler to call executeEutrMulti and show result snackbar | Done
568 | 004-eutr-documents | EUTR Documents Management | Phase 12: Update 6 - Real SharePoint Upload button on Screen1 | US2 | T077 | Review all new upload-related UI text is in English | Done
569 | 004-eutr-documents | EUTR Documents Management | Phase 12: Update 6 - Real SharePoint Upload button on Screen1 | US2 | T078 | Manual test scenarios 9e-9j for real SharePoint upload flow | To do
570 | 004-eutr-documents | EUTR Documents Management | Phase 13: Update 7 - Redesigned Upload area + prefix validation + eutr_references | US2 | T079 | Create migration adding StepId column to eutr_references | Done
571 | 004-eutr-documents | EUTR Documents Management | Phase 13: Update 7 - Redesigned Upload area + prefix validation + eutr_references | US2 | T080 | Sync StepId column/FK into eutr_db.sql design docs | Done
572 | 004-eutr-documents | EUTR Documents Management | Phase 13: Update 7 - Redesigned Upload area + prefix validation + eutr_references | US2 | T081 | Create EutrReferences domain entity | Done
573 | 004-eutr-documents | EUTR Documents Management | Phase 13: Update 7 - Redesigned Upload area + prefix validation + eutr_references | US2 | T082 | Add GetMatchingPrefixesAsync to IEutrMastersRepository | Done
574 | 004-eutr-documents | EUTR Documents Management | Phase 13: Update 7 - Redesigned Upload area + prefix validation + eutr_references | US2 | T083 | Implement GetMatchingPrefixesAsync via reverse LIKE match query | Done
575 | 004-eutr-documents | EUTR Documents Management | Phase 13: Update 7 - Redesigned Upload area + prefix validation + eutr_references | US2 | T084 | Add prefix validation step in EutrUploadService before SharePoint upload | Done
576 | 004-eutr-documents | EUTR Documents Management | Phase 13: Update 7 - Redesigned Upload area + prefix validation + eutr_references | US2 | T085 | Extend EutrUploadService to write EutrReferences per matched StepId in one transaction | Done
577 | 004-eutr-documents | EUTR Documents Management | Phase 13: Update 7 - Redesigned Upload area + prefix validation + eutr_references | US2 | T086 | Extract shared file-list handling function used by input change and drop | Done
578 | 004-eutr-documents | EUTR Documents Management | Phase 13: Update 7 - Redesigned Upload area + prefix validation + eutr_references | US2 | T087 | Redesign Upload card per upload.png mockup with real drag-drop support | Done
579 | 004-eutr-documents | EUTR Documents Management | Phase 13: Update 7 - Redesigned Upload area + prefix validation + eutr_references | US2 | T088 | Review all new UI text is in English | Done
580 | 004-eutr-documents | EUTR Documents Management | Phase 13: Update 7 - Redesigned Upload area + prefix validation + eutr_references | US2 | T089 | Manual test scenarios 9k-9o for redesigned upload and prefix validation | To do
581 | 004-eutr-documents | EUTR Documents Management | Phase 14: Update 8 - Load Step name/Type and List PO File/Step via eutr_references | US1 | T090 | Create EutrReferenceStepInfo projection DTO | Done
582 | 004-eutr-documents | EUTR Documents Management | Phase 14: Update 8 - Load Step name/Type and List PO File/Step via eutr_references | US2 | T091 | Create EutrReferencePoDocumentInfo projection DTO | Done
583 | 004-eutr-documents | EUTR Documents Management | Phase 14: Update 8 - Load Step name/Type and List PO File/Step via eutr_references | US2 | T092 | Create EutrDocumentsListPoReferencesRequestDto | Done
584 | 004-eutr-documents | EUTR Documents Management | Phase 14: Update 8 - Load Step name/Type and List PO File/Step via eutr_references | US2 | T093 | Create EutrDocumentsPoReferenceItemDto | Done
585 | 004-eutr-documents | EUTR Documents Management | Phase 14: Update 8 - Load Step name/Type and List PO File/Step via eutr_references | US2 | T094 | Create EutrDocumentsPoReferenceDto | Done
586 | 004-eutr-documents | EUTR Documents Management | Phase 14: Update 8 - Load Step name/Type and List PO File/Step via eutr_references | US1 | T095 | Create IEutrReferencesRepository interface with 2 read methods | Done
587 | 004-eutr-documents | EUTR Documents Management | Phase 14: Update 8 - Load Step name/Type and List PO File/Step via eutr_references | US1 | T096 | Create EutrReferencesRepository with GetStepInfoByDocumentIdsAsync | Done
588 | 004-eutr-documents | EUTR Documents Management | Phase 14: Update 8 - Load Step name/Type and List PO File/Step via eutr_references | US2 | T097 | Implement GetDocumentsByPoCodesAsync in EutrReferencesRepository | Done
589 | 004-eutr-documents | EUTR Documents Management | Phase 14: Update 8 - Load Step name/Type and List PO File/Step via eutr_references | US1 | T098 | Register IEutrReferencesRepository in DI | Done
590 | 004-eutr-documents | EUTR Documents Management | Phase 14: Update 8 - Load Step name/Type and List PO File/Step via eutr_references | US1 | T099 | Add StepNames/RefType fields to EutrDocumentsResponseDto | Done
591 | 004-eutr-documents | EUTR Documents Management | Phase 14: Update 8 - Load Step name/Type and List PO File/Step via eutr_references | US1 | T100 | Extend GetPagedAsync to attach Step name/Type info per document | Done
592 | 004-eutr-documents | EUTR Documents Management | Phase 14: Update 8 - Load Step name/Type and List PO File/Step via eutr_references | US2 | T101 | Add GetPoReferencesAsync to IEutrDocumentsService | Done
593 | 004-eutr-documents | EUTR Documents Management | Phase 14: Update 8 - Load Step name/Type and List PO File/Step via eutr_references | US2 | T102 | Implement GetPoReferencesAsync grouping documents by PO code | Done
594 | 004-eutr-documents | EUTR Documents Management | Phase 14: Update 8 - Load Step name/Type and List PO File/Step via eutr_references | US2 | T103 | Add POST /list-po-references action to controller | Done
595 | 004-eutr-documents | EUTR Documents Management | Phase 14: Update 8 - Load Step name/Type and List PO File/Step via eutr_references | US1 | T104 | Create MultiValueChips.jsx shared chip + '+N more' component | Done
596 | 004-eutr-documents | EUTR Documents Management | Phase 14: Update 8 - Load Step name/Type and List PO File/Step via eutr_references | US1 | T105 | Update columns hook to render Step name chips and Type label | Done
597 | 004-eutr-documents | EUTR Documents Management | Phase 14: Update 8 - Load Step name/Type and List PO File/Step via eutr_references | US1 | T106 | Add stepNames/refType fields to frontend EutrDocuments entity | Done
598 | 004-eutr-documents | EUTR Documents Management | Phase 14: Update 8 - Load Step name/Type and List PO File/Step via eutr_references | US1 | T107 | Verify stepNames/refType pass through repository mapping (no code change needed) | Done
599 | 004-eutr-documents | EUTR Documents Management | Phase 14: Update 8 - Load Step name/Type and List PO File/Step via eutr_references | US2 | T108 | Create GetEutrDocumentsPoReferencesUseCase | Done
600 | 004-eutr-documents | EUTR Documents Management | Phase 14: Update 8 - Load Step name/Type and List PO File/Step via eutr_references | US2 | T109 | Declare getPoReferences in IEutrDocumentsRepository | Done
601 | 004-eutr-documents | EUTR Documents Management | Phase 14: Update 8 - Load Step name/Type and List PO File/Step via eutr_references | US2 | T110 | Add listPoReferences function to eutrDocumentsApi.js | Done
602 | 004-eutr-documents | EUTR Documents Management | Phase 14: Update 8 - Load Step name/Type and List PO File/Step via eutr_references | US2 | T111 | Implement getPoReferences in RestEutrDocumentsRepository | Done
603 | 004-eutr-documents | EUTR Documents Management | Phase 14: Update 8 - Load Step name/Type and List PO File/Step via eutr_references | US2 | T112 | Add state/effect to fetch PO reference documents when a PO is selected | Done
604 | 004-eutr-documents | EUTR Documents Management | Phase 14: Update 8 - Load Step name/Type and List PO File/Step via eutr_references | US2 | T113 | Render List PO detail table rows from real poReferenceDocuments data | Done
605 | 004-eutr-documents | EUTR Documents Management | Phase 14: Update 8 - Load Step name/Type and List PO File/Step via eutr_references | US1 | T114 | Review new UI text is in English (Step name/Type labels) | Done
606 | 004-eutr-documents | EUTR Documents Management | Phase 14: Update 8 - Load Step name/Type and List PO File/Step via eutr_references | US2 | T115 | Review 'No data' text consistency in List PO detail table | Done
607 | 004-eutr-documents | EUTR Documents Management | Phase 14: Update 8 - Load Step name/Type and List PO File/Step via eutr_references | US1 | T116 | Manual test scenario 1a for real Step name/Type data | To do
608 | 004-eutr-documents | EUTR Documents Management | Phase 14: Update 8 - Load Step name/Type and List PO File/Step via eutr_references | US2 | T117 | Manual test scenarios 9p/9q for File name/Step name in List PO | To do
609 | 004-eutr-documents | EUTR Documents Management | Phase 15: Update 9 - Delete cascades eutr_references | US4 | T118 | Add DeleteByDocumentIdAsync to IEutrReferencesRepository | Done
610 | 004-eutr-documents | EUTR Documents Management | Phase 15: Update 9 - Delete cascades eutr_references | US4 | T119 | Implement DeleteByDocumentIdAsync via raw SQL delete | Done
611 | 004-eutr-documents | EUTR Documents Management | Phase 15: Update 9 - Delete cascades eutr_references | US4 | T120 | Override DeleteAsync in EutrDocumentsService with transactional cascade delete | Done
612 | 004-eutr-documents | EUTR Documents Management | Phase 15: Update 9 - Delete cascades eutr_references | US4 | T121 | Override DeleteMultiAsync with per-item transactions and collected failures | Done
613 | 004-eutr-documents | EUTR Documents Management | Phase 15: Update 9 - Delete cascades eutr_references | US4 | T122 | Manual test scenarios 5a-5c for cascading delete/rollback | To do
614 | 004-eutr-documents | EUTR Documents Management | Phase 16: Update 10 - View icon opens real file + per-file Delete in List PO | US5 | T123 | Add GET /get-file-by-idref action to controller (clone GetFileByIds) | Done
615 | 004-eutr-documents | EUTR Documents Management | Phase 16: Update 10 - View icon opens real file + per-file Delete in List PO | US2 | T124 | Add FileId field to EutrReferencePoDocumentInfo | Done
616 | 004-eutr-documents | EUTR Documents Management | Phase 16: Update 10 - View icon opens real file + per-file Delete in List PO | US2 | T125 | Add FileId field to EutrDocumentsPoReferenceItemDto | Done
617 | 004-eutr-documents | EUTR Documents Management | Phase 16: Update 10 - View icon opens real file + per-file Delete in List PO | US2 | T126 | Add FileId to SELECT in GetDocumentsByPoCodesAsync | Done
618 | 004-eutr-documents | EUTR Documents Management | Phase 16: Update 10 - View icon opens real file + per-file Delete in List PO | US2 | T127 | Assign FileId when building PO reference item DTOs | Done
619 | 004-eutr-documents | EUTR Documents Management | Phase 16: Update 10 - View icon opens real file + per-file Delete in List PO | US5 | T128 | Generalize FilePreviewer.jsx with optional fetchFile/onLoaded props | Done
620 | 004-eutr-documents | EUTR Documents Management | Phase 16: Update 10 - View icon opens real file + per-file Delete in List PO | US5 | T129 | Add getFileByIdRef function to eutrDocumentsApi.js | Done
621 | 004-eutr-documents | EUTR Documents Management | Phase 16: Update 10 - View icon opens real file + per-file Delete in List PO | US5 | T130 | Declare getFileByIdRef in IEutrDocumentsRepository | Done
622 | 004-eutr-documents | EUTR Documents Management | Phase 16: Update 10 - View icon opens real file + per-file Delete in List PO | US5 | T131 | Implement getFileByIdRef in RestEutrDocumentsRepository | Done
623 | 004-eutr-documents | EUTR Documents Management | Phase 16: Update 10 - View icon opens real file + per-file Delete in List PO | US5 | T132 | Create GetEutrDocumentsFileByIdRefUseCase | Done
624 | 004-eutr-documents | EUTR Documents Management | Phase 16: Update 10 - View icon opens real file + per-file Delete in List PO | US5 | T133 | Create EutrFileViewerDialog.jsx (preview dialog with Download button) | Done
625 | 004-eutr-documents | EUTR Documents Management | Phase 16: Update 10 - View icon opens real file + per-file Delete in List PO | US5 | T134 | Wire real View icon behavior (onView, disabled state, tooltip) in ActionCell | Done
626 | 004-eutr-documents | EUTR Documents Management | Phase 16: Update 10 - View icon opens real file + per-file Delete in List PO | US5 | T135 | Pass onView prop through columns hook | Done
627 | 004-eutr-documents | EUTR Documents Management | Phase 16: Update 10 - View icon opens real file + per-file Delete in List PO | US5 | T136 | Add viewerFile state and render EutrFileViewerDialog in index.jsx | Done
628 | 004-eutr-documents | EUTR Documents Management | Phase 16: Update 10 - View icon opens real file + per-file Delete in List PO | US2 | T137 | Wire View icon in List PO detail table to open file viewer dialog | Done
629 | 004-eutr-documents | EUTR Documents Management | Phase 16: Update 10 - View icon opens real file + per-file Delete in List PO | US2 | T138 | Wire Delete icon in List PO detail table with confirm dialog and refetch | Done
630 | 004-eutr-documents | EUTR Documents Management | Phase 16: Update 10 - View icon opens real file + per-file Delete in List PO | US5 | T139 | Review new UI text is in English (tooltips, dialog labels) | Done
631 | 004-eutr-documents | EUTR Documents Management | Phase 16: Update 10 - View icon opens real file + per-file Delete in List PO | US5 | T140 | Manual test scenarios 6/6a for real file preview | To do
632 | 004-eutr-documents | EUTR Documents Management | Phase 16: Update 10 - View icon opens real file + per-file Delete in List PO | US2 | T141 | Manual test scenarios 9r/9s for View/Delete per file in List PO | To do
633 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T142 | Create EutrReferenceDetails domain entity | Done
634 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T143 | Create EutrConditionGroupRow projection DTO | Done
635 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T144 | Create ConditionGroupDto | Done
636 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T145 | Create IEutrReferenceDetailsRepository interface | Done
637 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T146 | Create EutrReferenceDetailsRepository implementation | Done
638 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T147 | Register IEutrReferenceDetailsRepository in DI | Done
639 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T148 | Fix DeleteByDocumentIdAsync SQL to cascade-delete eutr_reference_details first | Done
640 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T149 | Create EutrManualMultiUploadFileRequest DTO (Files only) | Done
641 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T150 | Add UploadManualMultipleToSharePointAndSaveDataAsync to IEutrUploadService | Done
642 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T151 | Implement manual upload to fixed UploadManual folder without prefix/references | Done
643 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T152 | Add eutr-upload-manual-multi action to SharepointController | Done
644 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T153 | Add GetUnassignedDocumentsPagedAsync to IEutrReferencesRepository | Done
645 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T154 | Implement unassigned documents paging query (NOT EXISTS eutr_references) | Done
646 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T155 | Add GetUnassignedPagedAsync to IEutrDocumentsService | Done
647 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T156 | Implement GetUnassignedPagedAsync mapping to response DTOs | Done
648 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T157 | Add Conditions field (List<ConditionGroupDto>) to EutrDocumentsResponseDto | Done
649 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T158 | Extend step/condition attach method to compute grouped Conditions | Done
650 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T159 | Create EutrConditionRowDto (ConditionType, Values) | Done
651 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T160 | Create EutrAssignConditionsRequestDto | Done
652 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T161 | Create EutrAssignConditionsRequestDtoValidator | Done
653 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T162 | Create IEutrConditionAssignmentService interface | Done
654 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T163 | Implement EutrConditionAssignmentService.AssignConditionsAsync | Done
655 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T164 | Register condition assignment service and validator in DI | Done
656 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T165 | Add get-unassigned and assign-conditions actions to controller | Done
657 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T166 | Add CONDITION_TYPE_OPTIONS constant (PO/Vendor) | Done
658 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T167 | Declare uploadEutrManualFilesMulti in ISharePointRepository | Done
659 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T168 | Implement uploadEutrManualFilesMulti in RestSharePointRepository | Done
660 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T169 | Add executeManualMulti to UploadToSharePointUseCase | Done
661 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T170 | Declare getUnassigned/assignConditions in IEutrDocumentsRepository | Done
662 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T171 | Add getUnassigned/assignConditions functions to eutrDocumentsApi.js | Done
663 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T172 | Implement getUnassigned/assignConditions in RestEutrDocumentsRepository | Done
664 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T173 | Create GetEutrDocumentsUnassignedUseCase | Done
665 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T174 | Create AssignEutrConditionsUseCase | Done
666 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T175 | Create AssignConditionDialog.jsx create mode (Step + Conditions rows) | Done
667 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T176 | Render Conditions column with grouped condition-type labels | Done
668 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T177 | Wire Screen2 to real Upload File and unassigned documents list | Done
669 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T178 | Render unassigned files table with checkboxes and Assign condition button | Done
670 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T179 | Review new UI text is in English | Done
671 | 004-eutr-documents | EUTR Documents Management | Phase 17: Update 11 - Screen2 real upload + Assign condition popup (User Story 6) | US6 | T180 | Manual test scenarios 10/10a/11/11a/11b | To do
672 | 004-eutr-documents | EUTR Documents Management | Phase 18: Update 12 - Edit branches by Type (User Story 3) | US3 | T181 | Create EutrUpdateConditionAssignmentRequestDto | Done
673 | 004-eutr-documents | EUTR Documents Management | Phase 18: Update 12 - Edit branches by Type (User Story 3) | US3 | T182 | Create EutrUpdatePoStepRequestDto | Done
674 | 004-eutr-documents | EUTR Documents Management | Phase 18: Update 12 - Edit branches by Type (User Story 3) | US3 | T183 | Create EutrDocumentConditionAssignmentDto | Done
675 | 004-eutr-documents | EUTR Documents Management | Phase 18: Update 12 - Edit branches by Type (User Story 3) | US3 | T184 | Create EutrUpdateConditionAssignmentRequestDtoValidator | Done
676 | 004-eutr-documents | EUTR Documents Management | Phase 18: Update 12 - Edit branches by Type (User Story 3) | US3 | T185 | Extend IEutrConditionAssignmentService with get/update Step and Conditions methods | Done
677 | 004-eutr-documents | EUTR Documents Management | Phase 18: Update 12 - Edit branches by Type (User Story 3) | US3 | T186 | Implement GetConditionAssignmentAsync/UpdateConditionAssignmentAsync/UpdatePoStepAsync | Done
678 | 004-eutr-documents | EUTR Documents Management | Phase 18: Update 12 - Edit branches by Type (User Story 3) | US3 | T187 | Add GET/PUT condition-assignment and PUT step actions to controller | Done
679 | 004-eutr-documents | EUTR Documents Management | Phase 18: Update 12 - Edit branches by Type (User Story 3) | US3 | T188 | Register update-condition-assignment validator in DI | Done
680 | 004-eutr-documents | EUTR Documents Management | Phase 18: Update 12 - Edit branches by Type (User Story 3) | US3 | T189 | Declare getConditionAssignment/updateConditionAssignment/updatePoStep in repository interface | Done
681 | 004-eutr-documents | EUTR Documents Management | Phase 18: Update 12 - Edit branches by Type (User Story 3) | US3 | T190 | Add corresponding API functions to eutrDocumentsApi.js | Done
682 | 004-eutr-documents | EUTR Documents Management | Phase 18: Update 12 - Edit branches by Type (User Story 3) | US3 | T191 | Implement the 3 new methods in RestEutrDocumentsRepository | Done
683 | 004-eutr-documents | EUTR Documents Management | Phase 18: Update 12 - Edit branches by Type (User Story 3) | US3 | T192 | Create GetEutrDocumentConditionAssignmentUseCase | Done
684 | 004-eutr-documents | EUTR Documents Management | Phase 18: Update 12 - Edit branches by Type (User Story 3) | US3 | T193 | Create UpdateEutrConditionAssignmentUseCase | Done
685 | 004-eutr-documents | EUTR Documents Management | Phase 18: Update 12 - Edit branches by Type (User Story 3) | US3 | T194 | Create UpdateEutrDocumentPoStepUseCase | Done
686 | 004-eutr-documents | EUTR Documents Management | Phase 18: Update 12 - Edit branches by Type (User Story 3) | US3 | T195 | Extend AssignConditionDialog.jsx with edit mode | Done
687 | 004-eutr-documents | EUTR Documents Management | Phase 18: Update 12 - Edit branches by Type (User Story 3) | US3 | T196 | Add Step field to EutrDocumentsModal.jsx for PO type | Done
688 | 004-eutr-documents | EUTR Documents Management | Phase 18: Update 12 - Edit branches by Type (User Story 3) | US3 | T197 | Wire Edit to branch by refType (PO modal vs Assign condition dialog) | Done
689 | 004-eutr-documents | EUTR Documents Management | Phase 18: Update 12 - Edit branches by Type (User Story 3) | US3 | T198 | Review new UI text is in English | Done
690 | 004-eutr-documents | EUTR Documents Management | Phase 18: Update 12 - Edit branches by Type (User Story 3) | US3 | T199 | Manual test scenarios 12/13 | To do
691 | 004-eutr-documents | EUTR Documents Management | Phase 19: Update 13 - Clarify: deterministic Step + duplicate Conditions type guard | US3 | T200 | Add ReferenceId field to EutrReferenceStepInfo | Done
692 | 004-eutr-documents | EUTR Documents Management | Phase 19: Update 13 - Clarify: deterministic Step + duplicate Conditions type guard | US3 | T201 | Add r.Id AS ReferenceId to the step-info SELECT query | Done
693 | 004-eutr-documents | EUTR Documents Management | Phase 19: Update 13 - Clarify: deterministic Step + duplicate Conditions type guard | US3 | T202 | Add StepId field to EutrDocumentsResponseDto | Done
694 | 004-eutr-documents | EUTR Documents Management | Phase 19: Update 13 - Clarify: deterministic Step + duplicate Conditions type guard | US3 | T203 | Assign StepId based on the smallest ReferenceId per document group | Done
695 | 004-eutr-documents | EUTR Documents Management | Phase 19: Update 13 - Clarify: deterministic Step + duplicate Conditions type guard | US3 | T204 | Add duplicate Conditions-type validation rule to Assign validator | Done
696 | 004-eutr-documents | EUTR Documents Management | Phase 19: Update 13 - Clarify: deterministic Step + duplicate Conditions type guard | US3 | T205 | Add the same duplicate-type rule to Update validator | Done
697 | 004-eutr-documents | EUTR Documents Management | Phase 19: Update 13 - Clarify: deterministic Step + duplicate Conditions type guard | US3 | T206 | Disable already-used Conditions-type options in the dropdown | Done
698 | 004-eutr-documents | EUTR Documents Management | Phase 19: Update 13 - Clarify: deterministic Step + duplicate Conditions type guard | US3 | T207 | Review new error text is in English | Done
699 | 004-eutr-documents | EUTR Documents Management | Phase 19: Update 13 - Clarify: deterministic Step + duplicate Conditions type guard | US3 | T208 | Manual test scenarios 11b/12 | To do
700 | 004-eutr-documents | EUTR Documents Management | Phase 20: Update 14 - Type column uses real eutr_reference_types label | US1 | T209 | Create migration seeding eutr_reference_types Id=0 'PO'/Id=1 'Upload manual' | Done
701 | 004-eutr-documents | EUTR Documents Management | Phase 20: Update 14 - Type column uses real eutr_reference_types label | US1 | T210 | Add TypeName field to EutrReferenceStepInfo | Done
702 | 004-eutr-documents | EUTR Documents Management | Phase 20: Update 14 - Type column uses real eutr_reference_types label | US1 | T211 | Add LEFT JOIN eutr_reference_types and TypeName to SELECT | Done
703 | 004-eutr-documents | EUTR Documents Management | Phase 20: Update 14 - Type column uses real eutr_reference_types label | US1 | T212 | Add TypeName field to EutrDocumentsResponseDto | Done
704 | 004-eutr-documents | EUTR Documents Management | Phase 20: Update 14 - Type column uses real eutr_reference_types label | US1 | T213 | Assign TypeName in the step/condition attach method | Done
705 | 004-eutr-documents | EUTR Documents Management | Phase 20: Update 14 - Type column uses real eutr_reference_types label | US1 | T214 | Update Type column to use row.typeName instead of a front-end constant | Done
706 | 004-eutr-documents | EUTR Documents Management | Phase 20: Update 14 - Type column uses real eutr_reference_types label | US1 | T215 | Manual test scenario 14 for real Type label | To do
707 | 004-eutr-documents | EUTR Documents Management | Phase 21: Unified Add popup (Type/Step/Value/Upload) (User Story 7) | US7 | T216 | Create EutrTypeMultiUploadFileRequest DTO | Done
708 | 004-eutr-documents | EUTR Documents Management | Phase 21: Unified Add popup (Type/Step/Value/Upload) (User Story 7) | US7 | T217 | Add UploadMultipleForReferenceTypeAsync to IEutrUploadService | Done
709 | 004-eutr-documents | EUTR Documents Management | Phase 21: Unified Add popup (Type/Step/Value/Upload) (User Story 7) | US7 | T218 | Implement upload-by-type with dynamic folder resolution and reference writes | Done
710 | 004-eutr-documents | EUTR Documents Management | Phase 21: Unified Add popup (Type/Step/Value/Upload) (User Story 7) | US7 | T219 | Add eutr-upload-multi-by-type action to SharepointController | Done
711 | 004-eutr-documents | EUTR Documents Management | Phase 21: Unified Add popup (Type/Step/Value/Upload) (User Story 7) | US7 | T220 | Declare uploadEutrFilesMultiByType in ISharePointRepository | Done
712 | 004-eutr-documents | EUTR Documents Management | Phase 21: Unified Add popup (Type/Step/Value/Upload) (User Story 7) | US7 | T221 | Implement uploadEutrFilesMultiByType in RestSharePointRepository | Done
713 | 004-eutr-documents | EUTR Documents Management | Phase 21: Unified Add popup (Type/Step/Value/Upload) (User Story 7) | US7 | T222 | Add executeEutrMultiByType to UploadToSharePointUseCase | Done
714 | 004-eutr-documents | EUTR Documents Management | Phase 21: Unified Add popup (Type/Step/Value/Upload) (User Story 7) | US7 | T223 | Create EutrAddValueAutocomplete.jsx (Type-based suggestion/free-text/paste logic) | Done
715 | 004-eutr-documents | EUTR Documents Management | Phase 21: Unified Add popup (Type/Step/Value/Upload) (User Story 7) | US7 | T224 | Create EutrDocumentsAddDialog.jsx unified Type/Step/Value/Upload popup | Done
716 | 004-eutr-documents | EUTR Documents Management | Phase 21: Unified Add popup (Type/Step/Value/Upload) (User Story 7) | US7 | T225 | Wire toolbar Add button to open the new popup instead of navigating | Done
717 | 004-eutr-documents | EUTR Documents Management | Phase 21: Unified Add popup (Type/Step/Value/Upload) (User Story 7) | US7 | T226 | Manual test scenario 15 (+15a-15e) | To do
718 | 004-eutr-documents | EUTR Documents Management | Phase 22: Value auto-clear; PO hides manual Step selection (User Story 7) | US7 | T227 | Reset the Value input after each chip is added | Done
719 | 004-eutr-documents | EUTR Documents Management | Phase 22: Value auto-clear; PO hides manual Step selection (User Story 7) | US7 | T228 | Hide Step for PO type and call executeEutrMulti instead of executeEutrMultiByType | Done
720 | 004-eutr-documents | EUTR Documents Management | Phase 22: Value auto-clear; PO hides manual Step selection (User Story 7) | US7 | T229 | Manual test scenario 16 (+16a-16b) | To do
721 | 004-eutr-documents | EUTR Documents Management | Phase 23: Add popup sends TypeId for PO (User Story 7) | US7 | T230 | Add nullable TypeId field to EutrMultiUploadFileRequest | Done
722 | 004-eutr-documents | EUTR Documents Management | Phase 23: Add popup sends TypeId for PO (User Story 7) | US7 | T231 | Use request.TypeId as RefType when provided, else keep the old fallback constant | Done
723 | 004-eutr-documents | EUTR Documents Management | Phase 23: Add popup sends TypeId for PO (User Story 7) | US7 | T232 | Add typeId param to uploadEutrFilesMulti in RestSharePointRepository | Done
724 | 004-eutr-documents | EUTR Documents Management | Phase 23: Add popup sends TypeId for PO (User Story 7) | US7 | T233 | Add typeId param to executeEutrMulti in UploadToSharePointUseCase | Done
725 | 004-eutr-documents | EUTR Documents Management | Phase 23: Add popup sends TypeId for PO (User Story 7) | US7 | T234 | Pass type.id through the executeEutrMulti call for the PO branch | Done
726 | 004-eutr-documents | EUTR Documents Management | Phase 23: Add popup sends TypeId for PO (User Story 7) | US7 | T235 | Manual test scenario 17 (+17a) | To do
727 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US1 | T236 | Add RefValue field to EutrReferenceStepInfo | Done
728 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US1 | T237 | Add r.RefValue to the step-info SELECT query | Done
729 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US1 | T238 | Change Conditions field to List<string> in EutrDocumentsResponseDto | Done
730 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US1 | T239 | Compute Conditions as distinct flat RefValues, drop reference_details grouping | Done
731 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US3 | T240 | Add UpdateStepIdByDocumentIdAsync to IEutrReferencesRepository | Done
732 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US3 | T241 | Implement UpdateStepIdByDocumentIdAsync via raw SQL update | Done
733 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US3 | T242 | Rename EutrUpdatePoStepRequestDto to EutrUpdateReferenceStepRequestDto | Done
734 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US3 | T243 | Add UpdateReferenceStepAsync to IEutrDocumentsService | Done
735 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US3 | T244 | Implement UpdateReferenceStepAsync in EutrDocumentsService | Done
736 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US3 | T245 | Repurpose PUT {id}/step action; remove 4 obsolete condition-assignment actions (list-po-references kept) | Done
737 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US3 | T246 | Remove GetUnassignedPagedAsync from service (GetPoReferencesAsync kept) | Done
738 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US3 | T247 | Remove GetUnassignedDocumentsPagedAsync from repository (GetDocumentsByPoCodesAsync kept) | Done
739 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US3 | T248 | Delete IEutrConditionAssignmentService and EutrConditionAssignmentService | Done
740 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US3 | T249 | Delete EutrReferenceDetails entity and its repository | Done
741 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US3 | T250 | Delete Assign-condition DTOs and validators (7 files) | Done
742 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US3 | T251 | Keep List-PO DTOs instead of deleting (still used by eutr-sales-orders feature) | Done
743 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US3 | T252 | Remove eutr-upload-manual-multi action from SharepointController | Done
744 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US3 | T253 | Remove UploadManualMultipleToSharePointAndSaveDataAsync from EutrUploadService | Done
745 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) |  | T254 | Remove condition-assignment related DI registrations | Done
746 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US2 | T255 | Add ValidFrom/ValidTo fields to EutrMultiUploadFileRequest | Done
747 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US2 | T256 | Add ValidFrom/ValidTo fields to EutrTypeMultiUploadFileRequest | Done
748 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US2 | T257 | Use request.ValidFrom/ValidTo instead of hardcoded defaults in upload service | Done
749 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US1 | T258 | Update Conditions column to render flat MultiValueChips | Done
750 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US2 | T259 | Rename EutrDocumentsAddDialog.jsx to EutrDocumentsFormDialog.jsx with a mode prop | Done
751 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US2 | T260 | Add Valid from/Valid to date fields with validation to the form dialog | Done
752 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US2 | T261 | Add validFrom/validTo params to RestSharePointRepository upload methods | Done
753 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US2 | T262 | Add validFrom/validTo params to UploadToSharePointUseCase methods | Done
754 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US2 | T263 | Remove uploadEutrManualFilesMulti declaration from ISharePointRepository | Done
755 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US2 | T264 | Pass validFrom/validTo values to upload calls on submit | Done
756 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US3 | T265 | Rename UpdateEutrDocumentPoStepUseCase to UpdateEutrDocumentReferenceStepUseCase | Done
757 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US3 | T266 | Extend form dialog for edit mode: locked Type, read-only chips, Step for all types | Done
758 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US3 | T267 | Remove refType branching in onEdit, always open the unified form dialog | Done
759 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US3 | T268 | Delete EutrDocumentsModal.jsx and AssignConditionDialog.jsx | Done
760 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US3 | T269 | Delete EutrDocumentsAdd.jsx and its route/menu entry | Done
761 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US3 | T270 | Remove obsolete condition-assignment methods from frontend repository (keep getPoReferences) | Done
762 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US3 | T271 | Delete unused use cases, keeping GetEutrDocumentsPoReferencesUseCase (still referenced elsewhere) | Done
763 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US3 | T272 | Confirm CONDITION_TYPE_OPTIONS is unused elsewhere and remove it | Done
764 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US1 | T273 | Manual test scenario 18h for flat Conditions column | To do
765 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US2 | T274 | Manual test scenarios 18a-18c for Valid from/to in Add popup | To do
766 | 004-eutr-documents | EUTR Documents Management | Phase 24: Merge Add/Edit into one popup; flatten Conditions; remove old Add page (User Story 1/2/3) | US3 | T275 | Manual test scenarios 18/18d-18g/18i for unified Edit popup | To do
767 | 004-eutr-documents | EUTR Documents Management | Phase 25: Step combobox filtered by Assign Steps of Type (User Story 2/3) | US2 | T276 | Import and instantiate GetByTypeIdEutrReferenceTypeDetailsUseCase in form dialog | Done
768 | 004-eutr-documents | EUTR Documents Management | Phase 25: Step combobox filtered by Assign Steps of Type (User Story 2/3) | US2 | T277 | Create loadFilteredSteps(typeId) helper function | Done
769 | 004-eutr-documents | EUTR Documents Management | Phase 25: Step combobox filtered by Assign Steps of Type (User Story 2/3) | US2 | T278 | Wire Add mode to filter Step by Type and default-select the first row | Done
770 | 004-eutr-documents | EUTR Documents Management | Phase 25: Step combobox filtered by Assign Steps of Type (User Story 2/3) | US3 | T279 | Wire Edit mode to filter Step by Type, preserving the current Step if removed | Done
771 | 004-eutr-documents | EUTR Documents Management | Phase 25: Step combobox filtered by Assign Steps of Type (User Story 2/3) | US2 | T280 | Manual test scenarios 19/19b for filtered Step in Add | To do
772 | 004-eutr-documents | EUTR Documents Management | Phase 25: Step combobox filtered by Assign Steps of Type (User Story 2/3) | US3 | T281 | Manual test scenario 19a for Edit preserving a removed Step | To do
773 | 004-eutr-documents | EUTR Documents Management | Phase 26: Search box for Type/Step name/Conditions (User Story 6) | US6 | T282 | Add GetMatchingDocumentIdsAsync to IEutrReferencesRepository | Done
774 | 004-eutr-documents | EUTR Documents Management | Phase 26: Search box for Type/Step name/Conditions (User Story 6) | US6 | T283 | Implement GetMatchingDocumentIdsAsync with 3 independent EXISTS conditions | Done
775 | 004-eutr-documents | EUTR Documents Management | Phase 26: Search box for Type/Step name/Conditions (User Story 6) | US6 | T284 | Extend GetPagedAsync to consume virtual TypeId/StepId/Conditions filters | Done
776 | 004-eutr-documents | EUTR Documents Management | Phase 26: Search box for Type/Step name/Conditions (User Story 6) | US6 | T285 | Create EutrDocumentsFilterBar.jsx (Type/Step name/Conditions/Search controls) | Done
777 | 004-eutr-documents | EUTR Documents Management | Phase 26: Search box for Type/Step name/Conditions (User Story 6) | US6 | T286 | Add defaultFilters parameter to useEutrDocumentsData hook | Done
778 | 004-eutr-documents | EUTR Documents Management | Phase 26: Search box for Type/Step name/Conditions (User Story 6) | US6 | T287 | Wire search state/handleSearch and render the filter bar in index.jsx | Done
779 | 004-eutr-documents | EUTR Documents Management | Phase 26: Search box for Type/Step name/Conditions (User Story 6) | US6 | T288 | Manual test scenarios 20/20a/20b for the search box | To do
780 | 004-eutr-documents | EUTR Documents Management | Phase 27: Edit allows add/remove chips for non-PO Types (User Story 3) | US3 | T289 | Add RefValues field to EutrUpdateReferenceStepRequestDto | Done
781 | 004-eutr-documents | EUTR Documents Management | Phase 27: Edit allows add/remove chips for non-PO Types (User Story 3) | US3 | T290 | Add DeleteByDocumentIdAndRefValuesAsync/AddReferencesAsync to repository interface | Done
782 | 004-eutr-documents | EUTR Documents Management | Phase 27: Edit allows add/remove chips for non-PO Types (User Story 3) | US3 | T291 | Implement both new repository methods | Done
783 | 004-eutr-documents | EUTR Documents Management | Phase 27: Edit allows add/remove chips for non-PO Types (User Story 3) | US3 | T292 | Extend UpdateReferenceStepAsync with chip diff reconciliation logic | Done
784 | 004-eutr-documents | EUTR Documents Management | Phase 27: Edit allows add/remove chips for non-PO Types (User Story 3) | US3 | T293 | Pass dto.RefValues through in the UpdateReferenceStep controller action | Done
785 | 004-eutr-documents | EUTR Documents Management | Phase 27: Edit allows add/remove chips for non-PO Types (User Story 3) | US3 | T294 | Add refValues param to updateReferenceStep API client function | Done
786 | 004-eutr-documents | EUTR Documents Management | Phase 27: Edit allows add/remove chips for non-PO Types (User Story 3) | US3 | T295 | Add refValues param to repository interface declaration | Done
787 | 004-eutr-documents | EUTR Documents Management | Phase 27: Edit allows add/remove chips for non-PO Types (User Story 3) | US3 | T296 | Pass refValues through RestEutrDocumentsRepository | Done
788 | 004-eutr-documents | EUTR Documents Management | Phase 27: Edit allows add/remove chips for non-PO Types (User Story 3) | US3 | T297 | Pass refValues through UpdateEutrDocumentReferenceStepUseCase | Done
789 | 004-eutr-documents | EUTR Documents Management | Phase 27: Edit allows add/remove chips for non-PO Types (User Story 3) | US3 | T298 | Enable editable chips for non-PO types in Edit mode with Save wiring | Done
790 | 004-eutr-documents | EUTR Documents Management | Phase 27: Edit allows add/remove chips for non-PO Types (User Story 3) | US3 | T299 | Manual test scenarios 21/21a-21d for editable chips in Edit | To do
791 | 004-eutr-documents | EUTR Documents Management | Phase 28: Invoice number field for Type=Invoice (User Story 2/3) |  | T300 | Create migration adding Invoice column to eutr_documents | Done
792 | 004-eutr-documents | EUTR Documents Management | Phase 28: Invoice number field for Type=Invoice (User Story 2/3) |  | T301 | Sync Invoice column into eutr_db.sql design docs | Done
793 | 004-eutr-documents | EUTR Documents Management | Phase 28: Invoice number field for Type=Invoice (User Story 2/3) |  | T302 | Add Invoice field to EutrDocuments entity | Done
794 | 004-eutr-documents | EUTR Documents Management | Phase 28: Invoice number field for Type=Invoice (User Story 2/3) |  | T303 | Add Invoice field to EutrDocumentsRequestDto | Done
795 | 004-eutr-documents | EUTR Documents Management | Phase 28: Invoice number field for Type=Invoice (User Story 2/3) |  | T304 | Add Invoice field to EutrTypeMultiUploadFileRequest | Done
796 | 004-eutr-documents | EUTR Documents Management | Phase 28: Invoice number field for Type=Invoice (User Story 2/3) |  | T305 | Assign Invoice value when creating a document in the upload-by-type service | Done
797 | 004-eutr-documents | EUTR Documents Management | Phase 28: Invoice number field for Type=Invoice (User Story 2/3) |  | T306 | Add invoice param to ISharePointRepository uploadEutrFilesMultiByType signature | Done
798 | 004-eutr-documents | EUTR Documents Management | Phase 28: Invoice number field for Type=Invoice (User Story 2/3) |  | T307 | Add invoice param to RestSharePointRepository implementation | Done
799 | 004-eutr-documents | EUTR Documents Management | Phase 28: Invoice number field for Type=Invoice (User Story 2/3) |  | T308 | Add invoice param to UploadToSharePointUseCase.executeEutrMultiByType | Done
800 | 004-eutr-documents | EUTR Documents Management | Phase 28: Invoice number field for Type=Invoice (User Story 2/3) |  | T309 | Add required Invoice number field to form dialog for Type=Invoice (both modes) | Done
801 | 004-eutr-documents | EUTR Documents Management | Phase 28: Invoice number field for Type=Invoice (User Story 2/3) |  | T310 | Manual test scenario 22 (22a-22d) for Invoice number field | Done
802 | 004-eutr-documents | EUTR Documents Management | Phase 29: Invoice column on list screen (User Story 1) |  | T311 | Add Invoice column to the grid, positioned right after Step name | Done
803 | 004-eutr-documents | EUTR Documents Management | Phase 29: Invoice column on list screen (User Story 1) |  | T312 | Manual test scenario 23 for Invoice column display | Done
804 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 1: Setup |  | T001 | Confirm compliance-sys-api (with valid D365 connection) and compliance-client both run locally. | Done
805 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 2: Foundational |  | T002 | Add nullable CustAccount and DeliveryDate properties to the relevant entity/DTO. | Done
806 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 2: Foundational |  | T003 | Add the corresponding mapping entry for the new CustAccount/DeliveryDate fields. | Done
807 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 2: Foundational |  | T004 | Add a case 11 branch to MapDynamicsResponse for the reftype=11 source. | Done
808 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 2: Foundational |  | T005 | Manually verify POST /api/dynamics/reference for refType=11 returns real data. | To do
809 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 3: User Story 1 | US1 | T006 | Replace the mock sales order fetch with a real reftype=11 API call. | Done
810 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 3: User Story 1 | US1 | T007 | Map each fetched item to the grid row shape per data-model.md. | Done
811 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 3: User Story 1 | US1 | T008 | Render a blank placeholder in Delivery Date cell when the value is missing. | Done
812 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 3: User Story 1 | US1 | T009 | Replace the Template/Progress cell logic that used static EUTR_TEMPLATES lookups. | Done
813 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 3: User Story 1 | US1 | T010 | Add loading and error UI states around the sales order fetch. | Done
814 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 3: User Story 1 | US1 | T011 | Confirm the existing empty-state row displays correctly for no results. | Done
815 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 4: User Story 2 | US2 | T012 | Implement search filtering of the list by Sales ID or Customer. | Done
816 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 4: User Story 2 | US2 | T013 | Ensure clearing the search box re-fetches the default unfiltered list. | Done
817 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 4: User Story 2 | US2 | T014 | Confirm/implement the No Data empty state when search has no matches. | Done
818 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 5: User Story 3 | US3 | T015 | Implement pagination controls for the sales order list. | Done
819 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 5: User Story 3 | US3 | T016 | Wire the page-change handler to re-invoke the data fetch. | Done
820 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 6: Polish & Cross-Cutting Concerns |  | T017 | Run the backend manual verification steps from quickstart.md. | To do
821 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 6: Polish & Cross-Cutting Concerns |  | T018 | Run the frontend manual verification steps from quickstart.md. | To do
822 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 6: Polish & Cross-Cutting Concerns |  | T019 | Confirm build/lint is clean for the changed files. | Done
823 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 6: Polish & Cross-Cutting Concerns |  | T020 | Review new/changed lines for quality before sign-off. | Done
824 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 7: Backend — EutrPurchaseAttachments Entity/Repo/Service/Controller |  | T021 | Create the EutrPurchaseAttachments entity. | Done
825 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 7: Backend — EutrPurchaseAttachments Entity/Repo/Service/Controller |  | T022 | Create the SalesOrderTemplateDto. | Done
826 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 7: Backend — EutrPurchaseAttachments Entity/Repo/Service/Controller |  | T023 | Create the IEutrPurchaseAttachmentsRepository interface. | Done
827 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 7: Backend — EutrPurchaseAttachments Entity/Repo/Service/Controller |  | T024 | Implement EutrPurchaseAttachmentsRepository. | Done
828 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 7: Backend — EutrPurchaseAttachments Entity/Repo/Service/Controller |  | T025 | Create the IEutrPurchaseAttachmentsService interface. | Done
829 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 7: Backend — EutrPurchaseAttachments Entity/Repo/Service/Controller |  | T026 | Implement EutrPurchaseAttachmentsService. | Done
830 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 7: Backend — EutrPurchaseAttachments Entity/Repo/Service/Controller |  | T027 | Register the service in DI. | Done
831 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 7: Backend — EutrPurchaseAttachments Entity/Repo/Service/Controller |  | T028 | Register the repository in DI. | Done
832 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 7: Backend — EutrPurchaseAttachments Entity/Repo/Service/Controller |  | T029 | Create the EutrPurchaseAttachmentsController. | Done
833 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 7: Backend — EutrPurchaseAttachments Entity/Repo/Service/Controller |  | T030 | Manually verify the new endpoint per quickstart.md backend steps 4-7. | To do
834 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 8: Frontend — Purchase Attachments Read Path |  | T031 | Create the IEutrPurchaseAttachmentsRepository.js interface. | Done
835 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 8: Frontend — Purchase Attachments Read Path |  | T032 | Create the eutrPurchaseAttachmentsApi.js axios wrapper. | Done
836 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 8: Frontend — Purchase Attachments Read Path |  | T033 | Create RestEutrPurchaseAttachmentsRepository.js. | Done
837 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 8: Frontend — Purchase Attachments Read Path |  | T034 | Create a use case for reading purchase attachments. | Done
838 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 8: Frontend — Purchase Attachments Read Path |  | T035 | Register the repository in the frontend DI container. | Done
839 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 9: User Story 1 (continued) — Template Column | US1 | T036 | Fetch purchase attachments for the sales IDs on the current page. | Done
840 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 9: User Story 1 (continued) — Template Column | US1 | T037 | After the reftype=11 fetch resolves, fetch attachments for the current page's sales IDs. | Done
841 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 9: User Story 1 (continued) — Template Column | US1 | T038 | Derive a salesId-to-templates map grouped from the fetched attachments. | Done
842 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 9: User Story 1 (continued) — Template Column | US1 | T039 | Render the Template cell as one chip per template from that map. | Done
843 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 9: User Story 1 (continued) — Template Column | US1 | T040 | Ensure the template fetch re-runs whenever page/search dependencies change. | Done
844 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 10: Polish & Validation (Template Column) |  | T041 | Run backend verification steps 4-7 from quickstart.md. | To do
845 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 10: Polish & Validation (Template Column) |  | T042 | Run frontend verification steps 3-5 from quickstart.md. | To do
846 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 10: Polish & Validation (Template Column) |  | T043 | Review all new backend files from Phase 7. | Done
847 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 10: Polish & Validation (Template Column) |  | T044 | Confirm Map File and View pages still load without errors. | Done
848 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 10: Polish & Validation (Template Column) |  | T045 | Note the new EutrPurchaseAttachments.Read permission as an ops follow-up. | Done
849 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 11: Backend — New Read/Write Actions |  | T046 | Create the PurchaseAttachmentDto. | Done
850 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 11: Backend — New Read/Write Actions |  | T047 | Create the PurchaseAttachmentItemDto. | Done
851 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 11: Backend — New Read/Write Actions |  | T048 | Create the SavePoMappingRequestDto. | Done
852 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 11: Backend — New Read/Write Actions |  | T049 | Add a GetBySalesIdAsync method to the repository interface. | Done
853 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 11: Backend — New Read/Write Actions |  | T050 | Add a DeleteBySalesIdAsync method to the repository interface. | Done
854 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 11: Backend — New Read/Write Actions |  | T051 | Implement GetBySalesIdAsync in the repository. | Done
855 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 11: Backend — New Read/Write Actions |  | T052 | Implement DeleteBySalesIdAsync in the repository. | Done
856 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 11: Backend — New Read/Write Actions |  | T053 | Add the same two methods to the service interface. | Done
857 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 11: Backend — New Read/Write Actions |  | T054 | Implement both new methods in the service. | Done
858 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 11: Backend — New Read/Write Actions |  | T055 | Add two new controller actions for read/save-PO-mapping. | Done
859 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 11: Backend — New Read/Write Actions |  | T056 | Manually verify per quickstart.md Update 2 backend steps 1-7. | To do
860 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 12: Frontend — Extend Purchase Attachments Layer |  | T057 | Add getBySalesId/savePoMapping stubs to the repository interface. | Done
861 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 12: Frontend — Extend Purchase Attachments Layer |  | T058 | Add getBySalesId/savePoMapping calls to the API wrapper. | Done
862 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 12: Frontend — Extend Purchase Attachments Layer |  | T059 | Implement both new methods in the Rest repository. | Done
863 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 12: Frontend — Extend Purchase Attachments Layer |  | T060 | Create a GetBySalesId use case. | Done
864 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 12: Frontend — Extend Purchase Attachments Layer |  | T061 | Create a SavePoMapping use case. | Done
865 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 13: User Story 4 — Map File | US4 | T062 | Replace the mock Sales Order lookup in Map File with a real reftype=11 fetch. | Done
866 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 13: User Story 4 — Map File | US4 | T063 | Update the header card to show real Sales ID/Customer/Customer name. | Done
867 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 13: User Story 4 — Map File | US4 | T064 | Replace mocked Step 1 PO list with a real D365 PO fetch (reftype=16). | Done
868 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 13: User Story 4 — Map File | US4 | T065 | Update Step 1 PO table columns from mock fields to PO/Name/Order account/Qty. | Done
869 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 13: User Story 4 — Map File | US4 | T066 | On mount, fetch saved purchase attachments to pre-tick previously saved POs. | Done
870 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 13: User Story 4 — Map File | US4 | T067 | Replace handleSavePOMapping to call the real save-PO-mapping API. | Done
871 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 13: User Story 4 — Map File | US4 | T068 | Disable/omit PO rows lacking a valid template from selection. | Done
872 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 13: User Story 4 — Map File | US4 | T069 | Rebuild the Step 2 template tree memo from real template details. | Done
873 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 13: User Story 4 — Map File | US4 | T070 | Update Step 2 tree rendering to loop over the real template array. | Done
874 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 13: User Story 4 — Map File | US4 | T071 | Render a clear empty state in Step 2 when there is no template tree. | Done
875 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 13: User Story 4 — Map File | US4 | T072 | Replace the mocked AVAILABLE FILES list with a real documents fetch. | Done
876 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 13: User Story 4 — Map File | US4 | T073 | Update the tree's already-mapped detection to match real StepId values. | Done
877 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 13: User Story 4 — Map File | US4 | T074 | Render a clear empty state in AVAILABLE FILES for a PO with no documents. | Done
878 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 13: User Story 4 — Map File | US4 | T075 | Remove now-unused mock data imports. | Done
879 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 13: User Story 4 — Map File | US4 | T076 | Confirm the Step 2 Upload button/footer remain demo/no-op at this stage. | Done
880 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 14: Polish (Update 2) |  | T077 | Run the backend verification steps from quickstart.md. | To do
881 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 14: Polish (Update 2) |  | T078 | Run the frontend manual verification steps from quickstart.md. | To do
882 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 14: Polish (Update 2) |  | T079 | Review all new/changed backend code from Phase 11. | Done
883 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 14: Polish (Update 2) |  | T080 | Confirm ViewSalesOrderPage.jsx still loads without errors. | Done
884 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 14: Polish (Update 2) |  | T081 | Note the new EutrPurchaseAttachments.Update permission as an ops follow-up. | Done
885 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 15: User Story 4 (continued) — Select-More-POs, Back Button | US4 | T082 | Confirm not-yet-saved PO rows remain selectable (checkbox enabled). | Done
886 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 15: User Story 4 (continued) — Select-More-POs, Back Button | US4 | T083 | Confirm handleSavePOMapping's items array includes newly ticked POs alongside existing ones. | Done
887 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 15: User Story 4 (continued) — Select-More-POs, Back Button | US4 | T084 | Wire the Back button to navigate to /eutr/sales-orders. | Done
888 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 16: Polish (Update 3) |  | T085 | Run the frontend manual verification steps from quickstart.md. | To do
889 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 16: Polish (Update 3) |  | T086 | Confirm git diff/status for this update touches only expected files. | Done
890 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 16: Polish (Update 3) |  | T087 | Review any fix uncovered by T082/T083 for correctness. | Done
891 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 17: User Story 5 — View Sales Order | US5 | T088 | Replace the mock Sales Order lookup in View with a real reftype=11 fetch. | Done
892 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 17: User Story 5 — View Sales Order | US5 | T089 | Update the header with real Sales ID/Customer/Customer name. | Done
893 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 17: User Story 5 — View Sales Order | US5 | T090 | Replace mocked PO mapping with real saved purchase attachments. | Done
894 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 17: User Story 5 — View Sales Order | US5 | T091 | Update the Selected Purchase Orders table columns to real PO fields. | Done
895 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 17: User Story 5 — View Sales Order | US5 | T092 | Rebuild the tree/details memos from real template data. | Done
896 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 17: User Story 5 — View Sales Order | US5 | T093 | Render a clear empty state when there is no template tree yet. | Done
897 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 17: User Story 5 — View Sales Order | US5 | T094 | Replace mocked file mappings with a real documents lookup. | Done
898 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 17: User Story 5 — View Sales Order | US5 | T095 | Confirm the read-only tree-row component works correctly with real data. | Done
899 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 17: User Story 5 — View Sales Order | US5 | T096 | Update the Validation Summary calculation to use real data. | Done
900 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 17: User Story 5 — View Sales Order | US5 | T097 | Remove now-unused mock data imports. | Done
901 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 17: User Story 5 — View Sales Order | US5 | T098 | Confirm the Edit/Map File button still navigates correctly. | Done
902 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 17: User Story 5 — View Sales Order | US5 | T099 | Confirm the Download button remains demo/no-op at this stage. | Done
903 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 18: Cleanup — Delete Dead Mock Fixtures |  | T100 | Full-repo search for references to now-dead mock fixture files. | Done
904 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 18: Cleanup — Delete Dead Mock Fixtures |  | T101 | Delete the now-dead mock fixture files. | Done
905 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 19: Polish (Update 4) |  | T102 | Run the frontend manual verification steps from quickstart.md. | To do
906 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 19: Polish (Update 4) |  | T103 | Review all new/changed lines from this update. | Done
907 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 19: Polish (Update 4) |  | T104 | Confirm Map File and Overview pages still load without errors. | Done
908 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 19: Polish (Update 4) |  | T105 | Confirm no new authorization policy is required for this change. | Done
909 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 20: Backend — Widen list-po-references Response |  | T106 | Add nullable StepId/RefType/TypeName fields to the response DTO. | Done
910 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 20: Backend — Widen list-po-references Response |  | T107 | Update GetDocumentsByPoCodesAsync's SQL to include the new fields. | Done
911 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 20: Backend — Widen list-po-references Response |  | T108 | Add StepIds/RefType/TypeName fields to another response DTO. | Done
912 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 20: Backend — Widen list-po-references Response |  | T109 | Update GetPoReferencesAsync's grouping to populate the new fields. | Done
913 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 20: Backend — Widen list-po-references Response |  | T110 | Manually verify per quickstart.md Update 5 backend steps 1-3. | To do
914 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 21: User Story 4 (continued) — Toolbar Reload, Dynamic Badges | US4 | T111 | Set up toolbar reload wiring for the template tree. | Done
915 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 21: User Story 4 (continued) — Toolbar Reload, Dynamic Badges | US4 | T112 | Add a reload action fetching the latest templatesData for all saved templates. | Done
916 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 21: User Story 4 (continued) — Toolbar Reload, Dynamic Badges | US4 | T113 | Incorporate the new StepId/RefType/TypeName fields into the available-files memo. | Done
917 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 21: User Story 4 (continued) — Toolbar Reload, Dynamic Badges | US4 | T114 | Replace the static Map status chip with a dynamic Mapped/No map value. | Done
918 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 21: User Story 4 (continued) — Toolbar Reload, Dynamic Badges | US4 | T115 | Replace the static File type chip with a dynamic value. | Done
919 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 21: User Story 4 (continued) — Toolbar Reload, Dynamic Badges | US4 | T116 | Replace the static PO value chip with a dynamic value. | Done
920 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 21: User Story 4 (continued) — Toolbar Reload, Dynamic Badges | US4 | T117 | Confirm the tree's own already-mapped indicator stays consistent. | Done
921 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 22: Polish (Update 5) |  | T118 | Run the backend verification steps from quickstart.md. | To do
922 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 22: Polish (Update 5) |  | T119 | Run the frontend manual verification steps from quickstart.md. | To do
923 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 22: Polish (Update 5) |  | T120 | Review new/changed lines in the affected DTO/service files. | Done
924 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 22: Polish (Update 5) |  | T121 | Confirm ViewSalesOrderPage.jsx's Template Checklist is unaffected. | Done
925 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 23: User Story 4 (continued) — Wire Upload/Edit to Documents Popup | US4 | T122 | Import the shared 004-eutr-documents Add/Edit dialog components. | Done
926 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 23: User Story 4 (continued) — Wire Upload/Edit to Documents Popup | US4 | T123 | Replace the local upload/edit dialog state with the shared dialog's state. | Done
927 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 23: User Story 4 (continued) — Wire Upload/Edit to Documents Popup | US4 | T124 | Extract the documents-loading effect body into a reusable refetch function. | Done
928 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 23: User Story 4 (continued) — Wire Upload/Edit to Documents Popup | US4 | T125 | Remove the local-only UploadDialog component and map dialog code. | Done
929 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 23: User Story 4 (continued) — Wire Upload/Edit to Documents Popup | US4 | T126 | Update the allFiles memo to reflect real documents after rewiring. | Done
930 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 23: User Story 4 (continued) — Wire Upload/Edit to Documents Popup | US4 | T127 | Wire the Upload button to open the real Add-document dialog. | Done
931 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 23: User Story 4 (continued) — Wire Upload/Edit to Documents Popup | US4 | T128 | Add a callback to load a document's data for editing. | Done
932 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 23: User Story 4 (continued) — Wire Upload/Edit to Documents Popup | US4 | T129 | Wire the Edit button to open the real Edit-document dialog. | Done
933 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 23: User Story 4 (continued) — Wire Upload/Edit to Documents Popup | US4 | T130 | Render the shared Add/Edit document dialog component. | Done
934 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 23: User Story 4 (continued) — Wire Upload/Edit to Documents Popup | US4 | T131 | Remove now-unused local SOURCES/SOURCE_COLORS/AUTO_SOURCES constants. | Done
935 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 24: Polish (Update 6) |  | T132 | Run the frontend manual verification steps from quickstart.md. | To do
936 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 24: Polish (Update 6) |  | T133 | Review new/changed lines in MapFilePage.jsx. | Done
937 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 24: Polish (Update 6) |  | T134 | Confirm git diff/status touches only expected files. | Done
938 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 24: Polish (Update 6) |  | T135 | Confirm View and Overview pages still load without errors. | Done
939 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 25: User Story 4 (continued) — Scope AVAILABLE FILES by PO<->Template | US4 | T136 | Add a purchIdToTemplateCode map for scoping documents to their owning template. | Done
940 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 25: User Story 4 (continued) — Scope AVAILABLE FILES by PO<->Template | US4 | T137 | Add a templateComputations memo computing each template's own status. | Done
941 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 25: User Story 4 (continued) — Scope AVAILABLE FILES by PO<->Template | US4 | T138 | Replace the global allFiles alias with a per-template scoped file list. | Done
942 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 25: User Story 4 (continued) — Scope AVAILABLE FILES by PO<->Template | US4 | T139 | Reset the file list's page to 1 whenever the selected template changes. | Done
943 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 25: User Story 4 (continued) — Scope AVAILABLE FILES by PO<->Template | US4 | T140 | Replace the global mapping computations with per-template scoped ones. | Done
944 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 25: User Story 4 (continued) — Scope AVAILABLE FILES by PO<->Template | US4 | T141 | Update the tree render call site to use the per-template scoped status. | Done
945 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 25: User Story 4 (continued) — Scope AVAILABLE FILES by PO<->Template | US4 | T142 | Replace the single aggregate progress computation with a per-template sum. | Done
946 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 25: User Story 4 (continued) — Scope AVAILABLE FILES by PO<->Template | US4 | T143 | Update the missingRequired count to use per-template PO/Template scoping. | Done
947 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 25: User Story 4 (continued) — Scope AVAILABLE FILES by PO<->Template | US4 | T144 | Replace the per-file mapped-by-step computation with a PO/Template-scoped version. | Done
948 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 25: User Story 4 (continued) — Scope AVAILABLE FILES by PO<->Template | US4 | T145 | Guardrail: confirm earlier Map-status chip and post-upload refresh logic still work. | Done
949 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 26: Polish (Update 7) |  | T146 | Run the frontend manual verification steps from quickstart.md. | To do
950 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 26: Polish (Update 7) |  | T147 | Review new/changed lines in MapFilePage.jsx from Phase 25. | Done
951 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 26: Polish (Update 7) |  | T148 | Confirm git diff/status touches only expected files. | Done
952 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 26: Polish (Update 7) |  | T149 | Confirm View and Overview pages still load without errors. | Done
953 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 27: User Story 5 (continued) — Template Tree Toolbar | US5 | T150 | Add real per-template toolbar chips to the View screen. | Done
954 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 27: User Story 5 (continued) — Template Tree Toolbar | US5 | T151 | Add a default-first-template effect cloned from Map File. | Done
955 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 27: User Story 5 (continued) — Template Tree Toolbar | US5 | T152 | Add a poCode field to the PO object literal used for scoping. | Done
956 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 27: User Story 5 (continued) — Template Tree Toolbar | US5 | T153 | Add a purchIdToTemplateCode memo. | Done
957 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 27: User Story 5 (continued) — Template Tree Toolbar | US5 | T154 | Add a templateComputations memo for per-template status. | Done
958 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 27: User Story 5 (continued) — Template Tree Toolbar | US5 | T155 | Replace the 3 hardcoded toolbar chips with real per-template chips. | Done
959 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 27: User Story 5 (continued) — Template Tree Toolbar | US5 | T156 | Change the Template Checklist to render only the selected template's tree. | Done
960 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 27: User Story 5 (continued) — Template Tree Toolbar | US5 | T157 | Replace the single-pass Validation Summary computation with a per-template scoped sum. | Done
961 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 27: User Story 5 (continued) — Template Tree Toolbar | US5 | T158 | Guardrail: confirm Edit/Map File, Download, and the PO table remain unaffected. | Done
962 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 28: Polish (Update 8) |  | T159 | Run the frontend manual verification steps from quickstart.md. | To do
963 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 28: Polish (Update 8) |  | T160 | Review new/changed lines in ViewSalesOrderPage.jsx from Phase 27. | Done
964 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 28: Polish (Update 8) |  | T161 | Confirm git diff/status touches only expected files. | Done
965 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 28: Polish (Update 8) |  | T162 | Confirm Map File and Overview pages still load without errors. | Done
966 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 29: User Story 4 (continued) — View Button on Files | US4 | T163 | Set up file preview viewer wiring in Map File. | Done
967 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 29: User Story 4 (continued) — View Button on Files | US4 | T164 | Add a viewerFile state near the existing dialog state. | Done
968 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 29: User Story 4 (continued) — View Button on Files | US4 | T165 | Add a new View icon button alongside Edit in the AVAILABLE FILES rows. | Done
969 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 29: User Story 4 (continued) — View Button on Files | US4 | T166 | Render the read-only file preview dialog component. | Done
970 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 29: User Story 4 (continued) — View Button on Files | US4 | T167 | Guardrail: confirm Edit/Upload/Map buttons still function correctly. | Done
971 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 30: Polish (Update 9) |  | T168 | Run the frontend manual verification steps from quickstart.md. | To do
972 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 30: Polish (Update 9) |  | T169 | Review new/changed lines in MapFilePage.jsx from Phase 29. | Done
973 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 30: Polish (Update 9) |  | T170 | Confirm git diff/status touches only expected files. | Done
974 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 30: Polish (Update 9) |  | T171 | Confirm View and Overview pages still load without errors. | Done
975 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 31: Backend — DownloadZip Action |  | T172 | Create the EutrDownloadZipFileDto. | Done
976 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 31: Backend — DownloadZip Action |  | T173 | Create the EutrDownloadZipFolderDto. | Done
977 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 31: Backend — DownloadZip Action |  | T174 | Create the EutrDownloadZipRequestDto. | Done
978 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 31: Backend — DownloadZip Action |  | T175 | Add scaffolding for the download-zip route on the documents controller. | Done
979 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 31: Backend — DownloadZip Action |  | T176 | Add a private helper for building the zip, cloned from an existing pattern. | Done
980 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 31: Backend — DownloadZip Action |  | T177 | Add the new DownloadZip controller action. | Done
981 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 31: Backend — DownloadZip Action |  | T178 | Manually verify the new endpoint per quickstart.md Update 10 backend steps 1-5. | To do
982 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 32: Frontend — Download Use Case |  | T179 | Add a downloadZip(payload) method stub to the repository interface. | Done
983 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 32: Frontend — Download Use Case |  | T180 | Add downloadZip to the documents API wrapper. | Done
984 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 32: Frontend — Download Use Case |  | T181 | Implement downloadZip(payload) in the Rest repository. | Done
985 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 32: Frontend — Download Use Case |  | T182 | Create the DownloadEutrSalesOrderZipUseCase. | Done
986 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 33: User Story 5 (continued) — Wire Download Button | US5 | T183 | Build the folder/file structure for the zip download in View. | Done
987 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 33: User Story 5 (continued) — Wire Download Button | US5 | T184 | Wire the Download button to call the use case and trigger the file download. | Done
988 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 33: User Story 5 (continued) — Wire Download Button | US5 | T185 | Guardrail: confirm other View features remain unaffected. | Done
989 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 34: Polish (Update 10) |  | T186 | Run the backend verification steps from quickstart.md. | To do
990 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 34: Polish (Update 10) |  | T187 | Run the frontend manual verification steps from quickstart.md. | To do
991 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 34: Polish (Update 10) |  | T188 | Review new/changed lines in the documents controller and DTOs. | Done
992 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 34: Polish (Update 10) |  | T189 | Confirm git diff/status touches only the 3 new DTO files and expected changes. | Done
993 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 34: Polish (Update 10) |  | T190 | Confirm Map File and Overview pages still load without errors. | Done
994 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 35: User Story 4 (continued) — Exclude AUTO_SOURCES from Progress | US4 | T191 | Edit computeProgress()'s Required-step filter to exclude AUTO_SOURCES. | Done
995 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 35: User Story 4 (continued) — Exclude AUTO_SOURCES from Progress | US4 | T192 | Guardrail: confirm no other call site is affected inconsistently by the change. | Done
996 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 36: Polish (Update 11) |  | T193 | Run the frontend manual verification steps from quickstart.md. | To do
997 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 36: Polish (Update 11) |  | T194 | Review the new comment added in T191 for clarity. | Done
998 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 36: Polish (Update 11) |  | T195 | Confirm git diff/status touches only the expected file. | Done
999 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 36: Polish (Update 11) |  | T196 | Confirm Overview and View pages still load without errors. | Done
1000 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 37: Backend — by-sales-ids-raw Endpoint |  | T197 | Add a GetBySalesIdsAsync method to the repository interface. | Done
1001 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 37: Backend — by-sales-ids-raw Endpoint |  | T198 | Add a GetRawBySalesIdsAsync method to the repository interface. | Done
1002 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 37: Backend — by-sales-ids-raw Endpoint |  | T199 | Implement GetBySalesIdsAsync. | Done
1003 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 37: Backend — by-sales-ids-raw Endpoint |  | T200 | Implement GetRawBySalesIdsAsync. | Done
1004 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 37: Backend — by-sales-ids-raw Endpoint |  | T201 | Add the new by-sales-ids-raw controller action. | Done
1005 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 38: Backend — by-codes Endpoint |  | T202 | Add a GetManyByCodesWithDetailsAsync method to the service interface. | Done
1006 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 38: Backend — by-codes Endpoint |  | T203 | Add the same method signature to the repository interface. | Done
1007 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 38: Backend — by-codes Endpoint |  | T204 | Implement GetManyByCodesWithDetailsAsync in the service. | Done
1008 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 38: Backend — by-codes Endpoint |  | T205 | Implement GetManyByCodesWithDetailsAsync in the repository. | Done
1009 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 38: Backend — by-codes Endpoint |  | T206 | Add the new by-codes endpoint to the templates controller. | Done
1010 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 38: Backend — by-codes Endpoint |  | T207 | Manually verify both new endpoints per quickstart.md Update 12 backend steps 1-3. | To do
1011 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 39: Frontend — Shared progressUtils.js |  | T208 | Create the shared progressUtils.js module. | Done
1012 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 39: Frontend — Shared progressUtils.js |  | T209 | Add buildTemplateComputations() to progressUtils.js. | Done
1013 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 39: Frontend — Shared progressUtils.js |  | T210 | Remove duplicated progress logic in Map File, use the shared util. | Done
1014 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 39: Frontend — Shared progressUtils.js |  | T211 | Remove duplicated progress logic in View, use the shared util. | Done
1015 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 39: Frontend — Shared progressUtils.js |  | T212 | Guardrail: re-run earlier progress/toolbar verification steps against both pages. | Done
1016 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 40: Frontend — Use Cases for Batch Endpoints |  | T213 | Add a getBySalesIdsRaw stub to the repository interface. | Done
1017 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 40: Frontend — Use Cases for Batch Endpoints |  | T214 | Add getBySalesIdsRaw to the API wrapper. | Done
1018 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 40: Frontend — Use Cases for Batch Endpoints |  | T215 | Implement getBySalesIdsRaw in the Rest repository. | Done
1019 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 40: Frontend — Use Cases for Batch Endpoints |  | T216 | Create a use case for getBySalesIdsRaw. | Done
1020 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 40: Frontend — Use Cases for Batch Endpoints |  | T217 | Add a getManyByCodes stub to the repository interface. | Done
1021 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 40: Frontend — Use Cases for Batch Endpoints |  | T218 | Add getManyByCodes to the API wrapper. | Done
1022 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 40: Frontend — Use Cases for Batch Endpoints |  | T219 | Implement getManyByCodes in the Rest repository. | Done
1023 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 40: Frontend — Use Cases for Batch Endpoints |  | T220 | Create a use case for getManyByCodes. | Done
1024 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 41: User Story 1 (continued) — Batched Progress Column | US1 | T221 | Set up batched progress fetching for the Overview grid. | Done
1025 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 41: User Story 1 (continued) — Batched Progress Column | US1 | T222 | Add a fetchProgressForRows callback running in parallel with the existing fetch. | Done
1026 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 41: User Story 1 (continued) — Batched Progress Column | US1 | T223 | Once all 3 batch calls resolve, compute each row's progress via the shared util. | Done
1027 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 41: User Story 1 (continued) — Batched Progress Column | US1 | T224 | Render the Progress cell from the computed per-row state. | Done
1028 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 41: User Story 1 (continued) — Batched Progress Column | US1 | T225 | Wire fetchProgressForRows to fire alongside the existing template fetch. | Done
1029 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 41: User Story 1 (continued) — Batched Progress Column | US1 | T226 | Mark affected rows with an error state if any of the batch calls rejects. | Done
1030 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 41: User Story 1 (continued) — Batched Progress Column | US1 | T227 | Guardrail: confirm other columns/behaviors remain unaffected. | Done
1031 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 42: Polish (Update 12) |  | T228 | Run the backend verification steps from quickstart.md. | To do
1032 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 42: Polish (Update 12) |  | T229 | Run the frontend manual verification steps from quickstart.md. | To do
1033 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 42: Polish (Update 12) |  | T230 | Review all new/changed lines across the affected files. | Done
1034 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 42: Polish (Update 12) |  | T231 | Confirm git diff/status touches only expected files. | Done
1035 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 42: Polish (Update 12) |  | T232 | Confirm Map File and View pages' own progress logic remains unaffected. | Done
1036 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 43: User Story 1 (continued) — Per-Row Download Button | US1 | T233 | Set up the per-row download handler in Overview. | Done
1037 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 43: User Story 1 (continued) — Per-Row Download Button | US1 | T234 | Add a handleDownload callback fetching the needed data for one row. | Done
1038 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 43: User Story 1 (continued) — Per-Row Download Button | US1 | T235 | Build this row's download folder structure once both calls resolve. | Done
1039 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 43: User Story 1 (continued) — Per-Row Download Button | US1 | T236 | Check whether every folder is empty and show a nothing-to-download message. | Done
1040 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 43: User Story 1 (continued) — Per-Row Download Button | US1 | T237 | Otherwise call DownloadEutrSalesOrderZipUseCase.execute(...). | Done
1041 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 43: User Story 1 (continued) — Per-Row Download Button | US1 | T238 | Wire the existing Download icon button to the new handler. | Done
1042 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 43: User Story 1 (continued) — Per-Row Download Button | US1 | T239 | Guardrail: confirm Download on one row doesn't block other rows/interactions. | Done
1043 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 44: Polish (Update 13) |  | T240 | Run the frontend manual verification steps from quickstart.md. | To do
1044 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 44: Polish (Update 13) |  | T241 | Review new/changed lines in SalesOrderOverviewPage.jsx. | Done
1045 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 44: Polish (Update 13) |  | T242 | Confirm git diff/status touches only expected files. | Done
1046 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 44: Polish (Update 13) |  | T243 | Confirm Download never writes to documents/references/attachments (read-only). | Done
1047 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 45: URL-Persisted Search/Page + Smart Back | US1 | T244 | Persist Overview's search/page state to URL query params. | Done
1048 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 45: URL-Persisted Search/Page + Smart Back | US1 | T245 | Update the URL inside the debounced search callback. | Done
1049 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 45: URL-Persisted Search/Page + Smart Back | US1 | T246 | Update the URL in the page-change/page-size-change handlers similarly. | Done
1050 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 45: URL-Persisted Search/Page + Smart Back | US1 | T247 | Pass a fromOverview navigation state flag when opening Map File/View. | Done
1051 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 45: URL-Persisted Search/Page + Smart Back | US4 | T248 | Make Map File's Back button restore Overview using the fromOverview state. | Done
1052 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 45: URL-Persisted Search/Page + Smart Back | US5 | T249 | Apply the same Back-button fix in View Sales Order. | Done
1053 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 45: URL-Persisted Search/Page + Smart Back | US1 | T250 | Guardrail: confirm restoring search/page from the URL on mount still works normally. | Done
1054 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 46: Polish (Update 14) |  | T251 | Run the frontend manual verification steps from quickstart.md. | To do
1055 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 46: Polish (Update 14) |  | T252 | Review new/changed lines in the 3 affected pages. | Done
1056 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 46: Polish (Update 14) |  | T253 | Confirm git diff/status touches only these 3 frontend files. | Done
1057 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 46: Polish (Update 14) |  | T254 | Confirm the Back button's fallback (deep link, no fromOverview flag) still works. | Done
1058 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 47: User Story 5 (continued) — AVAILABLE FILES Panel | US5 | T255 | Add an AVAILABLE FILES panel to the right sidebar of View. | Done
1059 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 47: User Story 5 (continued) — AVAILABLE FILES Panel | US5 | T256 | Shape the available-files data for the new panel. | Done
1060 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 47: User Story 5 (continued) — AVAILABLE FILES Panel | US5 | T257 | Add a selectedStepId state defaulting to no step filter. | Done
1061 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 47: User Story 5 (continued) — AVAILABLE FILES Panel | US5 | T258 | Add selection props to the tree-row component, threaded down from the page. | Done
1062 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 47: User Story 5 (continued) — AVAILABLE FILES Panel | US5 | T259 | Clear the step filter whenever the user switches templates in the toolbar. | Done
1063 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 47: User Story 5 (continued) — AVAILABLE FILES Panel | US5 | T260 | Add a memo filtering available files by the selected step when set. | Done
1064 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 47: User Story 5 (continued) — AVAILABLE FILES Panel | US5 | T261 | Render the new AVAILABLE FILES panel below the Steps Missing Files list. | Done
1065 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 47: User Story 5 (continued) — AVAILABLE FILES Panel | US5 | T262 | Render the file viewer dialog wired to the panel's View button. | Done
1066 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 48: Polish (Update 15) |  | T263 | Run the frontend manual verification steps from quickstart.md. | To do
1067 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 48: Polish (Update 15) |  | T264 | Review new/changed lines in ViewSalesOrderPage.jsx from Phase 47. | Done
1068 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 48: Polish (Update 15) |  | T265 | Confirm git diff/status touches only ViewSalesOrderPage.jsx. | Done
1069 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 48: Polish (Update 15) |  | T266 | Confirm the new panel has no Edit/Upload/write buttons (read-only). | Done
1070 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 49: Backend — sales-ids-with-template Endpoint |  | T267 | Add a GetSalesIdsWithTemplateAsync method to the service interface. | Done
1071 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 49: Backend — sales-ids-with-template Endpoint |  | T268 | Add the same method signature to the repository interface. | Done
1072 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 49: Backend — sales-ids-with-template Endpoint |  | T269 | Implement GetSalesIdsWithTemplateAsync in the service. | Done
1073 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 49: Backend — sales-ids-with-template Endpoint |  | T270 | Implement GetSalesIdsWithTemplateAsync in the repository. | Done
1074 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 49: Backend — sales-ids-with-template Endpoint |  | T271 | Add the new GET endpoint to the controller. | Done
1075 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 49: Backend — sales-ids-with-template Endpoint |  | T272 | Manually verify the new endpoint per quickstart.md Update 16 backend steps 1-2. | To do
1076 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 50: Frontend — Use Case for sales-ids-with-template |  | T273 | Add a getSalesIdsWithTemplate stub to the repository interface. | Done
1077 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 50: Frontend — Use Case for sales-ids-with-template |  | T274 | Add getSalesIdsWithTemplate to the API wrapper. | Done
1078 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 50: Frontend — Use Case for sales-ids-with-template |  | T275 | Implement getSalesIdsWithTemplate in the Rest repository. | Done
1079 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 50: Frontend — Use Case for sales-ids-with-template |  | T276 | Create a use case for getSalesIdsWithTemplate. | Done
1080 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 51: User Story 1 (continued) — Default Row Set Scoped to Template | US1 | T277 | Apply the sales-ids-with-template filter to Overview's default (empty-search) list. | To do
1081 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 51: User Story 1 (continued) — Default Row Set Scoped to Template | US1 | T278 | Add a fetchSalesIdsWithTemplate callback. | To do
1082 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 51: User Story 1 (continued) — Default Row Set Scoped to Template | US1 | T279 | Modify the reference-data fetch to apply the template filter only when search is empty. | To do
1083 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 51: User Story 1 (continued) — Default Row Set Scoped to Template | US1 | T280 | Confirm the clear-search handler re-triggers the sales-ids-with-template refetch. | To do
1084 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 51: User Story 1 (continued) — Default Row Set Scoped to Template | US1 | T281 | Guardrail: confirm the Back-navigation restore path branches correctly for empty vs non-empty search. | To do
1085 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 51: User Story 1 (continued) — Default Row Set Scoped to Template | US1 | T282 | Guardrail: confirm other columns remain unaffected by the new default filter. | To do
1086 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 52: Polish (Update 16) |  | T283 | Run the backend verification steps from quickstart.md. | To do
1087 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 52: Polish (Update 16) |  | T284 | Run the frontend manual verification steps from quickstart.md. | To do
1088 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 52: Polish (Update 16) |  | T285 | Review new/changed lines from this update. | Done
1089 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 52: Polish (Update 16) |  | T286 | Confirm the Dynamics service/controller/OData converter behave as expected. | Done
1090 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 53: Backend — Fix EntityMappings[20] Registration Gap |  | T287 | Register the missing EntityMappings[20] entry for reference type 20. | Done
1091 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 53: Backend — Fix EntityMappings[20] Registration Gap |  | T288 | Confirm (read-only) that response mapping/sort-column logic for type 20 is already correct. | Done
1092 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 53: Backend — Fix EntityMappings[20] Registration Gap |  | T289 | Manually verify per quickstart.md Update 17 backend steps 1-3. | To do
1093 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 54: Frontend — Variants/Materials on Step 1 | US4 | T290 | Add a fetch for reference type 20 data in Map File. | Done
1094 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 54: Frontend — Variants/Materials on Step 1 | US4 | T291 | Add a poLinesByPurchId map of materials/variants per PO. | Done
1095 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 54: Frontend — Variants/Materials on Step 1 | US4 | T292 | Add a new effect to batch-fetch type=20 data alongside the existing sales-ID-scoped fetch. | Done
1096 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 54: Frontend — Variants/Materials on Step 1 | US4 | T293 | Group the response into poLinesByPurchId inside the fetch handler. | Done
1097 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 54: Frontend — Variants/Materials on Step 1 | US4 | T294 | Replace the static Variants/Materials text with real per-PO values in the Step 1 table. | Done
1098 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 54: Frontend — Variants/Materials on Step 1 | US4 | T295 | Render a loading/failed-to-load indicator for the two new columns. | Done
1099 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 54: Frontend — Variants/Materials on Step 1 | US4 | T296 | Guardrail: confirm PO selection/save logic is unaffected by the new columns. | Done
1100 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 55: Polish (Update 17) |  | T297 | Run the backend verification steps from quickstart.md. | To do
1101 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 55: Polish (Update 17) |  | T298 | Run the frontend manual verification steps from quickstart.md. | To do
1102 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 55: Polish (Update 17) |  | T299 | Review new/changed lines in the Dynamics service and Map File page. | Done
1103 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 55: Polish (Update 17) |  | T300 | Confirm the Dynamics controller/OData converter/response mapping stay consistent. | Done
1104 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 56: Frontend — Variants/Materials on Selected POs (View) | US5 | T301 | Add a fetch for reference type 20 data in View Sales Order. | Done
1105 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 56: Frontend — Variants/Materials on Selected POs (View) | US5 | T302 | Add a poLinesByPurchId map of materials/variants per PO. | Done
1106 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 56: Frontend — Variants/Materials on Selected POs (View) | US5 | T303 | Add a new effect to batch-fetch type=20 data for this screen. | Done
1107 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 56: Frontend — Variants/Materials on Selected POs (View) | US5 | T304 | Group the response into poLinesByPurchId inside the fetch handler. | Done
1108 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 56: Frontend — Variants/Materials on Selected POs (View) | US5 | T305 | Replace the static literal columns with real per-PO Variants/Materials values. | Done
1109 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 56: Frontend — Variants/Materials on Selected POs (View) | US5 | T306 | Render a loading/failed-to-load indicator for the two new columns. | Done
1110 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 56: Frontend — Variants/Materials on Selected POs (View) | US5 | T307 | Guardrail: confirm the screen's read-only guarantee is unaffected. | Done
1111 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 57: Polish (Update 18) |  | T308 | Run the frontend manual verification steps from quickstart.md. | To do
1112 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 57: Polish (Update 18) |  | T309 | Review new/changed lines in ViewSalesOrderPage.jsx. | Done
1113 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 57: Polish (Update 18) |  | T310 | Confirm the Dynamics service/controller/OData converter remain unaffected. | Done
1114 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 58: Frontend — Real Logic for the All Toolbar Chip | US5 | T311 | Add tree filter/reparent helper logic for the All mode. | Done
1115 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 58: Frontend — Real Logic for the All Toolbar Chip | US5 | T312 | Add a defaultTemplate state/fetch for the system-wide default template. | Done
1116 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 58: Frontend — Real Logic for the All Toolbar Chip | US5 | T313 | Extend the All chip's click handler to fetch the default template and compute the filtered tree. | Done
1117 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 58: Frontend — Real Logic for the All Toolbar Chip | US5 | T314 | Show a clear empty state when no default template is configured. | Done
1118 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 58: Frontend — Real Logic for the All Toolbar Chip | US5 | T315 | Add a memo computing the set of step IDs across all saved templates. | Done
1119 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 58: Frontend — Real Logic for the All Toolbar Chip | US5 | T316 | Show a no-matching-steps empty state when the filtered All tree is empty. | Done
1120 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 58: Frontend — Real Logic for the All Toolbar Chip | US5 | T317 | Add a memo computing which steps already have mapped documents across templates. | Done
1121 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 58: Frontend — Real Logic for the All Toolbar Chip | US5 | T318 | Add a memo computing the union of files across all saved templates. | Done
1122 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 58: Frontend — Real Logic for the All Toolbar Chip | US5 | T319 | Add an All-active render branch to the Template Checklist. | Done
1123 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 58: Frontend — Real Logic for the All Toolbar Chip | US5 | T320 | Use the union-of-files memo for AVAILABLE FILES when All is active. | Done
1124 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 58: Frontend — Real Logic for the All Toolbar Chip | US5 | T321 | Guardrail: confirm clicking All clears the step filter correctly. | Done
1125 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 58: Frontend — Real Logic for the All Toolbar Chip | US5 | T322 | Guardrail: confirm the page-load default template selection is unaffected by All logic. | Done
1126 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 58: Frontend — Real Logic for the All Toolbar Chip | US5 | T323 | Guardrail: confirm header/Validation Summary aggregate figures are unaffected by All mode. | Done
1127 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 59: Polish (Update 19) |  | T324 | Run the frontend manual verification steps from quickstart.md. | To do
1128 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 59: Polish (Update 19) |  | T325 | Review new/changed lines in ViewSalesOrderPage.jsx and treeUtils.js. | Done
1129 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 59: Polish (Update 19) |  | T326 | Confirm the templates controller/service/repository and Map File remain unaffected. | Done
1130 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 60: Frontend — All as Default Selection on First Open | US5 | T327 | Change the default-selection effect to select All instead of the first template. | Done
1131 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 60: Frontend — All as Default Selection on First Open | US5 | T328 | Add an effect to auto-load default template data now that All is the default. | Done
1132 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 60: Frontend — All as Default Selection on First Open | US5 | T329 | Guardrail: confirm a Sales Order with zero saved templates behaves correctly. | Done
1133 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 60: Frontend — All as Default Selection on First Open | US5 | T330 | Guardrail: confirm All's own fetch/filter/reparent logic is unaffected. | Done
1134 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 61: Polish (Update 20) |  | T331 | Run the frontend manual verification steps from quickstart.md. | To do
1135 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 61: Polish (Update 20) |  | T332 | Review changed lines in ViewSalesOrderPage.jsx for comment clarity. | Done
1136 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 62: Backend — Reshape FolderName to FolderPath |  | T333 | Reshape EutrDownloadZipFolderDto's FolderName field into a nested FolderPath. | Done
1137 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 62: Backend — Reshape FolderName to FolderPath |  | T334 | Update the controller's per-folder name derivation to use FolderPath. | Done
1138 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 62: Backend — Reshape FolderName to FolderPath |  | T335 | Manually verify the updated endpoint directly (e.g. via a REST client). | To do
1139 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 63: Frontend — All Folder in the Download Zip | US5 | T336 | Add a function flattening the step tree into nested folder entries. | Done
1140 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 63: Frontend — All Folder in the Download Zip | US5 | T337 | Add a filesById memo in View Sales Order for the All-folder build. | Done
1141 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 63: Frontend — All Folder in the Download Zip | US5 | T338 | Guardrail: confirm the all-folders-empty message logic still applies including the All folder. | Done
1142 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 63: Frontend — All Folder in the Download Zip | US1 | T339 | Add a default-template fetch to Overview's per-row download for the All folder. | Done
1143 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 63: Frontend — All Folder in the Download Zip | US1 | T340 | Build this row's All-folder entries the same way View does. | Done
1144 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 63: Frontend — All Folder in the Download Zip | US1 | T341 | Guardrail: confirm a failure in the new fetch degrades gracefully. | Done
1145 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 64: Polish (Update 21) |  | T342 | Run the frontend manual verification steps from quickstart.md. | To do
1146 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 64: Polish (Update 21) |  | T343 | Review new/changed lines in the documents controller and download DTOs. | Done
1147 | 005-eutr-sales-orders | EUTR Sales Orders Management | Phase 64: Polish (Update 21) |  | T344 | Confirm several DTO/use-case/API/repository files remain byte-for-byte unchanged. | Done
1148 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 1: Setup |  | T001 | Verify the eutr_reference_types table matches the design (columns/FK); no schema changes. | Done
1149 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 1: Setup |  | T002 | Read the reference backend pattern (EutrStep entity/DTOs/service/controller) for conventions. | Done
1150 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 1: Setup |  | T003 | Read the reference frontend pattern (EutrStep entity/repository/use cases/pages). | Done
1151 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 1: Setup |  | T004 | Read the validation middleware and BaseService to find the extension point for the delete-block rule. | Done
1152 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 2: Foundational |  | T005 | Create the EutrReferenceTypes domain entity. | Done
1153 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 2: Foundational |  | T006 | Create the EutrReferenceTypesRequestDto. | Done
1154 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 2: Foundational |  | T007 | Create the EutrReferenceTypesResponseDto. | Done
1155 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 2: Foundational |  | T008 | Create the EutrReferenceTypesRequestDtoValidator (Name required). | Done
1156 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 2: Foundational |  | T009 | Create the IEutrReferenceTypesService interface with GetPagedAsync. | Done
1157 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 2: Foundational |  | T010 | Implement EutrReferenceTypesService. | Done
1158 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 2: Foundational |  | T011 | Add AutoMapper CreateMap entries for EutrReferenceTypes. | Done
1159 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 2: Foundational |  | T012 | Register the service and validator in DI. | Done
1160 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 2: Foundational |  | T013 | Create EutrReferenceTypesController with 7 CRUD endpoints. | Done
1161 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 2: Foundational |  | T014 | Create the frontend EutrReferenceTypes.js domain entity. | Done
1162 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 2: Foundational |  | T015 | Create the IEutrReferenceTypesRepository.js interface. | Done
1163 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 2: Foundational |  | T016 | Create the eutrReferenceTypesApi.js axios wrapper. | Done
1164 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 2: Foundational |  | T017 | Create RestEutrReferenceTypesRepository.js. | Done
1165 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 2: Foundational |  | T018 | Register the repository in the DI container. | Done
1166 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 2: Foundational |  | T019 | Create the 6 CRUD/paging use cases for reference types. | Done
1167 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 2: Foundational |  | T020 | Create a sample seed SQL for the new menu/permissions (comment-out template, not run). | Done
1168 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 2: Foundational |  | T021 | Seed the menu/permissions on the dev/test Authorization DB. | To do
1169 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 3: User Story 1 | US1 | T022 | Create the useEutrReferenceTypesData.js data-loading hook. | Done
1170 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 3: User Story 1 | US1 | T023 | Create useEutrReferenceTypesColumns.jsx (Name/Created by/Created date/Action columns). | Done
1171 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 3: User Story 1 | US1 | T024 | Create the index.jsx list page (grid, breadcrumb, search, pagination). | Done
1172 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 3: User Story 1 | US1 | T025 | Add the route in RouteResolver.jsx. | Done
1173 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 3: User Story 1 | US1 | T026 | Add the menu item in the ComplianceSystem menu. | Done
1174 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 4: User Story 2 | US2 | T027 | Create EutrReferenceTypesModal.jsx (Name field with validation). | Done
1175 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 4: User Story 2 | US2 | T028 | Wire the Create action into index.jsx with a success snackbar. | Done
1176 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 5: User Story 3 | US3 | T029 | Wire the Edit action into index.jsx, reusing the Create modal. | Done
1177 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 6: User Story 4 | US4 | T030 | Override DeleteAsync in the service to catch FK violations and throw a clear in-use error. | Done
1178 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 6: User Story 4 | US4 | T031 | Override DeleteMultiAsync to check the FK per id, aborting the batch on failure. | Done
1179 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 6: User Story 4 | US4 | T032 | Extend the validation middleware to map InvalidOperationException to a 409 response. | Done
1180 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 6: User Story 4 | US4 | T033 | Create EutrReferenceTypesActionCell.jsx with permission-gated Edit/Delete buttons. | Done
1181 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 6: User Story 4 | US4 | T034 | Wire single and bulk delete into index.jsx with a confirmation dialog. | Done
1182 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 6: User Story 4 | US4 | T035 | Handle the 409 in-use error response without removing the row from the UI. | Done
1183 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 7: Polish & Cross-cutting |  | T036 | Review that all user-facing text is in English. | Done
1184 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 7: Polish & Cross-cutting |  | T037 | Verify permission-based show/hide of Create/Update/Delete controls. | Done
1185 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 7: Polish & Cross-cutting |  | T038 | Run dotnet build with 0 compile errors. | Done
1186 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 7: Polish & Cross-cutting |  | T039 | Run npm lint/build and fix warnings on new files. | Done
1187 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 7: Polish & Cross-cutting |  | T040 | Manually test per quickstart.md's 7 scenarios. | To do
1188 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 8: Setup (Update 1) |  | T041 | Verify the eutr_reference_type_details table matches the design (FKs to types/steps). | Done
1189 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 8: Setup (Update 1) |  | T042 | Read the Apply-to-Customer backend reference pattern (EutrTemplateReferences). | Done
1190 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 8: Setup (Update 1) |  | T043 | Read the Apply-to-Customer frontend pattern plus the EutrStep use case for the Step combobox. | Done
1191 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 9: Foundational (Update 1) |  | T044 | Create the EutrReferenceTypeDetails domain entity. | Done
1192 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 9: Foundational (Update 1) |  | T045 | Create the EutrReferenceTypeDetailsRequestDto. | Done
1193 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 9: Foundational (Update 1) |  | T046 | Create the EutrReferenceTypeDetailsResponseDto with a resolved StepName. | Done
1194 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 9: Foundational (Update 1) |  | T047 | Create the EutrReferenceTypeDetailsRequestDtoValidator. | Done
1195 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 9: Foundational (Update 1) |  | T048 | Create IEutrReferenceTypeDetailsRepository with GetByTypeIdAsync/HasStepAssignedAsync. | Done
1196 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 9: Foundational (Update 1) |  | T049 | Implement EutrReferenceTypeDetailsRepository. | Done
1197 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 9: Foundational (Update 1) |  | T050 | Create the IEutrReferenceTypeDetailsService interface. | Done
1198 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 9: Foundational (Update 1) |  | T051 | Implement EutrReferenceTypeDetailsService with duplicate-assignment validation. | Done
1199 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 9: Foundational (Update 1) |  | T052 | Add AutoMapper CreateMap entries for EutrReferenceTypeDetails. | Done
1200 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 9: Foundational (Update 1) |  | T053 | Register the service/validator/repository in DI. | Done
1201 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 9: Foundational (Update 1) |  | T054 | Create EutrReferenceTypeDetailsController with 4 endpoints, reusing existing policies. | Done
1202 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 9: Foundational (Update 1) |  | T055 | Create the frontend EutrReferenceTypeDetails.js entity. | Done
1203 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 9: Foundational (Update 1) |  | T056 | Create the IEutrReferenceTypeDetailsRepository.js interface. | Done
1204 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 9: Foundational (Update 1) |  | T057 | Create the eutrReferenceTypeDetailsApi.js wrapper. | Done
1205 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 9: Foundational (Update 1) |  | T058 | Create RestEutrReferenceTypeDetailsRepository.js. | Done
1206 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 9: Foundational (Update 1) |  | T059 | Register the repository in the DI container. | Done
1207 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 9: Foundational (Update 1) |  | T060 | Create the 4 CRUD use cases for reference type details. | Done
1208 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 10: User Story 5 | US5 | T061 | Create AssignStepsPage.jsx with breadcrumb, assigned-steps table, and Add/Edit/Delete via a Step combobox. | Done
1209 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 10: User Story 5 | US5 | T062 | Add the route for /eutr/reference-types/assign-steps/:id. | Done
1210 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 10: User Story 5 | US5 | T063 | Add an Assign Steps icon to the reference types list navigating to the new page. | Done
1211 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 11: Polish (Update 1) |  | T064 | Review AssignStepsPage's user-facing text is in English. | Done
1212 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 11: Polish (Update 1) |  | T065 | Verify permission-based show/hide on the Assign Steps page/icon. | Done
1213 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 11: Polish (Update 1) |  | T066 | Run dotnet build for the Update 1 changes. | Done
1214 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 11: Polish (Update 1) |  | T067 | Run npm lint/build for the Update 1 changes. | Done
1215 | 006-eutr-reference-types | EUTR Reference Types Management | Phase 11: Polish (Update 1) |  | T068 | Manually test per quickstart.md's Update 1 Assign Steps scenarios. | To do
1394 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 1: Setup |  | T001 | Confirm the solution builds and existing unit tests run green (baseline). | Done
1395 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 2: Foundational (US1) |  | T002 | Fix the refType=19 gap in ComplDynamicsService's entity mapping and case branch. | Done
1396 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 3: User Story 1 | US1 | T003 | Create EutrSynchronizeSummaryDto with fetched/added/skipped counts. | Done
1397 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 3: User Story 1 | US1 | T004 | Create IEutrSynchronizeDataService interface declaring the sync method. | Done
1398 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 3: User Story 1 | US1 | T005 | Implement SyncSalesOrderTemplatesAsync to sync Sales Order Template data. | Done
1399 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 3: User Story 1 | US1 | T006 | Register the new service in dependency injection. | Done
1400 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 3: User Story 1 | US1 | T007 | Create EutrSynchronizeDataController with the test-so-template-sync endpoint. | Done
1401 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 3: User Story 1 | US1 | T008 | Add unit tests covering User Story 1's four acceptance scenarios. | Done
1402 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 4: User Story 2 | US2 | T009 | Update the case 15 mapping to populate the OrderAccount field. | Done
1403 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 4: User Story 2 | US2 | T010 | Create EutrPurchaseMissingSummaryDto with fetched/flagged/notified counts. | Done
1404 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 4: User Story 2 | US2 | T011 | Extend the interface with SendPurchaseMissingAlertAsync. | Done
1405 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 4: User Story 2 | US2 | T012 | Implement SendPurchaseMissingAlertAsync to flag and email missing documentation. | Done
1406 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 4: User Story 2 | US2 | T013 | Add the test-purchase-missing HTTP GET endpoint to the controller. | Done
1407 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 4: User Story 2 | US2 | T014 | Add unit tests covering User Story 2's ten acceptance scenarios. | Done
1408 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 4: US2 persistence redesign | US2 | T017 | Create the eutr_purchase_missing table migration and bootstrap SQL. | Done
1409 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 4: US2 persistence redesign | US2 | T018 | Create the EutrPurchaseMissing domain entity. | Done
1410 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 4: US2 persistence redesign | US2 | T019 | Create IEutrPurchaseMissingRepository interface. | Done
1411 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 4: US2 persistence redesign | US2 | T020 | Implement EutrPurchaseMissingRepository (delete-all/insert-many/get-all). | Done
1412 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 4: US2 persistence redesign | US2 | T021 | Register the new repository in dependency injection. | Done
1413 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 4: US2 persistence redesign | US2 | T022 | Rewire SendPurchaseMissingAlertAsync to persist findings to the new store. | Done
1414 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 4: US2 persistence redesign | US2 | T023 | Update unit tests for the persisted-store read-back behavior. | Done
1415 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 5: User Story 3 | US3 | T026 | Create EutrSynchronizeTemplatesSummaryDto with eligible/delete/push counts. | Done
1416 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 5: User Story 3 | US3 | T027 | Add GetEligibleForDynamicsSyncAsync repository method for eligible templates. | Done
1417 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 5: User Story 3 | US3 | T028 | Add GetActiveByTemplateIdsAsync repository method for active vendor mappings. | Done
1418 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 5: User Story 3 | US3 | T029 | Extend the interface with SyncTemplatesToDynamicsAsync. | Done
1419 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 5: User Story 3 | US3 | T030 | Implement SyncTemplatesToDynamicsAsync: delete then push templates to the ERP. | Done
1420 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 5: User Story 3 | US3 | T031 | Add the test-synchronize-templates HTTP GET endpoint to the controller. | Done
1421 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 5: User Story 3 | US3 | T032 | Add unit tests covering User Story 3's eight acceptance scenarios. | Done
1422 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 5: US3 left-join correction | US3 | T034 | Rewrite the push phase to left-join, pushing a blank Vendor Code when no mapping exists. | Done
1423 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 5: US3 left-join correction | US3 | T035 | Update unit tests to match the corrected left-join push behavior. | Done
1424 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 6: Polish |  | T024 | Run quickstart.md Part A validation against a live D365 connection (US1). | To do
1425 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 6: Polish |  | T025 | Run quickstart.md Part B validation against live D365/SharePoint/mail/DB (US2). | To do
1426 | 011-eutr-synchronize-data | EUTR Synchronize Data (Sales Order Template Sync + Purchase-Order Missing-Documentation Alert + Outbound Template Sync) | Phase 6: Polish |  | T033 | Run quickstart.md Part C validation against a live D365 sandbox (US3). | To do
1427 | 012-eutr-purchase-orders | EUTR Purchase Orders | Phase 1: Setup |  | T001 | Create a minimal PurchaseOrderOverviewPage.jsx placeholder component. | Done
1428 | 012-eutr-purchase-orders | EUTR Purchase Orders | Phase 1: Setup |  | T002 | Create a minimal PurchaseOrderViewPage.jsx placeholder component. | Done
1429 | 012-eutr-purchase-orders | EUTR Purchase Orders | Phase 2: Foundational |  | T003 | Register the Overview screen route in RouteResolver.jsx. | Done
1430 | 012-eutr-purchase-orders | EUTR Purchase Orders | Phase 2: Foundational |  | T004 | Register the detail screen route in MainRoutes.jsx. | Done
1431 | 012-eutr-purchase-orders | EUTR Purchase Orders | Phase 2: Foundational |  | T005 | Add a static navigation menu entry for EUTR Purchase Orders. | Done
1432 | 012-eutr-purchase-orders | EUTR Purchase Orders | Phase 3: User Story 1 | US1 | T006 | Implement the paged purchase order fetch and base table columns. | Done
1433 | 012-eutr-purchase-orders | EUTR Purchase Orders | Phase 3: User Story 1 | US1 | T007 | Add batched Vendor-name resolution via the reference type 14 lookup. | Done
1434 | 012-eutr-purchase-orders | EUTR Purchase Orders | Phase 3: User Story 1 | US1 | T008 | Add a batched Template-steps fetch for the current page. | Done
1435 | 012-eutr-purchase-orders | EUTR Purchase Orders | Phase 3: User Story 1 | US1 | T009 | Add a batched Documents fetch for the current page's purchase orders. | Done
1436 | 012-eutr-purchase-orders | EUTR Purchase Orders | Phase 3: User Story 1 | US1 | T010 | Compute the Progress column per row, adding no-Template/no-required-steps states. | Done
1437 | 012-eutr-purchase-orders | EUTR Purchase Orders | Phase 3: User Story 1 | US1 | T011 | Add the View action button navigating to the detail screen. | Done
1438 | 012-eutr-purchase-orders | EUTR Purchase Orders | Phase 3: User Story 1 | US1 | T012 | Add loading, error, and empty states for the page-level fetch. | Done
1439 | 012-eutr-purchase-orders | EUTR Purchase Orders | Phase 4: User Story 2 | US2 | T013 | Implement the PO existence check and header (Purch id/Vendor code/name). | Done
1440 | 012-eutr-purchase-orders | EUTR Purchase Orders | Phase 4: User Story 2 | US2 | T014 | Build the template step tree for the viewed purchase order. | Done
1441 | 012-eutr-purchase-orders | EUTR Purchase Orders | Phase 4: User Story 2 | US2 | T015 | Implement the AVAILABLE FILES section showing recorded documents per step. | Done
1442 | 012-eutr-purchase-orders | EUTR Purchase Orders | Phase 4: User Story 2 | US2 | T016 | Render a Progress indicator for the single purchase order. | Done
1443 | 012-eutr-purchase-orders | EUTR Purchase Orders | Phase 4: User Story 2 | US2 | T017 | Wire the Upload action to the document Add dialog, refetching on success. | Done
1444 | 012-eutr-purchase-orders | EUTR Purchase Orders | Phase 4: User Story 2 | US2 | T018 | Wire the Edit action to the document Edit dialog, refetching on success. | Done
1445 | 012-eutr-purchase-orders | EUTR Purchase Orders | Phase 4: User Story 2 | US2 | T019 | Wire the View action to the document file-viewer dialog. | Done
1446 | 012-eutr-purchase-orders | EUTR Purchase Orders | Phase 4: User Story 2 | US2 | T020 | Review the page to confirm no leftover Step 1/Selected POs markup remains. | Done
1447 | 012-eutr-purchase-orders | EUTR Purchase Orders | Phase 5: User Story 3 | US3 | T021 | Extend the backend filter builder with a vendor-code search bucket. | Done
1448 | 012-eutr-purchase-orders | EUTR Purchase Orders | Phase 5: User Story 3 | US3 | T022 | Add a debounced search field filtering by Purch id/Vendor code. | Done
1449 | 012-eutr-purchase-orders | EUTR Purchase Orders | Phase 5: User Story 3 | US3 | T023 | Confirm the No data empty state covers a non-matching search keyword. | Done
1450 | 012-eutr-purchase-orders | EUTR Purchase Orders | Phase 6: Polish |  | T024 | Run the quickstart.md validation checklist end to end against a real environment. | To do
1451 | 012-eutr-purchase-orders | EUTR Purchase Orders | Phase 6: Polish |  | T025 | Review the pages for Vietnamese code comments on non-obvious logic. | Done
1452 | 012-eutr-purchase-orders | EUTR Purchase Orders | Phase 6: Polish |  | T026 | Cross-check that Overview and View screen Progress figures match. | To do
1453 | 012-eutr-purchase-orders | EUTR Purchase Orders | Post-implementation fix |  | T027 | Fix the by-codes template query, which was missing an IsHide=0 filter. | Done
1454 | 012-eutr-purchase-orders | EUTR Purchase Orders | Post-implementation fix |  | T028 | Fix document lookup to also include Vendor code for Vendor-type steps. | Done
1455 | 012-eutr-purchase-orders | EUTR Purchase Orders | Post-implementation fix |  | T029 | Backport the Vendor-code document-lookup fix to the 005-eutr-sales-orders screens. | Done
1456 | 012-eutr-purchase-orders | EUTR Purchase Orders | Post-implementation fix |  | T030 | Check and fix Download functions for the same Vendor-code lookup gap. | Done
1457 | 012-eutr-purchase-orders | EUTR Purchase Orders | Post-implementation fix |  | T031 | Fix the 011 purchase-missing check to include Vendor code in its document lookup. | Done
1498 | 014-map-product-test | Map for Product Test — Complete Record Visibility | Phase 1: Setup |  | T001 | Reconfirm live DB stored procedure definitions match earlier research analysis. | Done
1499 | 014-map-product-test | Map for Product Test — Complete Record Visibility | Phase 1: Setup |  | T002 | Re-run data-verification query for MAS-01104/MAS-01105; discover the paging_count proc has the same bug. | Done
1500 | 014-map-product-test | Map for Product Test — Complete Record Visibility | Phase 2: Foundational |  | T003 | Create the migration file for the IsDelete guard fix and MAS-01104 data correction. | Done
1501 | 014-map-product-test | Map for Product Test — Complete Record Visibility | Phase 3: User Story 1 | US1 | T004a | Add the IsDelete guard fix to compl_sp_get_compl_master_paging_count procedure. | Done
1502 | 014-map-product-test | Map for Product Test — Complete Record Visibility | Phase 3: User Story 1 | US1 | T004 | Add IsDelete=0 guard to all three EXISTS occurrences in compl_sp_get_compl_master_paging. | Done
1503 | 014-map-product-test | Map for Product Test — Complete Record Visibility | Phase 3: User Story 1 | US1 | T005 | Add the same IsDelete guard to compl_sp_get_compl_master_missing_for_alert procedure. | Done
1504 | 014-map-product-test | Map for Product Test — Complete Record Visibility | Phase 3: User Story 1 | US1 | T006 | Add an UPDATE fixing MAS-01104's condition row ComplType from 0 to 1. | Done
1505 | 014-map-product-test | Map for Product Test — Complete Record Visibility | Phase 3: User Story 1 | US1 | T007 | Update the repo mirror copy of compl_sp_get_compl_master_paging.sql. | Done
1506 | 014-map-product-test | Map for Product Test — Complete Record Visibility | Phase 3: User Story 1 | US1 | T008 | Update the repo mirror copy of compl_sp_get_compl_master_missing_for_alert.sql. | Done
1507 | 014-map-product-test | Map for Product Test — Complete Record Visibility | Phase 3: User Story 1 | US1 | T009 | Apply the migration to the dev database. | Done
1508 | 014-map-product-test | Map for Product Test — Complete Record Visibility | Phase 3: User Story 1 | US1 | T010 | Re-verify MAS-01104's computed Status is now 'Missing'. | Done
1509 | 014-map-product-test | Map for Product Test — Complete Record Visibility | Phase 3: User Story 1 | US1 | T011 | UI validation that MAS-01104 appears in the Map for product test tab. | Done
1510 | 014-map-product-test | Map for Product Test — Complete Record Visibility | Phase 4: User Story 2 | US2 | T012 | Regression check: an active-compliance master still shows OK, excluded from Missing. | Done
1511 | 014-map-product-test | Map for Product Test — Complete Record Visibility | Phase 4: User Story 2 | US2 | T013 | Regression check: no master disappeared from the Map general tab. | Done
1512 | 014-map-product-test | Map for Product Test — Complete Record Visibility | Phase 4: User Story 2 | US2 | T014 | Regression check: the missing-alert procedure output is consistent with the paging fix. | Done
1513 | 014-map-product-test | Map for Product Test — Complete Record Visibility | Phase 5: Polish |  | T015 | Update the repo mirror of compl_sp_get_compl_master_paging_count.sql (scope expanded). | Done
1514 | 014-map-product-test | Map for Product Test — Complete Record Visibility | Phase 5: Polish |  | T016 | Document that the root cause of the lost ComplType marker remains uninvestigated. | Done